## Decision brief
Corrected specimen-retention operating plan
Tidewater Health Network ¦ Controlled-response reading ¦ Prepared for Hana Merriweather ¦ Source: tidewater_transition_snapshot.xlsx
Decision status | CONTROLLED RESPONSE - NO COMPLIANT TRANSITION |  | On the supplied snapshot, no candidate can claim compliant completion by 17 April 2026. Ontario and New York each require a separate validation, requiring 10 + 8 hours, while the sole cross-border validation processing bench has a 12-hour slot. S3 is the sole eligible controlled response: hold the transition, leave both validations pending, and preserve the correction path. This workbook is not an approval of a completed transition.
Selected package | S3
Interpretation | Controlled-response reading
Completion deadline | 2026-04-17
Projection through | 2026-09-30
Required validation hours | 18
Sole-slot capacity | 12
Capacity shortfall | 6
SELECTION AND COVERAGE AUDIT
Scenario | Description | Status | Transition labor | Validation prep | Incremental storage | Deferral / hold | Other support | Package total | Eligible under reading | Selected? | Required activities | Completion claim | Selection rule
S1 | Standard internal transition | Near miss - shared slot over capacity | 4500 | 1200 | 1600 | 0 | 1000 | 8300 | No - mandatory validations require 18 hours against 12 |  | VAL-ON; VAL-NY | Yes | Not eligible as compliant because the mandatory validation occupancy exceeds the sole slot
S2 | Expedited transition with additional internal effort | Near miss - same mandatory validation bottleneck | 6800 | 2200 | 2600 | 0 | 1250 | 12850 | No - extra effort does not create shared-bench capacity |  | VAL-ON; VAL-NY | Yes | Not eligible as compliant because additional effort does not create shared-bench capacity
S3 | Controlled hold and documented no-compliant-selection response | Eligible controlled response - transition held | 2100 | 850 | 1800 | 5200 | 750 | 10700 | Yes - controlled response only; no completion claim | SELECTED | VAL-ON; VAL-NY (pending) | No | Eligible only when it reports no compliant transition selection and leaves blocked validation work pending
S4 | Partial validation transition | Near-miss distractor - incomplete validation coverage | 1500 | 450 | 900 | 0 | 250 | 3100 | No - New York validation is omitted |  | VAL-ON only | Yes | Ineligible because it leaves one mandatory jurisdictional validation unaddressed
Mandatory criterion | S1 | S2 | S3 | S4 | Selected package | Evidence
regulatory basis and source reconciliation | Y | Y | Y | Y | Y | Source reconciliation
five-stage prerequisite chain and deadline status | Y | Y | Y | Y | Y | Prerequisites & validation
validation capacity and infeasibility assessment | Y | Y | Y | N | Y | Prerequisites & validation
capacity projection through 2026-09-30 | Y | Y | Y | Y | Y | Capacity projection
financial impact through 2026-09-30 | Y | Y | Y | Y | Y | Financial impact
executable corrections with owners and timing | Y | Y | Y | Y | Y | Corrections register
Coverage result | ALL SIX MANDATORY CRITERIA COVERED
DECISION BASIS
Evidence area | Conclusion / operating implication
Regulatory basis | Frozen regulatory snapshot governs jurisdictional fields. Ontario remains 10 years and New York remains 6 years; later 7-year / 5-year internal values are not adopted for those fields.
Prerequisite status | P1 is in review, P3 is blocked by the shared-slot shortfall, and P4/P5 remain pending predecessors. No successor is shown as started.
Capacity | Ontario and New York are projected separately. Storage headroom becomes negative in each jurisdiction later in the period; the validation bench is a distinct 18-hour versus 12-hour bottleneck.
Financial effect | The selected S3 package cost is linked to its five source-supported components. Routine labor, processing and storage plus response components are carried through 30 September 2026 on the Financial impact sheet.
Execution | The correction register assigns each material gap to a named source-supported owner with timing, status and dependency for Hana's review.
Review boundary: this plan uses only the supplied frozen snapshot and verified internal records. It records an operational controlled response and does not add external legal interpretation.

## Source reconciliation
Source reconciliation and adopted jurisdictional basis
Regulatory fields use frozen snapshot precedence; operational fields use verified internal records where they do not override a regulatory requirement.
PRECEDENCE APPLIED
Precedence statement: the frozen Ontario-New York regulatory snapshot governs jurisdictional and regulatory requirements, regardless of later internal record dates. Verified internal records govern operational capacity, inventory, workflow, labor, storage, processing and cost fields only where they do not override a regulatory requirement.
MATERIAL CONFLICTS AND ADOPTED VALUES
Jurisdiction | Field | Frozen regulatory value | Frozen source / authority | Frozen date | Internal value | Internal source / date | Adopted value | Reason under precedence | Operational effect
Ontario | Retention minimum | 10 years | REG-ON-RET ¦ Ontario regulatory snapshot | 2025-12-15 | 7 years | INT-ON-RET ¦ Retention policy register v4 | 10 years | Use frozen regulatory requirement | Ontario records retain for 10 years
Ontario | Validation treatment | Mandatory Ontario validation; legally segregated | REG-ON-VAL ¦ Ontario regulatory snapshot | 2025-12-15 | Single cross-border review | INT-ON-VAL ¦ Cross-border workflow memo 2026-02 | Mandatory Ontario validation; legally segregated | Use frozen regulatory requirement | Ontario validation remains separate
New York | Retention minimum | 6 years | REG-NY-RET ¦ New York regulatory snapshot | 2025-12-15 | 5 years | INT-NY-RET ¦ Retention policy register v4 | 6 years | Use frozen regulatory requirement | New York records retain for 6 years
New York | Validation treatment | Mandatory New York validation; legally segregated | REG-NY-VAL ¦ New York regulatory snapshot | 2025-12-15 | Single cross-border review | INT-NY-VAL ¦ Cross-border workflow memo 2026-02 | Mandatory New York validation; legally segregated | Use frozen regulatory requirement | New York validation remains separate
ADOPTED JURISDICTION VIEW
Jurisdiction | Retention minimum | Mandatory validation | Legally segregated | Controlled repository | Effective from | Governing source | Use in plan
Ontario | 10 years | Ontario retention validation | Yes | Ontario-controlled archive | 2026-01-01 | REG-ON-RET / REG-ON-VAL | Adopted regulatory basis
New York | 6 years | New York retention validation | Yes | New York-controlled archive | 2026-01-01 | REG-NY-RET / REG-NY-VAL | Adopted regulatory basis
SOURCE REGISTER REFERENCES
Record ID | Source class | Authority / register | Record date | Effective date | Jurisdiction | Field | Value
REG-ON-RET | Frozen regulatory snapshot | Ontario regulatory snapshot | 2025-12-15 | 2026-01-01 | Ontario | Retention minimum | 10 years
REG-ON-VAL | Frozen regulatory snapshot | Ontario regulatory snapshot | 2025-12-15 | 2026-01-01 | Ontario | Validation treatment | Mandatory Ontario validation; legally segregated
REG-NY-RET | Frozen regulatory snapshot | New York regulatory snapshot | 2025-12-15 | 2026-01-01 | New York | Retention minimum | 6 years
REG-NY-VAL | Frozen regulatory snapshot | New York regulatory snapshot | 2025-12-15 | 2026-01-01 | New York | Validation treatment | Mandatory New York validation; legally segregated
INT-ON-RET | Verified internal record | Retention policy register v4 | 2026-02-20 | 2026-02-20 | Ontario | Retention minimum | 7 years
INT-ON-VAL | Verified internal record | Cross-border workflow memo 2026-02 | 2026-02-20 | 2026-02-20 | Ontario | Validation treatment | Single cross-border review
INT-NY-RET | Verified internal record | Retention policy register v4 | 2026-02-20 | 2026-02-20 | New York | Retention minimum | 5 years
INT-NY-VAL | Verified internal record | Cross-border workflow memo 2026-02 | 2026-02-20 | 2026-02-20 | New York | Validation treatment | Single cross-border review
Reconciliation note: the later internal records are retained as evidence of the conflict and are not silently deleted. They remain useful for operational context, but the adopted jurisdictional fields above are the frozen values.

## Prerequisites & validation
Prerequisite chain and shared validation capacity
The five source-defined stages remain in dependency order. The controlled response leaves both legally segregated validations pending.
DEADLINE ASSESSMENT
Deadline | 2026-04-17
Interpretation | Controlled-response reading
Deadline status | INCOMPLETE - no compliant transition selection exists
Control response | S3 hold; both mandatory validations pending; downstream stages not started
FIVE-STAGE PREREQUISITE CHAIN
Stage ID | Stage name (source terminology) | Predecessor | Target start | Target finish | Duration days | Current / adopted status | Actual start | Actual finish | Dependency check | Gate / evidence | Owner
P1 | Regulatory basis and source reconciliation | - | 2026-04-01 | 2026-04-02 | 2 | In review - adopted values recorded | Not recorded | Not recorded | Gate open for reconciliation record | Four regulatory-field conflicts require adoption | Ibrahim Asante
P2 | Capacity and cost baseline | P1 | 2026-04-03 | 2026-04-07 | 3 | Ready after P1 | Not recorded | Not recorded | Held behind P1 | Uses verified internal operational records | Theo Dimitrov
P3 | Validation slot reservation | P2 | 2026-04-08 | 2026-04-10 | 1 | BLOCKED - 6-hour slot shortfall | Not started | Not started | FAIL: 18 required > 12 available | 10 + 8 hours against 12-hour sole bench | Renata Guerrero
P4 | Retention transfer and verification | P3 | 2026-04-13 | 2026-04-16 | 4 | PENDING - P3 blocked | Not started | Not started | Not started; predecessor P3 blocked | Both jurisdiction validations required | Theo Dimitrov
P5 | Operational handoff and approval | P4 | 2026-04-17 | 2026-04-17 | 1 | PENDING - P4 blocked | Not started | Not started | Not started; predecessor P4 pending | Hana approval follows complete chain | Hana Merriweather
MANDATORY VALIDATION ACTIVITIES
Activity ID | Jurisdiction | Validation activity | Required hours | Required date | Segregation | Qualified resource pool | Assigned resource | Status | Booking state | Certification dependency | Source basis
VAL-ON | Ontario | Ontario retention validation | 10 | 2026-04-10 | No overlap with New York validation | Hana Merriweather; Renata Guerrero | Not assigned | PENDING - no compliant slot | Not booked | Active cross-jurisdiction validation | VAL-ON ¦ frozen snapshot
VAL-NY | New York | New York retention validation | 8 | 2026-04-10 | No overlap with Ontario validation | Hana Merriweather; Renata Guerrero | Not assigned | PENDING - no compliant slot | Not booked | Active cross-jurisdiction validation | VAL-NY ¦ frozen snapshot
SOLE PROCESSING-SLOT ASSESSMENT
Shared resource | Available date | Available hours | Currently booked | Ontario hours | New York hours | Required combined | Shortfall | Non-overlap check | Capacity check | Booking result | Interpretation
sole cross-border validation processing bench | 2026-04-10 | 12 | 0 | 10 | 8 | 18 | 6 | NO OVERLAP BOOKED | FAIL | HOLD - both validations pending | Legally segregated activities compete for the sole slot
Required hours | 18 | Slot capacity | 12 | Shortfall | 6 |  |  |  | No compliant booking is shown. The two activities remain pending/rejected for scheduling purposes; any future assignment must use an active certified resource and a non-overlapping slot with sufficient capacity.
CERTIFICATION AND RESOURCE CHECK
Name | Primary role | Other supported work | Certification | Status | Validation eligible? | Source-supported assignment use
Ibrahim Asante | operations manager | source reconciliation | None listed | Not held | No - certification not held | May support non-validation work
Hana Merriweather | approval | cross-jurisdiction validation | active cross-jurisdiction validation | Active | Yes - active certification | May be assigned to either validation when capacity is available
Theo Dimitrov | capacity analysis | operations correction | None listed | Not held | No - certification not held | May support non-validation work
Renata Guerrero | cross-jurisdiction validation | quality review | active cross-jurisdiction validation | Active | Yes - active certification | May be assigned to either validation when capacity is available
Estelle Ingram | financial analysis | document control | None listed | Not held | No - certification not held | May support non-validation work
Assignment control: Hana Merriweather and Renata Guerrero are the only source-listed people with active cross-jurisdiction validation certification. Because the shared slot is infeasible, neither validation is assigned in this controlled response. Ibrahim, Theo and Estelle are assigned to corrections within their source-supported roles.

## Capacity projection
Jurisdiction-specific capacity projection
Period: 1 April 2026 through 30 September 2026 ¦ Ontario and New York remain separate; headroom is not pooled.
ADOPTED PROJECTION BASIS
Input | Adopted value | Basis / use |  | Calculation definitions: projected retained inventory = opening retained inventory + projected intake; processing headroom = available processing capacity - routine processing volume; storage headroom = available storage capacity - projected retained inventory. The shared validation bench is assessed separately on the prerequisite sheet.
Projection start | 2026-04-01 | Frozen snapshot metadata
Projection end | 2026-09-30 | Frozen snapshot metadata
Ontario retention minimum | 10 years | Adopted frozen regulatory value
New York retention minimum | 6 years | Adopted frozen regulatory value
Operational input rule | Verified internal records | Capacity, inventory, labor and cost fields
Pooling rule | No pooling across jurisdictions | Each headroom value is calculated separately
CAPACITY AND HEADROOM
Period start | Period end | Jurisdiction | Retention years | Opening retained | Projected intake | Projected retained | Routine processing | Processing capacity | Processing headroom | Storage capacity | Storage headroom | Storage status | Processing status
2026-04-01 | 2026-04-30 | Ontario | 10 years | 8900 | 420 | 9320 | 400 | 520 | 120 | 9800 | 480 | OK | OK
2026-05-01 | 2026-05-31 | Ontario | 10 years | 9320 | 460 | 9780 | 440 | 540 | 100 | 10000 | 220 | OK | OK
2026-06-01 | 2026-06-30 | Ontario | 10 years | 9780 | 500 | 10280 | 480 | 560 | 80 | 10200 | -80 | SHORT | OK
2026-07-01 | 2026-07-31 | Ontario | 10 years | 10280 | 520 | 10800 | 500 | 570 | 70 | 10500 | -300 | SHORT | OK
2026-08-01 | 2026-08-31 | Ontario | 10 years | 10800 | 540 | 11340 | 520 | 580 | 60 | 11000 | -340 | SHORT | OK
2026-09-01 | 2026-09-30 | Ontario | 10 years | 11340 | 560 | 11900 | 540 | 590 | 50 | 11400 | -500 | SHORT | OK
2026-04-01 | 2026-04-30 | New York | 6 years | 6100 | 300 | 6400 | 290 | 400 | 110 | 7200 | 800 | OK | OK
2026-05-01 | 2026-05-31 | New York | 6 years | 6400 | 330 | 6730 | 320 | 420 | 100 | 7200 | 470 | OK | OK
2026-06-01 | 2026-06-30 | New York | 6 years | 6730 | 360 | 7090 | 350 | 430 | 80 | 7400 | 310 | OK | OK
2026-07-01 | 2026-07-31 | New York | 6 years | 7090 | 380 | 7470 | 370 | 440 | 70 | 7600 | 130 | OK | OK
2026-08-01 | 2026-08-31 | New York | 6 years | 7470 | 400 | 7870 | 390 | 450 | 60 | 7900 | 30 | OK | OK
2026-09-01 | 2026-09-30 | New York | 6 years | 7870 | 420 | 8290 | 410 | 460 | 50 | 8200 | -90 | SHORT | OK
COST INPUTS USED BY FINANCIAL IMPACT
Period start | Jurisdiction | Labor hours | Labor rate | Storage rate | Processing rate | Projected retained | Labor cost | Processing cost | Storage cost | Record ID | Record date
2026-04-01 | Ontario | 96 | 42 | 0.18 | 3.25 | 9320 | 4032 | 1300 | 1677.6 | OPS-ON-APR | 2026-03-01
2026-05-01 | Ontario | 102 | 42 | 0.18 | 3.25 | 9780 | 4284 | 1430 | 1760.4 | OPS-ON-MAY | 2026-03-01
2026-06-01 | Ontario | 110 | 42 | 0.18 | 3.25 | 10280 | 4620 | 1560 | 1850.4 | OPS-ON-JUN | 2026-03-01
2026-07-01 | Ontario | 114 | 42 | 0.18 | 3.25 | 10800 | 4788 | 1625 | 1944 | OPS-ON-JUL | 2026-03-01
2026-08-01 | Ontario | 118 | 42 | 0.18 | 3.25 | 11340 | 4956 | 1690 | 2041.2 | OPS-ON-AUG | 2026-03-01
2026-09-01 | Ontario | 122 | 42 | 0.18 | 3.25 | 11900 | 5124 | 1755 | 2142 | OPS-ON-SEP | 2026-03-01
2026-04-01 | New York | 72 | 46 | 0.21 | 3.75 | 6400 | 3312 | 1087.5 | 1344 | OPS-NY-APR | 2026-03-01
2026-05-01 | New York | 74 | 46 | 0.21 | 3.75 | 6730 | 3404 | 1200 | 1413.3 | OPS-NY-MAY | 2026-03-01
2026-06-01 | New York | 78 | 46 | 0.21 | 3.75 | 7090 | 3588 | 1312.5 | 1488.9 | OPS-NY-JUN | 2026-03-01
2026-07-01 | New York | 82 | 46 | 0.21 | 3.75 | 7470 | 3772 | 1387.5 | 1568.7 | OPS-NY-JUL | 2026-03-01
2026-08-01 | New York | 86 | 46 | 0.21 | 3.75 | 7870 | 3956 | 1462.5 | 1652.7 | OPS-NY-AUG | 2026-03-01
2026-09-01 | New York | 90 | 46 | 0.21 | 3.75 | 8290 | 4140 | 1537.5 | 1740.9 | OPS-NY-SEP | 2026-03-01
Capacity reading: Ontario reaches negative storage headroom in June-September and New York reaches negative storage headroom in September. These shortages are shown by jurisdiction and are not averaged away. Routine processing headroom remains visible separately.

## Financial impact
Financial impact through 30 September 2026
Selected package S3 ¦ USD planning view ¦ Routine operations are calculated by jurisdiction, then selected controlled-response components are added.
Selected package | S3 |  | Package cost | 10700 |  | Period total impact | 98647.6
SCENARIO PACKAGE COST COMPARISON
Scenario | Description | Status | Transition labor | Validation prep | Incremental storage | Deferral / hold | Other support | Calculated package cost | Eligible? | Selected? | Coverage | Required activities | Selection rule
S1 | Standard internal transition | Near miss - shared slot over capacity | 4500 | 1200 | 1600 | 0 | 1000 | 8300 | No - mandatory validations require 18 hours against 12 |  | All six criteria | VAL-ON; VAL-NY | Not eligible as compliant because the mandatory validation occupancy exceeds the sole slot
S2 | Expedited transition with additional internal effort | Near miss - same mandatory validation bottleneck | 6800 | 2200 | 2600 | 0 | 1250 | 12850 | No - extra effort does not create shared-bench capacity |  | All six criteria | VAL-ON; VAL-NY | Not eligible as compliant because additional effort does not create shared-bench capacity
S3 | Controlled hold and documented no-compliant-selection response | Eligible controlled response - transition held | 2100 | 850 | 1800 | 5200 | 750 | 10700 | Yes - controlled response only; no completion claim | SELECTED | All six criteria | VAL-ON; VAL-NY (pending) | Eligible only when it reports no compliant transition selection and leaves blocked validation work pending
S4 | Partial validation transition | Near-miss distractor - incomplete validation coverage | 1500 | 450 | 900 | 0 | 250 | 3100 | No - New York validation is omitted |  | 5 of 6 criteria | VAL-ON only | Ineligible because it leaves one mandatory jurisdictional validation unaddressed
Least-cost eligible interpretation | S3 - sole eligible controlled response
PERIOD FINANCIAL IMPACT
Period | Ontario labor | New York labor | Ontario processing | New York processing | Ontario storage | New York storage | Routine operations | Response labor | Validation prep | Incremental storage | Deferral / hold | Other support | Total impact
2026-04-01 | 4032 | 3312 | 1300 | 1087.5 | 1677.6 | 1344 | 12753.1 | 2100 | 850 | 300 | 866.6667 | 750 | 17619.7667
2026-05-01 | 4284 | 3404 | 1430 | 1200 | 1760.4 | 1413.3 | 13491.7 | 0 | 0 | 300 | 866.6667 | 0 | 14658.3667
2026-06-01 | 4620 | 3588 | 1560 | 1312.5 | 1850.4 | 1488.9 | 14419.8 | 0 | 0 | 300 | 866.6667 | 0 | 15586.4667
2026-07-01 | 4788 | 3772 | 1625 | 1387.5 | 1944 | 1568.7 | 15085.2 | 0 | 0 | 300 | 866.6667 | 0 | 16251.8667
2026-08-01 | 4956 | 3956 | 1690 | 1462.5 | 2041.2 | 1652.7 | 15758.4 | 0 | 0 | 300 | 866.6667 | 0 | 16925.0667
2026-09-01 | 5124 | 4140 | 1755 | 1537.5 | 2142 | 1740.9 | 16439.4 | 0 | 0 | 300 | 866.6667 | 0 | 17606.0667
Through 2026-09-30 | 27804 | 22172 | 9360 | 7987.5 | 11415.6 | 9208.5 | 87947.6 | 2100 | 850 | 1800 | 5200 | 750 | 98647.6
FINANCIAL RECONCILIATION
Component | Through 30 September 2026 | Calculation / source basis | Control check
Routine labor | 49976 | Separate Ontario and New York labor ledgers | OK
Routine processing | 17347.5 | Separate Ontario and New York processing ledgers | OK
Routine storage | 20624.1 | Separate Ontario and New York retained-inventory ledgers | OK
Selected response labor | 2100 | Selected package transition labor component | OK
Validation preparation | 850 | Selected package validation-preparation component | OK
Incremental storage | 1800 | Selected package incremental-storage component spread over 6 periods | OK
Deferral / hold | 5200 | Selected package deferral component spread over 6 periods | OK
Other support | 750 | Selected package amendment-support component | OK
Total projected financial impact | 98647.6 | Routine components plus selected response components | OK
Financial reading: the S3 package cost is the five source-supported response components shown in the scenario table. The period impact additionally includes routine jurisdiction-specific labor, processing and storage costs through 30 September 2026. No cost is assigned to an unperformed validation.

## Corrections register
Executable correction register
Named owners and timing are drawn from the supplied resource pool; each action is linked to a gate, dependency or evidence point.
MATERIAL CORRECTIONS
ID | Material gap | Executable action | Owner | Timing / due | Status | Dependency / evidence | Output for Hana | Source gap outcome | Priority
G1 | Regulatory-field reconciliation | Adopt the frozen Ontario 10-year and New York 6-year values; retain the 7-year / 5-year internal rows as conflicts for traceability. | Ibrahim Asante | By 2 April 2026 | Open | P1 | Adopted values recorded in Source reconciliation | Adopt frozen regulatory values and retain internal values as conflicting records | High
G2 | Validation-slot conflict | Keep VAL-ON and VAL-NY unbooked; document the 18-hour requirement against the 12-hour bench and obtain a capacity decision before booking. | Renata Guerrero | Before 10 April 2026 slot | Blocked | P3 | Validation infeasibility and pending status | Keep both activities pending until capacity is resolved; do not claim completion | High
G3 | Prerequisite/deadline status | Update the stage gates, mark P3 blocked and P4/P5 pending, and carry the no-compliant-selection finding to the deadline record. | Ibrahim Asante | By 17 April 2026 | Open | P3 | Deadline status and controlled-response record | Record no compliant transition selection and preserve predecessor gates | High
G4 | Capacity update | Refresh Ontario and New York inventory, processing and storage headroom separately through 30 September 2026. | Theo Dimitrov | Weekly through 30 September 2026 | Open | P2; capacity ledger | Jurisdiction-specific capacity ledger | Refresh jurisdiction-specific projection through 30 September 2026 | Medium
G5 | Financial amendment support | Attach the S3 component total and the period financial impact to the cross-border amendment working papers. | Estelle Ingram | By 7 April 2026 | Open | P2; S3 cost basis | Reconciled cost support | Attach S3 package cost and period financial impact | Medium
G6 | Controlled-response approval | Review the controlled-response package and record approval or rejection; do not approve a completed-transition claim. | Hana Merriweather | By 17 April 2026 | Awaiting approval | G1-G5 | Approval record for the documented hold | Approve or reject the documented hold response; do not approve a completion claim | High
RESOURCE QUALIFICATION REGISTER
Name | Primary role | Other supported work | Certification | Status | Eligible validation work | Source date / active through
Ibrahim Asante | operations manager | source reconciliation | None listed | Not held | No - not certified; non-validation work only | 2026-09-30
Hana Merriweather | approval | cross-jurisdiction validation | active cross-jurisdiction validation | Active | Yes - either validation when slot permits | 2026-09-30
Theo Dimitrov | capacity analysis | operations correction | None listed | Not held | No - not certified; non-validation work only | 2026-09-30
Renata Guerrero | cross-jurisdiction validation | quality review | active cross-jurisdiction validation | Active | Yes - either validation when slot permits | 2026-09-30
Estelle Ingram | financial analysis | document control | None listed | Not held | No - not certified; non-validation work only | 2026-09-30
Execution control: the two validation activities are deliberately unassigned in S3 because no compliant slot exists. Hana Merriweather and Renata Guerrero are the only qualified validation resources; Ibrahim Asante, Theo Dimitrov and Estelle Ingram are used for reconciliation, capacity and financial/document-control corrections within the roles supplied.