## Conditions Register
Specific Conditions Register ¦ Lars Lombardi ¦ culvert activity
Hazard-mitigation subaward ¦ approximately $140,000 already drawn ¦ work approximately half complete ¦ issued 2026-08-20
Condition ID | Policy condition label | Policy basis | Responsible party | Due / response point | Required evidence | Status | Issue / escalation | Reviewer notes
SC-01 | Accounting and Supporting-Records Package | §3(a), §5, §6 | Lars Lombardi | 10 business days after receipt (2026-09-03 if received 2026-08-20) | Accounting of approx. $140,000 drawn; expenditures, dates, vendors/payees, allowability support | Pending Evidence | If incomplete: request clarification/missing evidence; document any Substantiated Issue; refer proposed adverse action through authorized process. | Pending Evidence is not proof of noncompliance.
SC-02 | Remaining-Work and Schedule/Status Report | §3(b), §5 | Lars Lombardi | 10 business days after receipt (2026-09-03) | Current status/percentage; work remaining; schedule; barriers | Pending Evidence | Same bounded escalation sequence; no automatic termination or acceleration. | Work is approx. half complete.
SC-03 | Material Change Notice | §4, §5 | Lars Lombardi | 10 business days after receipt; promptly identify material changes | Notice identifying changes affecting performance, record access, or ability to complete | Pending Evidence | Review whether reported change affects performance or records; document issue if substantiated. | No inference from silence.
SC-04 | Future Draw/Reimbursement Support | §3(c), §5 | Lars Lombardi | With each future draw or reimbursement request | Costs incurred and source records | Pending Evidence | Request missing support; record status as Under Review until assessed. | Supports conditional review of allowable, supported costs.
SC-05 | Completion/Closeout Evidence | §3(d), §5 | Lars Lombardi | When culvert work is complete and before final closeout review | Completion documentation and final supporting records | Pending Evidence | Request missing evidence; document any Substantiated Issue; authorized-process referral only. | Does not promise reimbursement or continued funding.
Status vocabulary: Pending Evidence ¦ Incomplete Evidence ¦ Under Review ¦ Substantiated Issue ¦ Complete
Exported 2026-08-20 for peer review