## Operating Plan
Cobblemoor Provisions ¦ corrected maintenance-access operating plan
Inspection preparation record ¦ prepared for peer review ¦ source schedule retained with permitted normalization and documented duplicate disposition
Selected candidate |  | Candidate B |  |  |  | Inspection result |  | Compliant |  |  |  | Overall status |  | Pending approval
Site jurisdiction |  | England |  |  |  | Prepared by |  | Tadeo Penrose |  |  |  | Peer reviewer |  | Isabel Tikhonov
Inspection date |  | 2026-06-05 |  |  |  | Peer-review due |  | 2026-06-10 12:00 |  |  |  | Approval decision |  | Pending approval
Assurance summary (live calculations)
Required activities | 16 |  |  |  |  | Scheduled activities | 16 |  |  |  |  | Planned maintenance minutes | 570
Zone transitions | 1 |  |  |  |  | Changeover minutes | 30 |  |  |  |  | Schedule compliance | PASS
Plan row | Activity ID | Activity | Class | Date | Start | Finish | Elapsed min | Registered min | Location | Zone | Electrician | Escort | Noisy | Predecessor | Source candidate | Source row | Disposition | Duration check | Changeover min | Access check | Precedence check | Compliance
1 | A01 | North lockout setup | Maintenance | 2026-06-16 | 8:00 | 8:30 | 30 | 30 | North Electrical Room | North | Yes | 1 | No |  | Candidate B | B-001 | Corrected | PASS | 0 | PASS | PASS | PASS
2 | A09 | Noisy functional test 1 | Maintenance | 2026-06-16 | 8:00 | 9:00 | 60 | 60 | Test Bay | Test | No | 1 | Yes |  | Candidate B | B-009 | Corrected | PASS | 0 | PASS | PASS | PASS
3 | A02 | North isolation | Maintenance | 2026-06-16 | 8:30 | 9:30 | 60 | 60 | North Electrical Room | North | Yes | 1 | No | A01 | Candidate B | B-002 | Corrected | PASS | 0 | PASS | PASS | PASS
4 | A03 | North isolation-dependent work | Maintenance | 2026-06-16 | 9:30 | 10:30 | 60 | 60 | North Electrical Room | North | Yes | 1 | No | A02 | Candidate B | B-003 | Corrected | PASS | 0 | PASS | PASS | PASS
5 | P01 | Public counter - morning 16 June | Public-counter service | 2026-06-16 | 9:30 | 12:00 | 150 | 150 | Public Counter | None | No | 0 | No |  | Candidate B | B-013 | Corrected | PASS | 0 | PASS | PASS | PASS
6 | A04 | North re-energisation | Maintenance | 2026-06-16 | 10:30 | 11:00 | 30 | 30 | North Electrical Room | North | Yes | 1 | No | A03 | Candidate B | B-004 | Corrected | PASS | 0 | PASS | PASS | PASS
7 | A05 | South lockout setup | Maintenance | 2026-06-16 | 11:30 | 12:00 | 30 | 30 | South Electrical Room | South | Yes | 1 | No |  | Candidate B | B-005 | Corrected | PASS | 30 | PASS | PASS | PASS
8 | A06 | South isolation | Maintenance | 2026-06-16 | 12:00 | 13:00 | 60 | 60 | South Electrical Room | South | Yes | 1 | No | A05 | Candidate B | B-006 | Corrected | PASS | 0 | PASS | PASS | PASS
9 | A07 | South isolation-dependent work | Maintenance | 2026-06-16 | 13:00 | 14:00 | 60 | 60 | South Electrical Room | South | Yes | 1 | No | A06 | Candidate B | B-007 | Corrected | PASS | 0 | PASS | PASS | PASS
10 | P02 | Public counter - afternoon 16 June | Public-counter service | 2026-06-16 | 13:00 | 15:00 | 120 | 120 | Public Counter | None | No | 0 | No |  | Candidate B | B-014 | No change | PASS | 0 | PASS | PASS | PASS
11 | A08 | South re-energisation | Maintenance | 2026-06-16 | 14:00 | 14:30 | 30 | 30 | South Electrical Room | South | Yes | 1 | No | A07 | Candidate B | B-008 | Corrected | PASS | 0 | PASS | PASS | PASS
12 | A10 | Barrier setup | Maintenance | 2026-06-17 | 8:00 | 8:30 | 30 | 30 | Loading Entrance | None | No | 1 | No |  | Candidate B | B-010A | Retained by judgement | PASS | 0 | PASS | PASS | PASS
13 | A11 | Access inspection | Maintenance | 2026-06-17 | 9:00 | 10:00 | 60 | 60 | Loading Entrance | None | No | 1 | No | A10 | Candidate B | B-011 | Corrected | PASS | 0 | PASS | PASS | PASS
14 | P03 | Public counter - morning 17 June | Public-counter service | 2026-06-17 | 9:30 | 12:00 | 150 | 150 | Public Counter | None | No | 0 | No |  | Candidate B | B-015 | Corrected | PASS | 0 | PASS | PASS | PASS
15 | P04 | Public counter - afternoon 17 June | Public-counter service | 2026-06-17 | 13:00 | 15:00 | 120 | 120 | Public Counter | None | No | 0 | No |  | Candidate B | B-016 | No change | PASS | 0 | PASS | PASS | PASS
16 | A12 | Noisy functional test 2 | Maintenance | 2026-06-17 | 15:30 | 16:30 | 60 | 60 | Test Bay | Test | No | 1 | Yes | A11 | Candidate B | B-012 | Corrected | PASS | 0 | PASS | PASS | PASS
Peer-review / approval fields
Prepared by | Tadeo Penrose |  |  | Peer reviewer | Isabel Tikhonov |  |  | Approval decision | Pending approval |  |  | Approval authority | Not recorded |  |  | Approval date | Not recorded

## Issue Register
Cobblemoor Provisions ¦ inspection issue and correction lineage
Each item below links a permitted normalization or duplicate disposition to a Candidate B source row. The duplicate judgement is explicitly an inference, not a source fact.
Issue ID | Source candidate | Source row | Activity ID | Issue type | Field | Observed value | Result / exclusion | Disposition | Basis
IR-01 | Candidate B | B-001 | A01 | Normalization | Finish time | 08.30 | 08:30 | Corrected | Unique parse of submitted time representation
IR-02 | Candidate B | B-001 | A01 | Normalization | Location | North Elec Room | North Electrical Room | Corrected | Unique supplied room-name mapping
IR-03 | Candidate B | B-002 | A02 | Normalization | Start time | 08:30 hrs | 08:30 | Corrected | Unique parse of submitted time representation
IR-04 | Candidate B | B-002 | A02 | Normalization | Location | N. Electrical Rm | North Electrical Room | Corrected | Unique supplied room-name mapping
IR-05 | Candidate B | B-003 | A03 | Normalization | Finish time | 10h30 | 10:30 | Corrected | Unique parse of submitted time representation
IR-06 | Candidate B | B-003X | A03 | Normalization | Finish time | 10h30 | 10:30 (excluded source row) | Excluded | Unique parse of submitted time representation; source row is excluded by duplicate disposition.
IR-07 | Candidate B | B-004 | A04 | Normalization | Start time | 10.30 | 10:30 | Corrected | Unique parse of submitted time representation
IR-08 | Candidate B | B-004 | A04 | Normalization | Location | North electrical | North Electrical Room | Corrected | Unique supplied room-name mapping
IR-09 | Candidate B | B-005 | A05 | Normalization | Start time | 11h30 | 11:30 | Corrected | Unique parse of submitted time representation
IR-10 | Candidate B | B-005 | A05 | Normalization | Location | South Elec Rm | South Electrical Room | Corrected | Unique supplied room-name mapping
IR-11 | Candidate B | B-006 | A06 | Normalization | Finish time | 13:00 hrs | 13:00 | Corrected | Unique parse of submitted time representation
IR-12 | Candidate B | B-007 | A07 | Normalization | Start time | 13:00 | 13:00 | Corrected | Unique parse of submitted time representation
IR-13 | Candidate B | B-007 | A07 | Normalization | Finish time | 14.00 | 14:00 | Corrected | Unique parse of submitted time representation
IR-14 | Candidate B | B-007 | A07 | Normalization | Location | S Electrical | South Electrical Room | Corrected | Unique supplied room-name mapping
IR-15 | Candidate B | B-008 | A08 | Normalization | Location | South electrical | South Electrical Room | Corrected | Unique supplied room-name mapping
IR-16 | Candidate B | B-009 | A09 | Normalization | Start time | 08:00 hrs | 08:00 | Corrected | Unique parse of submitted time representation
IR-17 | Candidate B | B-009 | A09 | Normalization | Finish time | 09h00 | 09:00 | Corrected | Unique parse of submitted time representation
IR-18 | Candidate B | B-009 | A09 | Normalization | Location | Test-bay | Test Bay | Corrected | Unique supplied room-name mapping
IR-19 | Candidate B | B-010A | A10 | Normalization | Start time | 08.00 | 08:00 | Corrected | Unique parse of submitted time representation
IR-20 | Candidate B | B-010A | A10 | Normalization | Finish time | 08.30 | 08:30 | Corrected | Unique parse of submitted time representation
IR-21 | Candidate B | B-010A | A10 | Normalization | Location | Loading Dock Entrance | Loading Entrance | Corrected | Unique supplied room-name mapping
IR-22 | Candidate B | B-010B | A10 | Normalization | Location | Barrier area | Loading Entrance (excluded source row) | Excluded | Unique supplied room-name mapping; source row is excluded by duplicate disposition.
IR-23 | Candidate B | B-011 | A11 | Normalization | Finish time | 10:00 hrs | 10:00 | Corrected | Unique parse of submitted time representation
IR-24 | Candidate B | B-012 | A12 | Normalization | Start time | 15h30 | 15:30 | Corrected | Unique parse of submitted time representation
IR-25 | Candidate B | B-012 | A12 | Normalization | Finish time | 16h30 | 16:30 | Corrected | Unique parse of submitted time representation
IR-26 | Candidate B | B-012 | A12 | Normalization | Location | Function test bay | Test Bay | Corrected | Unique supplied room-name mapping
IR-27 | Candidate B | B-013 | P01 | Normalization | Location | Counter - Public | Public Counter | Corrected | Unique supplied room-name mapping
IR-28 | Candidate B | B-015 | P03 | Normalization | Location | Public service counter | Public Counter | Corrected | Unique supplied room-name mapping
IR-29 | Candidate B | B-003X | A03 | Duplicate disposition | Scheduled occurrence | Exact repeat of B-003 | Excluded; B-003 retained | Excluded | Same activity, date, interval and mapped location as B-003; retain one occurrence only.
IR-30 | Candidate B | B-010B | A10 | Duplicate disposition | Scheduled occurrence | Conflicting submitted Barrier setup interval | Excluded; B-010A retained | Excluded | Judgement: source evidence does not establish supersession. Retained earlier submitted row because it preserves additional predecessor slack.
IR-31 | Candidate B | B-010A | A10 | Duplicate disposition | Scheduled occurrence | Conflicting submitted Barrier setup interval | Retained at 08:00-08:30 | Retained by judgement | Judgement: source evidence does not establish supersession. Retained earlier submitted row because it preserves additional predecessor slack.

## Inspection Findings
Cobblemoor Provisions ¦ inspection findings for peer review
Selected submission | Candidate B
Inspection result | Compliant after permitted normalization and documented duplicate disposition.
Overall status | Pending approval
Candidate A finding | England noisy-testing separation fails: A-009 ends at 09:30 immediately before fixed counter block A-013 begins; no full clear 30-minute slot is available.
Candidate C finding | Electrician sequence alternates North/South zones. The 360 minutes of electrical work occupy a 390-minute availability window but require 210 minutes of zone-changeover time; the fixed submitted placements leave only 30 minutes unassigned.
Jurisdiction comparison | England applies. England requires no noisy-testing overlap and one full clear 30-minute separation slot from every public-counter block; Wales prohibits overlap but has no clear-slot requirement.
Duplicate judgement | Source evidence does not establish supersession. B-010A is retained at 08:00-08:30 on 17 June as a judgement, not a source fact.
Summary figures | Required activities: 16; scheduled activities: 16; planned maintenance minutes: 570; changeover minutes: 30.
Authority | This record states inspection findings only. Approval is not recorded and remains pending peer review.