## Transition Snapshot
Tidewater Health Network ¦ Enterprise specimen-retention transition snapshot
Frozen Ontario-New York planning extract ¦ Operations and delivery working material
Snapshot ID | THN-STR-2026-03-02 |  | Frozen as of | 2026-03-02 |  | Projection start | 2026-04-01 |  | Projection through | 2026-09-30 |  | Currency | USD
Fixed completion deadline | 2026-04-17 |  | Shared slot date | 2026-04-10 |  | Prepared for | Hana Merriweather |  | Operations manager | Ibrahim Asante
SOURCE ORDER AND RECORD REGISTER
Record ID | Source class | Authority / register | Record date | Effective date | Jurisdiction | Field | Value
REG-ON-RET | Frozen regulatory snapshot | Ontario regulatory snapshot | 2025-12-15 | 2026-01-01 | Ontario | Retention minimum | 10 years
REG-ON-VAL | Frozen regulatory snapshot | Ontario regulatory snapshot | 2025-12-15 | 2026-01-01 | Ontario | Validation treatment | Mandatory Ontario validation; legally segregated
REG-NY-RET | Frozen regulatory snapshot | New York regulatory snapshot | 2025-12-15 | 2026-01-01 | New York | Retention minimum | 6 years
REG-NY-VAL | Frozen regulatory snapshot | New York regulatory snapshot | 2025-12-15 | 2026-01-01 | New York | Validation treatment | Mandatory New York validation; legally segregated
INT-ON-RET | Verified internal record | Retention policy register v4 | 2026-02-20 | 2026-02-20 | Ontario | Retention minimum | 7 years
INT-ON-VAL | Verified internal record | Cross-border workflow memo 2026-02 | 2026-02-20 | 2026-02-20 | Ontario | Validation treatment | Single cross-border review
INT-NY-RET | Verified internal record | Retention policy register v4 | 2026-02-20 | 2026-02-20 | New York | Retention minimum | 5 years
INT-NY-VAL | Verified internal record | Cross-border workflow memo 2026-02 | 2026-02-20 | 2026-02-20 | New York | Validation treatment | Single cross-border review
PRECEDENCE
Rule ID | Field family | Governing record | Operational use
P1 | Jurisdictional and regulatory requirements | Frozen regulatory snapshot | Later internal record dates do not replace the frozen jurisdictional requirement.
P2 | Capacity, inventory, workflow, labor and cost fields | Verified internal operational records | Use the verified internal record when it does not override a regulatory requirement.
Precedence statement: the frozen Ontario-New York regulatory snapshot governs jurisdictional and regulatory requirements, regardless of later internal record dates. Verified internal records govern operational capacity, inventory, workflow, labor, storage, processing and cost fields only where they do not override a regulatory requirement.
JURISDICTIONAL REQUIREMENTS
Jurisdiction | Frozen snapshot ID | Effective from | Retention minimum | Mandatory validation | Legally segregated | Controlled repository | Source date
Ontario | REG-ON-RET / REG-ON-VAL | 2026-01-01 | 10 years | Ontario retention validation | Yes | Ontario-controlled archive | 2025-12-15
New York | REG-NY-RET / REG-NY-VAL | 2026-01-01 | 6 years | New York retention validation | Yes | New York-controlled archive | 2025-12-15
FIVE-STAGE PREREQUISITE CHAIN
Stage ID | Stage name | Predecessor | Duration (business days) | Target start | Target finish | Current status | Gate / evidence
P1 | Regulatory basis and source reconciliation | - | 2 | 2026-04-01 | 2026-04-02 | In review | Four regulatory-field conflicts require adoption
P2 | Capacity and cost baseline | P1 | 3 | 2026-04-03 | 2026-04-07 | Ready after P1 | Uses verified internal operational records
P3 | Validation slot reservation | P2 | 1 | 2026-04-08 | 2026-04-10 | Blocked | 10 + 8 hours against 12-hour sole bench
P4 | Retention transfer and verification | P3 | 4 | 2026-04-13 | 2026-04-16 | Pending predecessor | Both jurisdiction validations required
P5 | Operational handoff and approval | P4 | 1 | 2026-04-17 | 2026-04-17 | Pending predecessor | Hana approval follows complete chain
MANDATORY LEGALLY SEGREGATED VALIDATIONS
Activity ID | Jurisdiction | Validation activity | Required hours | Required date | Segregation rule | Qualified certification | Assigned resource | Current status
VAL-ON | Ontario | Ontario retention validation | 10 | 2026-04-10 | No overlap with New York validation | Active cross-jurisdiction validation | Unassigned | Pending - slot infeasible
VAL-NY | New York | New York retention validation | 8 | 2026-04-10 | No overlap with Ontario validation | Active cross-jurisdiction validation | Unassigned | Pending - slot infeasible
Shared resource | Available date | Available slot hours | Currently booked | Required combined hours | Capacity shortfall
sole cross-border validation processing bench | 2026-04-10 | 12 | 0 | 18 | 6
Occupancy rule: the two mandatory legally segregated validation activities may not overlap and their combined occupancy may not exceed 12 hours in the available 10 April 2026 slot.
RESOURCE POOL
Name | Primary role | Other supported work | Certification | Certification status | Active through
Ibrahim Asante | operations manager | source reconciliation |  | Not held | 2026-09-30
Hana Merriweather | approval | cross-jurisdiction validation | active cross-jurisdiction validation | Active | 2026-09-30
Theo Dimitrov | capacity analysis | operations correction |  | Not held | 2026-09-30
Renata Guerrero | cross-jurisdiction validation | quality review | active cross-jurisdiction validation | Active | 2026-09-30
Estelle Ingram | financial analysis | document control |  | Not held | 2026-09-30
VERIFIED INTERNAL OPERATIONAL RECORDS
Period start | Period end | Jurisdiction | Projected intake | Opening retained inventory | Routine processing volume | Available processing capacity | Available storage capacity | Labor hours | Labor rate | Storage rate / retained specimen-month | Processing rate / specimen | Record ID | Record date
2026-04-01 | 2026-04-30 | Ontario | 420 | 8900 | 400 | 520 | 9800 | 96 | 42 | 0.18 | 3.25 | OPS-ON-APR | 2026-03-01
2026-05-01 | 2026-05-31 | Ontario | 460 | 9320 | 440 | 540 | 10000 | 102 | 42 | 0.18 | 3.25 | OPS-ON-MAY | 2026-03-01
2026-06-01 | 2026-06-30 | Ontario | 500 | 9780 | 480 | 560 | 10200 | 110 | 42 | 0.18 | 3.25 | OPS-ON-JUN | 2026-03-01
2026-07-01 | 2026-07-31 | Ontario | 520 | 10280 | 500 | 570 | 10500 | 114 | 42 | 0.18 | 3.25 | OPS-ON-JUL | 2026-03-01
2026-08-01 | 2026-08-31 | Ontario | 540 | 10800 | 520 | 580 | 11000 | 118 | 42 | 0.18 | 3.25 | OPS-ON-AUG | 2026-03-01
2026-09-01 | 2026-09-30 | Ontario | 560 | 11340 | 540 | 590 | 11400 | 122 | 42 | 0.18 | 3.25 | OPS-ON-SEP | 2026-03-01
2026-04-01 | 2026-04-30 | New York | 300 | 6100 | 290 | 400 | 7200 | 72 | 46 | 0.21 | 3.75 | OPS-NY-APR | 2026-03-01
2026-05-01 | 2026-05-31 | New York | 330 | 6400 | 320 | 420 | 7200 | 74 | 46 | 0.21 | 3.75 | OPS-NY-MAY | 2026-03-01
2026-06-01 | 2026-06-30 | New York | 360 | 6730 | 350 | 430 | 7400 | 78 | 46 | 0.21 | 3.75 | OPS-NY-JUN | 2026-03-01
2026-07-01 | 2026-07-31 | New York | 380 | 7090 | 370 | 440 | 7600 | 82 | 46 | 0.21 | 3.75 | OPS-NY-JUL | 2026-03-01
2026-08-01 | 2026-08-31 | New York | 400 | 7470 | 390 | 450 | 7900 | 86 | 46 | 0.21 | 3.75 | OPS-NY-AUG | 2026-03-01
2026-09-01 | 2026-09-30 | New York | 420 | 7870 | 410 | 460 | 8200 | 90 | 46 | 0.21 | 3.75 | OPS-NY-SEP | 2026-03-01
CANDIDATE OPERATING SCENARIOS
Scenario ID | Description | Status | Required activities | Claims completed transition | Transition labor | Validation preparation | Incremental storage | Deferral / hold | Other support | Source total | Eligibility under source rules | Selection rule
S1 | Standard internal transition | Near miss - shared slot over capacity | VAL-ON; VAL-NY | Yes | 4500 | 1200 | 1600 | 0 | 1000 | 8300 | No - mandatory validations require 18 hours against 12 | Not eligible as compliant because the mandatory validation occupancy exceeds the sole slot
S2 | Expedited transition with additional internal effort | Near miss - same mandatory validation bottleneck | VAL-ON; VAL-NY | Yes | 6800 | 2200 | 2600 | 0 | 1250 | 12850 | No - extra effort does not create shared-bench capacity | Not eligible as compliant because additional effort does not create shared-bench capacity
S3 | Controlled hold and documented no-compliant-selection response | Eligible controlled response - transition held | VAL-ON; VAL-NY (pending) | No | 2100 | 850 | 1800 | 5200 | 750 | 10700 | Yes - controlled response only; no completion claim | Eligible only when it reports no compliant transition selection and leaves blocked validation work pending
S4 | Partial validation transition | Near-miss distractor - incomplete validation coverage | VAL-ON only | Yes | 1500 | 450 | 900 | 0 | 250 | 3100 | No - New York validation is omitted | Ineligible because it leaves one mandatory jurisdictional validation unaddressed
MANDATORY COVERAGE MATRIX
Scenario ID | regulatory basis and source reconciliation | five-stage prerequisite chain and deadline status | validation capacity and infeasibility assessment | capacity projection through 2026-09-30 | financial impact through 2026-09-30 | executable corrections with owners and timing
S1 | Y | Y | Y | Y | Y | Y
S2 | Y | Y | Y | Y | Y | Y
S3 | Y | Y | Y | Y | Y | Y
S4 | Y | Y | N | Y | Y | Y
CORRECTION GAPS
Gap ID | Material gap | Operational impact | Required outcome | Suggested owner | Timing | Dependency | Source status
G1 | Regulatory-field reconciliation | Retention and validation basis can diverge by jurisdiction | Adopt frozen regulatory values and retain internal values as conflicting records | Ibrahim Asante | By 2 April 2026 | P1 | Open
G2 | Validation-slot conflict | Mandatory validation work exceeds sole processing slot | Keep both activities pending until capacity is resolved; do not claim completion | Renata Guerrero | Before 10 April 2026 slot | P3 | Blocked
G3 | Prerequisite/deadline status | Downstream stages cannot pass the 17 April gate | Record no compliant transition selection and preserve predecessor gates | Ibrahim Asante | By 17 April 2026 | P3 | Open
G4 | Capacity update | Separate Ontario and New York inventory/headroom can change during the hold | Refresh jurisdiction-specific projection through 30 September 2026 | Theo Dimitrov | Weekly through 30 September 2026 | P2; capacity ledger | Open
G5 | Financial amendment support | Hana lacks a reconciled cost view for the amendment | Attach S3 package cost and period financial impact | Estelle Ingram | By 7 April 2026 | P2; S3 cost basis | Open
G6 | Controlled-response approval | The transition cannot be represented as complete | Approve or reject the documented hold response; do not approve a completion claim | Hana Merriweather | By 17 April 2026 | G1-G5 | Awaiting approval
Export note: operational rates and volumes are planning records for this frozen snapshot; jurisdictional fields remain governed by the frozen regulatory rows above.
Exported | 2026-03-02 14:15