## Site comparison export
Hollowpine Field Services ¦ candidate site & occupancy evidence
Exported 2026-08-24 09:14 UTC ¦ Facilities working file ¦ Version 3
Section | Item | Candidate / zone | Detail | Value | Units / basis | Status | Source / owner note
Decision horizon | Current lease expires | Hollowpine laboratory group | Facilities committee must select a site configuration before the lease end. | 14 | months from decision baseline | SOURCE FACT | Efua Sundqvist, facilities director
Decision horizon | Committee vote | Facilities committee | Requested in November; this worksheet supports the vote and legal review. | November | decision gate | SOURCE FACT | Efua Sundqvist
Requirements | Instrument bay floor loading | Instrument bay | Minimum structural capacity required. | 500 | psf minimum | SOURCE FACT | Laboratory requirements intake
Requirements | Instrument bay vibration | Instrument bay | Acceptance criterion; evidence must be specific to the installed bay. | <= 20 | micrometers/sec RMS | SOURCE FACT | Laboratory requirements intake
Requirements | General laboratory rooms | Laboratory group | Wet lab, analytical lab, prep, and instrument bay require laboratory fit-out and controlled laboratory access. | 4 | rooms total; isotope suite is included | SOURCE FACT | Space program
Requirements | Isotope suite exception | Isotope suite | One room within the laboratory rooms. Separate controls, occupancy confirmation, and technical sign-off are required; general laboratory fit-out is not evidence of isotope-suite suitability. | 1 | controlled room | SOURCE FACT | Space program / biosafety intake
Requirements | Access populations | Occupancy configuration | General occupants must be separated from controlled laboratory users. Laboratory access is controlled; isotope-suite access is a further controlled permission. | 3 | general / laboratory / isotope-suite | SOURCE FACT | Facilities access brief
Candidate | Cedar Ridge Industrial Center - Building 4 | Cedar Ridge | Lowest projected 14-month occupancy cost. Instrument-bay floor loading is documented at 650 psf. Base shell requires exhaust retrofit before laboratory occupancy. |  |  | SOURCE FACT | Broker tour / landlord engineering package
Candidate | Harbor Point Labs - Suite 210 | Harbor Point | Turnkey laboratory shell; earliest stated readiness. Owner cannot provide evidence demonstrating the instrument-bay vibration criterion. |  |  | SOURCE FACT | Landlord response dated 10/18
Candidate | Northline Commerce Campus - Building 2 | Northline | Landlord will not commit in the lease to separated badging for general occupants and laboratory users. |  |  | SOURCE FACT | Landlord call summary; not a contractual commitment
Access control | Badging commitment | Cedar Ridge | Landlord proposes three credential groups (general, laboratory, isotope suite); the configuration must be incorporated as a written lease/access-system commitment before execution. | 3 | credential groups proposed | CONFIRMATION REQUIRED | Landlord access proposal
Technical fit | Floor loading evidence | Cedar Ridge | Existing structural letter states 650 psf at proposed instrument-bay area. | 650 | psf | SOURCE FACT | Landlord structural letter
Technical fit | Floor loading evidence | Harbor Point | Existing slab schedule states 550 psf at proposed instrument-bay area. | 550 | psf | SOURCE FACT | Landlord shell package
Technical fit | Floor loading evidence | Northline | Existing slab schedule states 600 psf at proposed instrument-bay area. | 600 | psf | SOURCE FACT | Landlord shell package
Technical fit | Vibration evidence | Cedar Ridge | No acceptance test yet. Pre-occupancy vibration measurement at installed instrument-bay location is required. |  | against <=20 micrometers/sec RMS | CONFIRMATION REQUIRED | Laboratory requirements intake
Technical fit | Vibration evidence | Harbor Point | Landlord states it cannot demonstrate compliance with the <=20 micrometers/sec RMS instrument-bay criterion. |  | criterion cannot be demonstrated | SOURCE FACT | Landlord response dated 10/18
Technical fit | Vibration evidence | Northline | No acceptance test yet. Pre-occupancy vibration measurement would be required. |  | against <=20 micrometers/sec RMS | CONFIRMATION REQUIRED | Laboratory requirements intake
Building work | Exhaust retrofit | Cedar Ridge | Landlord-procured exhaust retrofit is required for laboratory occupancy; stated duration is 9 months after execution. Exhaust performance must be verified before laboratory occupancy. | 9 | months after execution | SOURCE FACT | Landlord scope letter
Building work | Exhaust retrofit | Harbor Point | Turnkey shell; no exhaust retrofit stated for general laboratory areas. | 0 | months | SOURCE FACT | Landlord scope summary
Building work | Exhaust retrofit | Northline | Minor duct extension included in tenant fit-out allowance. | 2 | months; may run with fit-out | SOURCE FACT | Landlord scope summary
Schedule | Lease / design / access-plan package | All candidates | Execution, fit-out drawings, access plan, and construction mobilization require 2 months before field work begins. | 2 | months | SOURCE FACT | Project controls estimate
Schedule | Laboratory fit-out after mobilization | Cedar Ridge | General laboratory fit-out duration. May proceed in parallel with exhaust retrofit after coordinated interface release. | 4 | months | SOURCE FACT | Tenant improvement estimate
Schedule | General occupancy move | Cedar Ridge | General occupants may move after general-area fit-out and access system commissioning; does not authorize laboratory occupancy. | 6 | month from decision baseline | PROJECTED MILESTONE | Derived from 2-month setup + 4-month fit-out
Schedule | Laboratory readiness | Cedar Ridge | Exhaust retrofit completion, laboratory fit-out, instrument-bay acceptance, and access commissioning are dependencies. | 11 | month from decision baseline | PROJECTED MILESTONE | Derived: 2-month setup + 9-month exhaust
Schedule | Isotope-suite occupancy gate | Cedar Ridge | Can occur only after its separate controls are confirmed and Callum Yamamoto provides technical sign-off; modeled after laboratory readiness. | 12 | month from decision baseline | ASSUMPTION / GATE | One month allowance after laboratory readiness
Schedule | Final phased-move completion | Cedar Ridge | Staged laboratory transfer and lease handback target. | 13 | month from decision baseline | PROJECTED MILESTONE | Leaves one month before lease end
Schedule | Sequential-plan result | Cedar Ridge | 2-month setup + 9-month exhaust + 4-month lab fit-out + 1-month isotope gate = 16 months; sequential plan misses lease end. | 16 | months | CALCULATED | Durations above; no overlap
Schedule | Fallback | Cedar Ridge | If landlord does not provide a committed interface release by the end of month 2, pause lease execution/escalate; do not assume a sequential retrofit-and-move plan fits. A short negotiated holdover is the bounded contingency to protect continuity. |  | decision contingency | PROPOSAL | Tenant-representation recommendation
Cost - 14 month basis | Base rent | Cedar Ridge | Quoted occupancy rent through the 14-month lease horizon. | 1260000 | USD / 14 months | SOURCE FACT | Landlord proposal
Cost - 14 month basis | Building preparation | Cedar Ridge | Core modifications other than exhaust retrofit. | 145000 | USD / 14 months | SOURCE FACT | Landlord proposal
Cost - 14 month basis | Laboratory fit-out | Cedar Ridge | Tenant work for general laboratory rooms; excludes any conclusion on isotope-suite suitability. | 260000 | USD / 14 months | SOURCE FACT | Tenant improvement estimate
Cost - 14 month basis | Exhaust retrofit | Cedar Ridge | Landlord scope pricing allowance; subject to documented final scope. | 285000 | USD / 14 months | ESTIMATE | Landlord scope letter
Cost - 14 month basis | Relocation / commissioning | Cedar Ridge | Move, commissioning, and staging allowance. | 75000 | USD / 14 months | ESTIMATE | Project controls estimate
Cost - 14 month basis | Base rent | Harbor Point | Quoted occupancy rent through the 14-month lease horizon. | 1712000 | USD / 14 months | SOURCE FACT | Landlord proposal
Cost - 14 month basis | Building preparation | Harbor Point | Turnkey punch and landlord coordination. | 90000 | USD / 14 months | SOURCE FACT | Landlord proposal
Cost - 14 month basis | Laboratory fit-out | Harbor Point | Tenant modifications for program placement. | 310000 | USD / 14 months | SOURCE FACT | Tenant improvement estimate
Cost - 14 month basis | Exhaust retrofit | Harbor Point | No retrofit stated for general laboratory areas. | 0 | USD / 14 months | SOURCE FACT | Landlord scope summary
Cost - 14 month basis | Relocation / commissioning | Harbor Point | Move and commissioning allowance. | 85000 | USD / 14 months | ESTIMATE | Project controls estimate
Cost - 14 month basis | Base rent | Northline | Quoted occupancy rent through the 14-month lease horizon. | 1600000 | USD / 14 months | SOURCE FACT | Landlord proposal
Cost - 14 month basis | Building preparation | Northline | Common-area and duct extension coordination. | 165000 | USD / 14 months | SOURCE FACT | Landlord proposal
Cost - 14 month basis | Laboratory fit-out | Northline | Tenant modifications for general laboratory rooms. | 275000 | USD / 14 months | SOURCE FACT | Tenant improvement estimate
Cost - 14 month basis | Exhaust retrofit | Northline | Duct extension included in preparation. | 0 | USD / 14 months | SOURCE FACT | Landlord scope summary
Cost - 14 month basis | Relocation / commissioning | Northline | Move and commissioning allowance. | 80000 | USD / 14 months | ESTIMATE | Project controls estimate
Commercial / technical authority | Tenant representation scope | Dagny Dunbar | Recommends commercial site, occupancy configuration, cost and schedule tradeoffs, and contract gates. Does not authorize biosafety, regulatory, or isotope-suite technical approval. |  |  | SOURCE FACT | Engagement scope
Commercial / technical authority | Biosafety authority | Callum Yamamoto | Provides biosafety and isotope-suite technical sign-off; approval cannot be inferred from general lab fit-out, occupancy planning, or this commercial recommendation. |  |  | SOURCE FACT | Facilities responsibility matrix