## Renewal Inputs
Yarrowfield Systems ¦ Lanternwood Logistics bearing framework renewal
Planning brief and source inputs ¦ exported 2026-02-10
Framework renewal | Five-year bearing framework with Lanternwood Logistics
Submission deadline | 31 March 2026 (month end)
Planning years | Year 1 (2026), Year 2 (2027), Year 3 (2028)
Demand signal | Lanternwood forecast rises sharply in Year 2
Qualification feedback | Final customer feedback on changed inspection arrangement expected 18 months after submission (30 September 2027)
Zara Pichler | Renewal submission lead / customer interface
Amara Jankowski | Capital commitment decision
Ingrid Jankowski | Independent inspection relationship
Emeka Almeida | Inspection systems / technical implementation
Olamide Chakraborty | Quality and certification governance
ROADMAP BRIEF (partially completed)
Section | Status / prompt
Decision | Select a three-year inspection capability path; recommendation pending
Capacity outlook | Quantify workload, effective capacity, reserve and bottlenecks
Certification | Preserve Lanternwood-accepted certificates through transition
Gates | Define commitments before and after qualification feedback
Risks | Record controls, owners and contingency
DEMAND FORECAST
Planning year | Product family | Inspection route | Revision date | Approval status | Quantity (bearings) | Business key | Notes
Year 1 (2026) | Angular contact | Legacy CMM | 2025-09-15 | Approved | 11000 | Y1¦Angular contact¦Legacy CMM
Year 1 (2026) | Angular contact | Legacy CMM | 2025-11-20 | Approved | 12000 | Y1¦Angular contact¦Legacy CMM | Retain latest approved revision; supersedes 15 Sep line.
Year 1 (2026) | Cylindrical roller | Legacy CMM | 2025-10-01 | Approved | 8000 | Y1¦Cylindrical roller¦Legacy CMM
Year 1 (2026) | Thrust | Independent agency | 2025-10-03 | Approved | 4000 | Y1¦Thrust¦Independent agency
Year 2 (2027) | Angular contact | Legacy CMM | 2025-10-10 | Approved | 28000 | Y2¦Angular contact¦Legacy CMM | Route shift: 10% of quantity may move to laser tracker after validation.
Year 2 (2027) | Cylindrical roller | Legacy CMM | 2025-08-01 | Approved | 25500 | Y2¦Cylindrical roller¦Legacy CMM
Year 2 (2027) | Cylindrical roller | Legacy CMM | 2025-12-12 | Approved | 26000 | Y2¦Cylindrical roller¦Legacy CMM | Retain latest approved revision.
Year 2 (2027) | Thrust | Independent agency | 2025-11-05 | Approved | 12000 | Y2¦Thrust¦Independent agency
Year 3 (2028) | Angular contact | Laser tracker | 2025-11-10 | Forecast | 34000 | Y3¦Angular contact¦Laser tracker
Year 3 (2028) | Cylindrical roller | Laser tracker | 2025-11-10 | Forecast | 30000 | Y3¦Cylindrical roller¦Laser tracker
Year 3 (2028) | Thrust | Independent agency | 2025-11-10 | Forecast | 16000 | Y3¦Thrust¦Independent agency
INSPECTION WORKLOAD & RESOURCE CAPACITY
Product family | Dimensional verification | Surface / visual | Certification pack
Angular contact | 3 | 1.5 | 0.8
Cylindrical roller | 2.5 | 1.2 | 0.7
Thrust | 4 | 2 | 1
Effective annual resource capacity (hours)
Resource | Year 1 (2026) | Year 2 (2027) | Year 3 (2028) | Notes
Legacy CMM | 1800 | 0 | 0 | Manufacturer support ends 30 Jun 2027; no planned use after Year 1.
Laser tracker | 0 | 4500 | 5500 | Purchase 01 Apr 2026; install 2 mo, train 2 mo, validate 1 mo; productive 01 Jan 2027.
Independent agency | 1200 | 3200 | 4000 | Year 2 note caps quoted 3,500 h at 3,200 h; approved signer retained through gate.
Calibration provider | 300 | 0 | 0 | Final feasible CMM calibration window closes 31 Dec 2026; provider closes 31 Mar 2027.
ISSUED DECISION POLICY
Maintain at least 20% reserve (utilization <=80%); no planned reliance on unsupported equipment; accepted certificates must have customer-recognized signing authority; staged capital may proceed before feedback only with a viable fallback.
COMMERCIAL DELIVERY OPTIONS
Option | Capital timing / cost | Annual fixed cost | Variable external rate | Lead-time / exposure | Notes
Retain independent | None | Reservation 90,000 + support 20,000 | 85 / external hour | Immediate; supplier dependence | Quote valid through 30 Sep 2027.
In-house laser tracker | 2026: purchase 420,000; install 60,000; validate 35,000; training 25,000 | Support 45,000 + 2 FTE 170,000 | 12 / internal hour + signer 70,000 | Productive 01 Jan 2027; qualification uncertainty; stranded-capital exposure | Training term applies only after purchase.
Staged hybrid (recommended) | 2026: 420,000 + 60,000 + 35,000 + 25,000 | Support 45,000 + 2 FTE 170,000 | 12 / internal hour; external balance 85 / h; signer retained | Immediate external coverage; internal ramp in Year 2; reversible gate | Note: reservation 90,000 is waived in hybrid Year 1 if 1,000 h reserved.
QUALIFICATION & SUPPLIER EVIDENCE | [6 empty] | ADMIN TRACKING
Evidence item | Status / value | Timing | Notes |  |  |  | Owner | Next review
Independent agency approval | Customer-recognized approval; may sign accepted certificates | Current / through 30 Sep 2027 | Note: approval covers dimensional verification and certificate signing, not equipment ownership. |  |  |  | Facilities | 2026-04-15
Laser tracker capability | Technical measurement capability after validation; no automatic signing authority | Productive 01 Jan 2027 | Lanternwood qualification feedback expected 30 Sep 2027. |  |  |  | Procurement | 2026-05-01
External capacity reservation | 1,200 h Y1; 3,200 h Y2; 4,000 h Y3 | Quote valid to 30 Sep 2027 | Year 2 staffing note caps quoted 3,500 h at 3,200 h. |  |  |  | Finance | 2026-05-15
Qualification response | 18 months after submission | 30 Sep 2027 | If late, continue approved agency route and do not expand internal certificate claims.