## Award actions
LANTERNWOOD TRADING COMPANY
Supplier award action register ¦ Control-panel assembly ¦ Halberdine Agricultural
Decision direction: controlled incumbent renewal for 1 Nov 2024 to 30 Apr 2025, subject to MUST gates. Approved alternate remains a continuity contingency; not authorized for target-assembly production.
Control amounts use the July-September expedite run rate for each of the two call-off quarters. As of 25 Oct 2024.
No. | Action | Owner | Due date | Status | Required evidence / decision gate | Fallback
1 | Approve controlled incumbent call-off; reasonably expected purchasing plus projected expedites is $1,024,200, above $1,000,000. | Viktor Stavropoulos | 2024-10-25 | Open - written approval required | Signed written approval of $1,024,200 control amount before release. | Hold production release. Viktor documents whether a time-bounded validated continuity bridge is authorized.
2 | Confirm incumbent allocation for 8,400 assemblies and the 1,550-unit peak month. | Ainsley Achterberg | 2024-10-28 | Open - capacity confirmation | Written allocation against stated 1,600/month capacity, showing 50-unit/month peak headroom and supply-plan coverage. | Hold release; Ainsley escalates the gap. Use only an approved, already valid continuity bridge authorized by Viktor.
3 | Secure incumbent recovery package and commercial protections for delivery, defects, lead time and expedite dependence. | Tadeo Gasparyan | 2024-10-29 | Open - supplier response | Signed corrective action, recovery milestones, capacity commitment, documented freight responsibility and performance remedies; addresses 84.7% on-time, 2.8% defects, 27-day lead time and 11 expedites in July-September. | Do not release the call-off. Tadeo escalates to Viktor; any bridge follows Viktor's documented continuity decision.
4 | Release controlled incumbent production call-off for 1 November 2024 to 30 April 2025. | Tadeo Gasparyan | 2024-10-31 | Blocked pending MUST gates | Viktor approval, Ainsley capacity confirmation, Tadeo recovery package, and current incumbent assembly release for Ontario, Canada and Victoria, Australia. | Hold release and execute only the documented time-bounded validated continuity path; do not release the alternate.
5 | Ontario, Canada: complete alternate part-, line-, and destination-specific engineering and quality review. | Sigrid Karlsson | 2024-12-20 | In progress - no commitment before 1 November | Sigrid's written Ontario-only production release or written no-release decision; approved-supplier status is insufficient. | Alternate remains a continuity contingency; no Ontario production release.
6 | Victoria, Australia: complete alternate part-, line-, and destination-specific engineering and quality review. | Sigrid Karlsson | 2024-12-20 | In progress - no commitment before 1 November | Sigrid's written Victoria-only production release or written no-release decision; Ontario evidence does not clear Victoria. | Alternate remains a continuity contingency; no Victoria production release.
7 | Resolve alternate peak-capacity gap: stated 1,500/month versus 1,550 peak leaves a 50-unit/month shortfall. | Ainsley Achterberg | 2024-12-20 | Open - contingency capacity work | Documented alternate capacity plan at or above 1,550 assemblies in the peak month; average-demand sufficiency is not enough. | Alternate remains a continuity contingency and is not eligible for production release.
8 | Run incumbent recovery KPI review after award. | Tadeo Gasparyan (commercial); Ainsley provides capacity input | 29 Nov 2024; monthly through 30 Apr 2025 | Scheduled after award | Monthly report: on-time delivery >=95.0%, incoming defects <=1.5%, lead time <=22 calendar days, and no more than one expedite per month. | Any breach: corrective action within 2 business days and reopen sourcing review; repeat breach in two months or capacity failure escalates to Viktor.
9 | Document exception decision for any missed MUST gate before the call-off start. | Viktor Stavropoulos | 2024-10-31 | Standby - only if a gate is missed | Written exception identifies blocked gate, accountable owner, validated bridge supplier/assembly, expiry date, and closure evidence. | No documented exception: retain hold; no unsupported award and no alternate production release.