## Register
Glassmere alternate approval — review events
Chronological event export ¦ source dates intentionally retain mixed formats
Event ID | Effective date/time | Event type | Affected key | Resulting status/value | Responsible party | Supporting reference | Event note
EV-001 | 2026-01-10T09:00 | Evidence received | TECH-01 | Under review | Mateo Ainsworth | REV-TECH-01 | Inspection photos logged
EV-002 | 2026-01-14T16:30 | Finding closed | TECH-01 | Closed | Mateo Ainsworth | REV-TECH-02 | Witness within acceptance band
EV-003 | 2026-01-18T11:00 | Test result | TECH-EDGE-01 | Closed | Mateo Ainsworth | REV-EDGE-01 | Initial sample passed
EV-004 | 2026-01-22T14:15 | Verification sample rejected | TECH-EDGE-01 | Unresolved | Mateo Ainsworth | REV-EDGE-02 | Required verification sample not accepted
EV-005 | 2026-01-27T10:00 | Finding closed | TECH-02 | Closed | Lucia Jelinek | REV-TECH-03 | Retention check complete
EV-006 | 02/03/2026 09:00 | Evidence accepted with limitation | EVID-01 | Accepted — limited to stated test condition | Mateo Ainsworth | REV-EVID-02 | Date is mixed-format in source
EV-007 | 2026-03-05T15:00 | Control revised | TRIAL-01 | Gate 1 ready | Lucia Jelinek | REV-TRIAL-02 | Inspection and escalation steps added
EV-008 | 2026-03-07T12:00 | Commercial confirmed | COMM-01 | Accepted | Lachlan Mikkelsen | REV-COMM-02 | Rate confirmed for decision pack