## Draft Plan
Kingsferry Regional Office – Move Draft
Prepared by Maren Chakraborty ¦ 18 Dec 2025 ¦ Draft for review
Package ID | Department | Origin | Draft Destination | Readiness | Dependency | Qty (cu ft) | Crew | Base Crew Hrs | Elevator Trips | Freight Vehicles | Draft Weekend | Draft Cost | Notes
FIN-01 | Finance | Floor 1 | Annex Floor 1 | 2026-02-07 07:00 | None | 420 | Crew A | 3 | 3 | 1 | Weekend 1 | 5200 | Included return trip for empty totes; bill 1 vehicle block.
HR-01 | People Services | Floor 1 | Annex Floor 2 | 2026-02-07 08:00 | FIN-01 | 300 | Crew A | 2.5 | 2 | 1 | Weekend 1 | 4300 | Destination confirmed as Annex Floor 2.
IT-01A | IT | Floor 2 | Swing Floor | 2026-02-07 07:00 | None | 500 | Crew A | 1.5 | 2 | 1 | Weekend 1 | 3800 | Stage to swing floor first; paid staging is 1.0 hour before onward move.
IT-01B | IT | Swing Floor | Annex Floor 3 | 2026-02-14 08:00 | IT-01A | 500 | Crew B | 2 | 2 | 1 | Weekend 2 | 4100 | Final placement after network cutover.
REC-01 | Records | Floor 2 Vault | Annex Floor 2 | 2026-02-14 09:00 | None | 260 | Crew B | 2 | 3 | 1 | Weekend 2 | 3600 | Vault opening/closing included; escort required.
OPS-01 | Operations | Floor 1 | Annex Floor 1 | 2026-02-21 07:00 | HR-01 | 600 | Crew C | 4 | 4 | 2 | Weekend 3 | 6900 | Requires two vehicle blocks.
LEG-01 | Legal | Floor 2 | Annex Floor 3 | 2026-02-21 08:00 | REC-01 | 180 | Crew C | 1.5 | 2 | 1 | Weekend 3 | 2900 | Final destination subject to review.
COM-01 | Communications | Floor 1 | Annex Floor 2 | 2026-02-21 10:00 | OPS-01 | 220 | Crew C | 1.5 | 2 | 1 | Weekend 3 | 3100 | Can move after Operations clears loading area.
Draft summary (old analyst)
Valid detail total
Old headline total (residual formula error)
Note | Old headline contains a residual analyst formula error; recompute from row detail.