Glassmere Terminals

Alternate elastic rail clip | Board decision brief

Saltmarsh Energy  |  For Josefa Ferreira and Elias Sepulveda (Contracting & Legal)  |  07 March 2026

Decision Summary

Saltmarsh requests conditional permission to run the alternate elastic rail clip through the proposed staged Glassmere trial, with no unrestricted alternate listing until the unresolved verification-sample finding is addressed and the trial record is reviewed.

| Headline current position | Basis |
| --- | --- |
| 5 of 6 records in a decision-ready state; 1 remains unresolved | Replay of opening register + all 8 review events; each stable key counted once. |

Decision-ready: TECH-01 and TECH-02 are closed; EVID-01 is accepted only with its test-condition limitation; TRIAL-01 is Gate 1 ready; COMM-01 is accepted.

Decision condition: TECH-EDGE-01 is unresolved because the later required verification sample was not accepted (EV-004 / REV-EDGE-02).

Service-History Comparison

| Item | Relevant in-track history | Decision meaning | Source |
| --- | --- | --- | --- |
| Saltmarsh alternate | 7.3 years | Shorter record; material uncertainty remains. | HIST-01 |
| Current incumbent | 31.8 years | Longer established field record. | HIST-01 |

The alternate has a substantially shorter field-service record than the incumbent (7.3 versus 31.8 years). Saltmarsh concedes this gap; fatigue testing supports the bounded trial but does not erase it.

Technical Evidence

| Measured item | Result | Evidence |
| --- | --- | --- |
| Test population | 12 alternate clips | FAT-01 |
| Applied condition | 1.5× nominal service load; 2.0 million cycles | FAT-01 |
| Observed outcome | 12/12 completed; no fracture or loss of retention | FAT-02 |

Interpretation: these results support performance under the stated accelerated condition. They are not proof of equivalent field life, and no such equivalence is claimed. (FAT-01/FAT-02)

Residual Concerns

| Key | Replayed current state | Why it matters | Last event / source |
| --- | --- | --- | --- |
| TECH-EDGE-01 | Unresolved | Required verification sample was rejected after an earlier apparent closure; do not treat as fully closed. | EV-004 / REV-EDGE-02 |
| EVID-01 | Accepted — limited to stated test condition | Accelerated test boundary limits extrapolation to field life. | EV-006 / REV-EVID-02 |
| Date convention | Disclosed assumption | 02/03/2026 is retained as DD/MM/YYYY (2 March 2026); MM/DD would be 3 February. Both fall after EV-005 and before EV-007, so the replayed predecessor/successor order is unchanged. | EV-006 |

Staged Trial

| Stage / window | Control and evidence | Gate / escalation | Owner |
| --- | --- | --- | --- |
| 1 ¦ 0–30 days | Baseline fit-up inspection; rail-seat and clip-position photographs. (TRIAL-01) | Proceed when checklist is complete; escalate any damage or misfit. | Lucia Jelinek |
| 2 ¦ 31–90 days | Inspections at day 30 and day 90; record retention and visible wear. (TRIAL-02) | Continue only with no loss of retention and complete wear record; stop/review on deviation. | Mateo Ainsworth |
| 3 ¦ 91–180 days | End-of-trial condition review and evidence pack. (TRIAL-03) | Recommend alternate listing only after records review and resolution of TECH-EDGE-01. | Mateo Ainsworth + Lucia Jelinek |

These are proposed controls from Saltmarsh evidence, subject to Glassmere confirmation. Timing is a proposed 180-day window, not a field-life guarantee.

Commercial Position

Supplied unit rate: USD 18.47 per clip (COMM-01; source value 18.4700000003 rounded to sensible currency precision). The rate covers clip supply only; installation, inspection, and trial administration are outside this unit rate.

Decision Requested

Approve a conditional, staged trial of Saltmarsh's alternate elastic rail clip for the defined Glassmere maintenance-equipment scope, subject to the gates above. Do not grant unrestricted approved-alternate status on the current evidence. Require TECH-EDGE-01 verification-sample resolution before any final standards listing.

Next Actions

| Action | Owner | Timing / completion condition |
| --- | --- | --- |
| Confirm trial scope, equipment list and Stage 1 checklist | Lucia Jelinek | Before Stage 1 start; Glassmere confirmation |
| Resolve or repeat the rejected TECH-EDGE-01 verification sample and record acceptance | Mateo Ainsworth | Before Stage 3 recommendation |
| Run day-30 and day-90 inspections; retain photographs and wear/retention records | Mateo Ainsworth | Within 31–90-day Stage 2 window |
| Confirm commercial treatment of installation and trial administration | Lachlan Mikkelsen | Before contracting approval |
| Review end-of-trial evidence and decide on listing | Josefa Ferreira / Elias Sepulveda | At Stage 3 close, 91–180 days |

Assumptions & Limitations

The mixed-format event date 02/03/2026 is interpreted as DD/MM/YYYY (2 March 2026), consistent with the source context; the alternate reading does not change event ordering here.

The headline counts six distinct register keys once after replay; “decision-ready” includes Closed, Accepted, Accepted — limited to stated test condition, and Gate 1 ready. The unresolved edge case is excluded.

Only supplied facts are used. Trial gates are proposals, not observed results or guarantees. Accelerated fatigue evidence is bounded to the stated test condition.