## 3-month roadmap
Saltmarsh Growers Co-operative — 12-week discovery & roadmap
Kestrel Lane Advisory ¦ Fixed fee: £18,600 excluding VAT and agreed travel ¦ No implementation costs included
Purpose: decision-quality evidence, prioritised roadmap, decision record and handover pack — not a working system, product approval or procurement decision.
Decision context: member-elected technology panel meets 14 October to decide whether to fund the engagement.
Phase | Weeks | Activity | Saltmarsh owner | Kestrel owner | Evidence / output | Depends on | Decision or status | If incomplete / confidence
Mobilisation | W1 | Kick-off: confirm purpose, boundaries, contact list and weekly check-in. | Karin Abara (sponsor) | Lorcan Egwuatu | Agreed scope; contact plan; open evidence log. | Panel funding decision | Start only after scope is agreed. | If scope is unclear, log change and escalate to Karin; panel decides material change.
Mobilisation | W1–2 | Arrange interviews and request access to relevant records and existing shared tools. | Karin Abara | Lorcan Egwuatu | Interview schedule; access tracker. | Kick-off; member availability | Planned. | If unavailable, use a group session or existing record; record gap and confidence.
Discovery | W3–5 | Member and volunteer interviews: what helps, what gets in the way, desired outcomes and pain points. | Panel representative | Lorcan Egwuatu | Interview themes; needs and pain-points log. | Interview schedule | Evidence gathering. | Missed voice is marked “unverified”; no finding is presented as confirmed without validation.
Discovery | W3–5 | Current-state review of working practices, information handling, access, risks and ownership. | Volunteer helpers | Lorcan Egwuatu | Current-state baseline; risk and ownership map. | Access tracker; volunteer knowledge | Evidence gathering. | Missing access: substitute existing records where possible; flag limitation, owner and effect on confidence.
Synthesis | W6 | Bring evidence together; separate confirmed findings, assumptions and unresolved questions. | Karin Abara | Lorcan Egwuatu | Baseline + evidence log with confidence ratings. | Interview themes; current-state baseline | Ready for Gate 1. | Open gaps remain assumptions, not findings; panel sees timing/confidence effect.
Decision gate 1 | End W6 | Review evidence and proposed priority criteria: member value, urgency, effort, risk and confidence. | Technology panel | Lorcan Egwuatu | Approved or revised priority criteria; decision record. | Baseline + evidence log | PANEL: accept, revise, defer or reject priorities. | If evidence is insufficient, defer affected item or request focused follow-up; do not guess.
Prioritisation | W7–8 | Score improvement themes against approved criteria and evidence; identify dependencies. | Panel representative | Lorcan Egwuatu | Prioritised options; dependency and risk view. | Gate 1 criteria; evidence log | Draft priorities. | Low-confidence items labelled provisional and carry validation needed.
Roadmap drafting | W9 | Turn agreed priorities into a practical sequence, owners, prerequisites and decision points. | Karin Abara | Lorcan Egwuatu | Draft roadmap and ownership outline. | Prioritised options; dependencies | Draft for validation. | Scope change is logged; Karin escalates material timing or cost effect to panel.
Validation | W10 | Working session: Saltmarsh checks findings, wording, priorities and what remains unknown. | Technology panel | Lorcan Egwuatu | Validated findings; corrections; unresolved questions. | Draft roadmap; decision record | Panel confirmation, not product approval. | Disputed finding stays open with named owner; roadmap states assumption rather than certainty.
Decision package | W11 | Complete the roadmap, risk responses, decision record and next-stage choices. | Karin Abara | Lorcan Egwuatu | Final decision package; handover pack. | Validated findings | Ready for final review. | Any open gap is retained in handover pack with owner and validation route.
Handover | W12 | Shared handover session: walk through evidence, priorities, files, owners and how to update the roadmap. | Karin Abara + panel representative | Lorcan Egwuatu | Saltmarsh-owned handover pack; maintained decision record. | Final decision package | Knowledge transfer completed. | If owner absent, reschedule within W12; note any transfer not completed.
Decision gate 2 | End W12 | Final review and acceptance of discovery outputs; decide whether any separate next-stage work is warranted. | Technology panel | Lorcan Egwuatu | Accepted, revised or deferred discovery outputs. | Handover pack | PANEL: accept, revise, defer or reject. No automatic procurement or implementation approval. | Unresolved items remain explicitly deferred with owner; discovery closes on agreed record.
Assumptions, open questions and active risks
Type | Item | Potential effect | Owner | Response / decision needed
Assumption | Relevant records can be shared within W1–2. | Delays reduce confidence in baseline. | Karin Abara | Use available records; log missing evidence; panel decides whether focused follow-up is needed.
Open question | Which working practices require urgent attention? | Priority order may change after validation. | Technology panel | Decide at Gate 1 using member value, urgency, effort, risk and confidence.
Risk | Volunteer dependency or unreviewed workarounds continue during discovery. | Lost knowledge, inconsistent access, shadow IT. | Karin Abara | Record urgent issue; pause new workaround or purchase pending proportionate panel decision.
Risk | Scope expands into implementation. | Time and fee no longer match discovery purpose. | Lorcan Egwuatu | Log change; explain impact; panel accepts, revises, defers or rejects before work changes.
Risk | Named owner cannot attend validation or handover. | Findings may be misunderstood after adviser leaves. | Karin Abara | Nominate delegate or reschedule in W12; record transfer gap and retained ownership.