## Recovery Schedule
Ballantry Utilities ¦ Glassmere Press tooling recovery
Baseline is conditional: insurer acknowledgement is targeted 09-Dec-2025 and still pending at issue. Customs release is expected 16-Dec (downside 19-Dec).
Access windows: 06:00–16:00 on 10, 12, 17, 19 Dec 2025 and 13, 14 Jan 2026. One 8-hour low-loader trip per window; max two standard sets, D03 alone.
Set | Class | Customs | Need date | Trip | Access window | Collection / load | Receipt | Layout slot | Layout report | Proving | Forecast ready | Predecessors / hold points | Primary handoff owner | Required evidence | Baseline status | Customs downside
D01 | Standard | No | 2026-01-13 | T1 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-11 | 2025-12-11 16:00 | 2025-12-12 | 2025-12-12 | Insurance ack; access; transport readiness | Buyer / transport / quality | Signed custody; photos; receipt check; layout report; proof assessment | Forecast on time (conditional gates) | Not affected by customs branch
D02 | Standard | No | 2026-01-13 | T1 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-12 | 2025-12-12 16:00 | 2025-12-15 | 2025-12-15 | Insurance ack; access; transport readiness | Buyer / transport / quality | Signed custody; photos; receipt check; layout report; proof assessment | Forecast on time (conditional gates) | Not affected by customs branch
D03 | Oversized | No | 2026-01-13 | T2 | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-15 | 2025-12-15 16:00 | 2025-12-16 | 2025-12-16 | Insurance ack; access; route/permit; lift plan | Buyer / transport / quality | Signed custody; photos; route confirmation; layout report; proof assessment | Forecast on time (conditional gates) | Not affected by customs branch
D04 | Standard | No | 2026-01-16 | T3 | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-17 16:00 | 2025-12-18 | 2025-12-18 | Insurance ack; access; transport readiness | Buyer / transport / quality | Signed custody; photos; receipt check; layout report; proof assessment | Forecast on time (conditional gates) | Not affected by customs branch
D05 | Standard | No | 2026-01-16 | T3 | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-18 | 2025-12-18 16:00 | 2025-12-19 | 2025-12-19 | Insurance ack; access; transport readiness | Buyer / transport / quality | Signed custody; photos; receipt check; layout report; proof assessment | Forecast on time (conditional gates) | Not affected by customs branch
D06 | Standard | No | 2026-01-16 | T4 | 2025-12-19 | 2025-12-19 | 2025-12-20 | 2026-01-13 | 2026-01-13 16:00 | 2026-01-14 | 2026-01-15 | Insurance ack; access; transport readiness; plant reopens | Buyer / transport / quality | Signed custody; photos; quarantine receipt; layout report; proof assessment | Forecast on time (zero float after reopen) | Not affected by customs branch
D07 | Standard | No | 2026-01-16 | T4 | 2025-12-19 | 2025-12-19 | 2025-12-20 | 2026-01-14 | 2026-01-14 16:00 | 2026-01-15 | 2026-01-16 | Insurance ack; access; transport readiness; plant reopens | Buyer / transport / quality | Signed custody; photos; quarantine receipt; layout report; proof assessment | Forecast on time (zero float) | Not affected by customs branch
D08 | Standard | Yes | 2026-01-23 | T5 | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-15 | 2026-01-15 16:00 | 2026-01-16 | 2026-01-16 | Insurance ack; access; written customs release (expected 16-Dec) | Buyer / customs / transport / quality | Customs release; signed custody; photos; receipt check; layout report; proof assessment | Forecast on time (expected customs case) | If release only 19-Dec: HOLD Jan load; no later offered access (need date unattainable without added window)
D09 | Standard | Yes | 2026-01-23 | T5 | 2026-01-13 | 2026-01-13 | 2026-01-13 | 2026-01-16 | 2026-01-16 16:00 | 2026-01-19 | 2026-01-19 | Insurance ack; access; written customs release (expected 16-Dec) | Buyer / customs / transport / quality | Customs release; signed custody; photos; receipt check; layout report; proof assessment | Forecast on time (expected customs case) | If release only 19-Dec: HOLD Jan load; no later offered access (need date unattainable without added window)
D10 | Standard | Yes | 2026-01-23 | T6 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-19 | 2026-01-19 16:00 | 2026-01-20 | 2026-01-20 | Insurance ack; access; written customs release (expected 16-Dec) | Buyer / customs / transport / quality | Customs release; signed custody; photos; receipt check; layout report; proof assessment | Forecast on time (expected customs case) | If release only 19-Dec: HOLD Jan load; no later offered access (need date unattainable without added window)
D11 | Standard | Yes | 2026-01-23 | T6 | 2026-01-14 | 2026-01-14 | 2026-01-14 | 2026-01-20 | 2026-01-20 16:00 | 2026-01-21 | 2026-01-21 | Insurance ack; access; written customs release (expected 16-Dec) | Buyer / customs / transport / quality | Customs release; signed custody; photos; receipt check; layout report; proof assessment | Forecast on time (expected customs case) | If release only 19-Dec: HOLD Jan load; no later offered access (need date unattainable without added window)
Control register
Insurance | Written acknowledgement must be received and acknowledged before any die is loaded; target 09-Dec is not confirmation. | [10 empty] | Insurer / buyer | Hold loading
Customs | D08–D11 require written release. Expected 16-Dec 08:00; downside 19-Dec 08:00. | [10 empty] | Customs specialist | Hold affected loading
Administrator access | Only listed 06:00–16:00 windows; site release record and signed custody acknowledgement required before departure. | [10 empty] | Administrator / buyer | Gate each trip
Transport | Transport planner confirms competent lifting/rigging, restraint, equipment suitability, and D03 route/permit; buyer coordinates only. | [10 empty] | Imani / transport specialist | Hold load
Receiving | Plant confirms unloading slot, handling capacity, secure quarantine/storage, and preservation before arrival. | [10 empty] | Receiving / buyer | Hold dispatch
Quality | Receipt inspection, accredited layout, proving, assessment to approved basis, then formal production disposition; proof part is not release. | [10 empty] | Selma / quality and production | Release gate
Shutdown | Receiving, laboratory and press closed 22-Dec through 12-Jan inclusive. | [10 empty] | Plant owner | No site work
Breakpoint logic
• Insurance: acknowledgement later than 09-Dec 16:00 loses the 10-Dec trip; D01–D03 restart need dates are then exposed because later windows are already allocated.
• Non-customs access: missing 17-Dec or 19-Dec collection leaves D04–D07 without a permitted pre-shutdown trip; their 16-Jan need is unattainable without a new window.
• Quality: D06 layout 13-Jan and D07 layout 14-Jan are the zero-float restart slots; losing either lab/press slot threatens 16-Jan.
• Customs downside: release at 19-Dec 08:00 is too late to make the 13/14-Jan loads conditional; with no later offered access, D08–D11 cannot meet 23-Jan absent an added window.