## Call-off Budget
Redcliffe Press call-off budget and control checks | [11 empty] | Source controls and update rules
Source basis: redcliffe_press_control_pack.pdf ¦ as at 20 June 2026 ¦ GBP excluding VAT | [11 empty] | As-of date | 2026-06-20 | Static source date; no external market check
Pale yellow = source-loaded editable inputs. Pale green = calculated formula. Change Qty or Rate/fixed GBP to update totals and controls. | [11 empty] | Preceding period | 2026-04-01 to 2026-06-30 | PRE label in detailed register
Period definitions: PRE = 1 Apr-30 Jun 2026; CALL = 1 Jul-30 Sep 2026. Source totals use the local 7.5% contingency reserve convention. | [11 empty] | Call-off period | 2026-07-01 to 2026-09-30 | CALL label in detailed register
[12 empty] | Contingency rate | 7.5% | Editable source input; applies only to eligible base
Line ID | Period | Month | Cost category | Activity class | Work item | Unit | Qty | Rate / fixed GBP | Line cost GBP | Contingency eligible? | Source trace | Eligible categories | Production,Setup,Delivery | Production, Setup and Delivery
P01 | PRE | Apr-26 | Production | Recurring | Community Update A5 16pp | copies | 3250 | 0.4 | 1300 | Yes | Control pack Appendix A ¦ P01 | Excluded category | Pass-through | Postal distribution pass-through
P02 | PRE | May-26 | Production | Recurring | Community Update A5 16pp | copies | 3250 | 0.4 | 1300 | Yes | Control pack Appendix A ¦ P02 | Material variance % | 15% | Both percentage and GBP threshold apply
P03 | PRE | Jun-26 | Production | Recurring | Community Update A5 16pp | copies | 3250 | 0.4 | 1300 | Yes | Control pack Appendix A ¦ P03 | Material variance GBP | 1000 | Both percentage and GBP threshold apply
P04 | PRE | Apr-26 | Production | Recurring | Committee papers inserts A4 mono | copies | 1000 | 0.08 | 80 | Yes | Control pack Appendix A ¦ P04 | Call-off ceiling GBP | 14000 | Includes the defined contingency reserve
P05 | PRE | May-26 | Production | Recurring | Committee papers inserts A4 mono | copies | 1000 | 0.08 | 80 | Yes | Control pack Appendix A ¦ P05 | Source control total | 13158.1 | Control pack financial summary; use for cross-file review
P06 | PRE | Jun-26 | Production | Recurring | Committee papers inserts A4 mono | copies | 1000 | 0.08 | 80 | Yes | Control pack Appendix A ¦ P06 | Zero denominator | n/a | Explain a new/specialist line; do not divide by zero
P07 | PRE | Apr-26 | Production | Recurring | Large-print community packs 18pt | packs | 30 | 3.4 | 102 | Yes | Control pack Appendix A ¦ P07 | Update owner | Administrative Services Manager | Update when scope, quantity, rate, route, release or timing changes
P08 | PRE | May-26 | Production | Recurring | Large-print community packs 18pt | packs | 30 | 3.4 | 102 | Yes | Control pack Appendix A ¦ P08
P09 | PRE | Jun-26 | Production | Recurring | Large-print community packs 18pt | packs | 30 | 3.4 | 102 | Yes | Control pack Appendix A ¦ P09
P10 | PRE | Apr-26 | Setup | One-off | Pre-press and proof PDF package | fixed | 1 | 540 | 540 | Yes | Control pack Appendix A ¦ P10
P11 | PRE | Apr-26 | Delivery | Recurring | Council-site delivery slot | slot | 1 | 160 | 160 | Yes | Control pack Appendix A ¦ P11
P12 | PRE | May-26 | Delivery | Recurring | Council-site delivery slot | slot | 1 | 160 | 160 | Yes | Control pack Appendix A ¦ P12
P13 | PRE | Jun-26 | Delivery | Recurring | Council-site delivery slot | slot | 1 | 160 | 160 | Yes | Control pack Appendix A ¦ P13
P14 | PRE | Apr-26 | Pass-through | Recurring | Postal distribution pass-through | month | 1 | 300 | 300 | No | Control pack Appendix A ¦ P14
P15 | PRE | May-26 | Pass-through | Recurring | Postal distribution pass-through | month | 1 | 300 | 300 | No | Control pack Appendix A ¦ P15
P16 | PRE | Jun-26 | Pass-through | Recurring | Postal distribution pass-through | month | 1 | 300 | 300 | No | Control pack Appendix A ¦ P16
C01 | CALL | Jul-26 | Production | Recurring | Community Update A5 16pp | copies | 4000 | 0.44 | 1760 | Yes | Control pack Appendix A ¦ C01
C02 | CALL | Aug-26 | Production | Recurring | Community Update A5 16pp | copies | 4000 | 0.44 | 1760 | Yes | Control pack Appendix A ¦ C02
C03 | CALL | Sep-26 | Production | Recurring | Community Update A5 16pp | copies | 4000 | 0.44 | 1760 | Yes | Control pack Appendix A ¦ C03
C04 | CALL | Jul-26 | Production | Recurring | Committee papers inserts A4 mono | copies | 1200 | 0.085 | 102 | Yes | Control pack Appendix A ¦ C04
C05 | CALL | Aug-26 | Production | Recurring | Committee papers inserts A4 mono | copies | 1200 | 0.085 | 102 | Yes | Control pack Appendix A ¦ C05
C06 | CALL | Sep-26 | Production | Recurring | Committee papers inserts A4 mono | copies | 1200 | 0.085 | 102 | Yes | Control pack Appendix A ¦ C06
C07 | CALL | Jul-26 | Production | Recurring | Large-print community packs 18pt | packs | 40 | 3.6 | 144 | Yes | Control pack Appendix A ¦ C07
C08 | CALL | Aug-26 | Production | Recurring | Large-print community packs 18pt | packs | 40 | 3.6 | 144 | Yes | Control pack Appendix A ¦ C08
C09 | CALL | Sep-26 | Production | Recurring | Large-print community packs 18pt | packs | 40 | 3.6 | 144 | Yes | Control pack Appendix A ¦ C09
C10 | CALL | Jul-26 | Setup | One-off | Pre-press and proof PDF package | fixed | 1 | 720 | 720 | Yes | Control pack Appendix A ¦ C10
C11 | CALL | Sep-26 | Production | Specialist | Tactile emergency-route foldout raised-line braille | copies | 180 | 15.5 | 2790 | Yes | Control pack Appendix A ¦ C11
C12 | CALL | Sep-26 | Setup | Specialist | Tactile master and braille tooling | fixed | 1 | 875 | 875 | Yes | Control pack Appendix A ¦ C12
C13 | CALL | Jul-26 | Delivery | Recurring | Council-site delivery slot | slot | 1 | 185 | 185 | Yes | Control pack Appendix A ¦ C13
C14 | CALL | Aug-26 | Delivery | Recurring | Council-site delivery slot | slot | 1 | 185 | 185 | Yes | Control pack Appendix A ¦ C14
C15 | CALL | Sep-26 | Delivery | Recurring | Council-site delivery slot | slot | 1 | 185 | 185 | Yes | Control pack Appendix A ¦ C15
C16 | CALL | Sep-26 | Delivery | Specialist | Secure courier tactile foldouts | journey | 1 | 110 | 110 | Yes | Control pack Appendix A ¦ C16
C17 | CALL | Jul-26 | Pass-through | Recurring | Postal distribution pass-through | month | 1 | 420 | 420 | No | Control pack Appendix A ¦ C17
C18 | CALL | Aug-26 | Pass-through | Recurring | Postal distribution pass-through | month | 1 | 420 | 420 | No | Control pack Appendix A ¦ C18
C19 | CALL | Sep-26 | Pass-through | Recurring | Postal distribution pass-through | month | 1 | 420 | 420 | No | Control pack Appendix A ¦ C19
Period summary and variance analysis
Basis | Preceding period (PRE) | Call-off period (CALL) | Variance GBP | Variance % | Control interpretation
Eligible supplier cost: Production + Setup + Delivery | 5466 | 11068 | 5602 | 102.5% | Supplier cost subtotal
Postal distribution pass-through | 900 | 1260 | 360 | 40% | Excluded from contingency
Contingency reserve at source rate | 409.95 | 830.1 | 420.15 | 102.5% | 7.5% of eligible supplier cost only
Period control total | 6775.95 | 13158.1 | 6382.15 | 94.19% | Call-off control value; not an invoice total
Approved call-off ceiling | n/a | 14000 |  |  | Source control ceiling including contingency
Headroom to approved ceiling | n/a | 841.9 |  |  | Do not treat as authority for optional scope
Material variance decision |  | YES - ESCALATE | 6382.15 | 94.19% | Threshold: both 15.0% and GBP 1,000.00
Monthly control-total roll-up
Period | Month | Eligible supplier cost | Pass-through | Contingency | Control total | Arithmetic check
PRE | Apr-26 | 2182 | 300 | 163.65 | 2645.65 | PASS
PRE | May-26 | 1642 | 300 | 123.15 | 2065.15 | PASS
PRE | Jun-26 | 1642 | 300 | 123.15 | 2065.15 | PASS
CALL | Jul-26 | 2911 | 420 | 218.325 | 3549.325 | PASS
CALL | Aug-26 | 2191 | 420 | 164.325 | 2775.325 | PASS
CALL | Sep-26 | 5966 | 420 | 447.45 | 6833.45 | PASS
Visible control checks
Detailed line arithmetic | PASS | Each detail line cost is Qty x Rate/fixed.
Preceding period roll-up | PASS | Monthly PRE control totals reconcile to summary.
Call-off period roll-up | PASS | Monthly CALL control totals reconcile to summary.
Contingency formula | PASS | Rate applies only to eligible supplier cost.
Source/cross-file control total | PASS | Compare operating plan call-off total to source control total.
Ceiling/headroom | PASS | Headroom must remain non-negative.
Notes: This workbook contains source-loaded cost inputs and local control values only. It contains no external links, market estimates, tax, quotation result or supplier commitment. For a changed future input, retain the revised source/approval record with the updated workbook.
Note on H7: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P01; quantity is editable for a future update.
Note on H8: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P02; quantity is editable for a future update.
Note on H9: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P03; quantity is editable for a future update.
Note on H10: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P04; quantity is editable for a future update.
Note on H11: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P05; quantity is editable for a future update.
Note on H12: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P06; quantity is editable for a future update.
Note on H13: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P07; quantity is editable for a future update.
Note on H14: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P08; quantity is editable for a future update.
Note on H15: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P09; quantity is editable for a future update.
Note on H16: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P10; quantity is editable for a future update.
Note on H17: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P11; quantity is editable for a future update.
Note on H18: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P12; quantity is editable for a future update.
Note on H19: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P13; quantity is editable for a future update.
Note on H20: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P14; quantity is editable for a future update.
Note on H21: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P15; quantity is editable for a future update.
Note on H22: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P16; quantity is editable for a future update.
Note on H23: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C01; quantity is editable for a future update.
Note on H24: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C02; quantity is editable for a future update.
Note on H25: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C03; quantity is editable for a future update.
Note on H26: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C04; quantity is editable for a future update.
Note on H27: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C05; quantity is editable for a future update.
Note on H28: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C06; quantity is editable for a future update.
Note on H29: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C07; quantity is editable for a future update.
Note on H30: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C08; quantity is editable for a future update.
Note on H31: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C09; quantity is editable for a future update.
Note on H32: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C10; quantity is editable for a future update.
Note on H33: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C11; quantity is editable for a future update.
Note on H34: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C12; quantity is editable for a future update.
Note on H35: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C13; quantity is editable for a future update.
Note on H36: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C14; quantity is editable for a future update.
Note on H37: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C15; quantity is editable for a future update.
Note on H38: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C16; quantity is editable for a future update.
Note on H39: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C17; quantity is editable for a future update.
Note on H40: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C18; quantity is editable for a future update.
Note on H41: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C19; quantity is editable for a future update.
Note on I7: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P01; rate is editable for a future update.
Note on I8: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P02; rate is editable for a future update.
Note on I9: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P03; rate is editable for a future update.
Note on I10: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P04; rate is editable for a future update.
Note on I11: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P05; rate is editable for a future update.
Note on I12: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P06; rate is editable for a future update.
Note on I13: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P07; rate is editable for a future update.
Note on I14: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P08; rate is editable for a future update.
Note on I15: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P09; rate is editable for a future update.
Note on I16: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P10; rate is editable for a future update.
Note on I17: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P11; rate is editable for a future update.
Note on I18: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P12; rate is editable for a future update.
Note on I19: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P13; rate is editable for a future update.
Note on I20: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P14; rate is editable for a future update.
Note on I21: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P15; rate is editable for a future update.
Note on I22: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line P16; rate is editable for a future update.
Note on I23: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C01; rate is editable for a future update.
Note on I24: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C02; rate is editable for a future update.
Note on I25: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C03; rate is editable for a future update.
Note on I26: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C04; rate is editable for a future update.
Note on I27: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C05; rate is editable for a future update.
Note on I28: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C06; rate is editable for a future update.
Note on I29: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C07; rate is editable for a future update.
Note on I30: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C08; rate is editable for a future update.
Note on I31: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C09; rate is editable for a future update.
Note on I32: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C10; rate is editable for a future update.
Note on I33: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C11; rate is editable for a future update.
Note on I34: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C12; rate is editable for a future update.
Note on I35: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C13; rate is editable for a future update.
Note on I36: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C14; rate is editable for a future update.
Note on I37: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C15; rate is editable for a future update.
Note on I38: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C16; rate is editable for a future update.
Note on I39: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C17; rate is editable for a future update.
Note on I40: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C18; rate is editable for a future update.
Note on I41: Loaded from redcliffe_press_control_pack.pdf, Appendix A cost record export. Line C19; rate is editable for a future update.