OSGOOD THANAPOULOS — LOCALISATION INGEST WORK ORDER

Overbrook Provisions / Quillhaven Industries  |  issued 4 November 2027

1. Delivery commitment

Overbrook Provisions will prepare the eleven listed factual-series episodes for Quillhaven Platform Relay. The platform ingest window closes at 18:00 GMT on 30 November 2027 and is unavailable for the following three weeks. All release packages must have completed ingest before that cutoff.

2. Pass order and booking

For each required language, caption lock must complete before dub-sync begins. Episode QC may begin only after every required Spanish and Portuguese caption and dub-sync pass has completed. Ingest may begin only after QC completes and all applicable release gates are met. Runtime-derived caption, dub-sync and QC effort is calculated from the pass register and booked upward to the next 5-minute increment. Each completed ingest occupies a 15-minute Relay booking.

3. Approved operating resources

Mireya Santos is the only approved language reviewer for both Spanish and Portuguese. Her rota alternates languages: Spanish bookings are permitted only on Monday, Wednesday and Friday entries; Portuguese bookings are permitted only on Tuesday and Thursday entries. She may not hold overlapping bookings. Darius Cole may operate only QC Bay 1; it is the sole approved QC bay and is single-occupancy. Quillhaven Platform Relay is available only in its dated weekday records. No overtime, substitute reviewer or second bay is authorised.

4. Clearance scenarios

FDK-204 and FDK-209 share the identified music cue. Under the Base clearance scenario, neither may be released to ingest before 26 November 2027 at 13:00 GMT. Under the Delayed-clearance scenario, neither may be released to ingest before 29 November 2027 at 11:00 GMT. Ivo Kettering is the music-clearance owner. Naledi Fairbairn is the localisation coordinator and Petra Marchetti is Quillhaven’s contracting counsel.

5. Governing terms

This work order is governed by the laws of England and Wales. It records the parties’ delivery position as at 4 November 2027. Unless a dated record provides a narrower interval, no activity may be inferred outside the supplied availability record.

Authorised for operational planning: Quillhaven Industries / Overbrook Provisions