# Closure governance memorandum

| To | From | Date | Subject |
| --- | --- | --- | --- |
| Wilhelmina Escamilla | Yewbank Associates - Planning Controls | 03 November 2027 | Sunderly Mutual open habitability case closure |

This memorandum governs the planning correction for the 36 open cases in the accompanying operations export. It is a scheduling control, not evidence of tenant contact, inspection findings, qualifications beyond the roster, or completed case closure.

# 1. Authority and cutoff

Where the rejected draft conflicts with this memorandum, this memorandum controls. Work may be planned only on 04-05, 08-12, 15-19, and 22-23 November 2027, in the local half-day slots AM (08:30-12:30) and PM (13:30-17:30). The oversight submission cutoff is 24 November 2027 at 17:00 local time. A case is planned for closure only when Final Determination & Closure Record (FDCR) follows its required inspection; no planning label is completion evidence.

# 2. Required closure sequence

Each source case requires Tenant Contact, then the jurisdiction-specific inspection below, then FDCR. The sequence is strict: activity dates and times must increase, and activities in the same half-day slot do not satisfy the predecessor rule. Tenant Contact is unavailable from 17 through 19 November inclusive. When a contact is delayed by that blackout, its inspection and FDCR may not occupy the blocked downstream slot; they must follow the actual contact time. Generic Property Review is not an accepted inspection step.

| Case jurisdiction | Required inspection | Roster qualification | Eligible roster names |
| --- | --- | --- | --- |
| Ontario | Ontario Habitability Inspection (OHI) | Ontario OHI qualification | Priya Ingram; Rowan Singh |
| Michigan | Michigan Habitability Inspection (MHI) | Michigan MHI qualification | Micah Pierce; Rowan Singh |

# 3. Capacity, availability and routing

Use only names in the supplied resource roster and only their marked Available slots. Each person may perform at most 4.0 case-work hours in a half-day and 8.0 case-work hours in a day. The dispatch ceiling is 12 case-activity records in a half-day. Tenant Contact and FDCR are mutually exclusive for the same owner in the same half-day, even if their nominal hours could fit. These controls apply in addition to, not instead of, qualification checks.

Whenever the same owner moves from Ontario case work to Michigan case work, or from Michigan case work to Ontario case work, reserve a complete half-day as Jurisdiction Changeover immediately before the incoming jurisdiction's case work. The changeover is unavailable for case work, consumes 4.0 capacity hours, and carries 0.0 case-activity effort because it is not a source case activity. Show the changeover separately in owner capacity indicators. A jurisdiction change without this full half-day buffer is not eligible.

| Exception | Treatment |
| --- | --- |
| 17-19 Nov tenant-contact blackout | No Tenant Contact in any slot; downstream work follows the actual contact. |
| Approved unavailable roster slot | No activity may be assigned, including a changeover. |
| Jurisdiction switch | A full AM or PM Jurisdiction Changeover is required before incoming case work. |
| Rejected draft wording | Keep it for comparison only; it does not override this memorandum. |

# 4. Review vocabulary

Use Planned for a future scheduled activity, Completed only when a supplied source independently supports completion, Forecast for a case not scheduled by the cutoff, Blocked for a rule-constrained unschedulable option, and Changeover for the non-case capacity reservation. Do not recast a source case fact, tenant response, inspection result, or credential. For this planning exercise, any full-completion choice means every case has a planned FDCR by the cutoff, not that the case is already completed.

Control note: the resource roster and date-by-slot availability extract are the authoritative operational detail for named owners. The rejected draft does not establish an exception to them.