## Delivery Register
Alderwick Utilities — video delivery register
PMO export ¦ snapshot 20 Aug 2026 16:30 ¦ milestones are contractual unless stated otherwise
Module | title | Jurisdiction | Scope/status | Contract baseline: accepted master | Actual: review copy | Actual: accepted master | Asset handover / status | Owner: acceptance
AU-01 | Isolation valves: site safe | England | Completed | 2026-02-02 | 2026-01-29 | 2026-02-02 | Complete | Alderwick Acceptance Lead
AU-02 | Control-room permit basics | Scotland | Completed | 2026-02-16 | 2026-02-11 | 2026-02-16 | Complete | Alderwick Acceptance Lead
AU-03 | Pumping station access | England | Completed | 2026-03-02 | 2026-02-26 | 2026-03-02 | Complete | Alderwick Acceptance Lead
AU-04 | Pressure management overview | Scotland | Completed | 2026-03-16 | 2026-03-13 | 2026-03-18 | Complete | Alderwick Acceptance Lead
AU-05 | Confined-space entry | England | Completed | 2026-03-30 | 2026-03-31 | 2026-04-02 | Complete after partial receipt | Alderwick Acceptance Lead
AU-06 | Meter exchange workflow | Scotland | Completed | 2026-04-13 | 2026-04-14 | 2026-04-17 | Complete | Alderwick Acceptance Lead
AU-07 | Incident reporting: field | England | Completed | 2026-04-27 | 2026-04-30 | 2026-05-04 | Complete | Alderwick Acceptance Lead
AU-08 | Chlorination records | Scotland | Completed | 2026-05-11 | 2026-05-11 | 2026-05-14 | Complete | Alderwick Acceptance Lead
AU-09 | Pump-start checks | England | Completed | 2026-05-25 | 2026-05-28 | 2026-06-01 | Complete after partial receipt | Alderwick Acceptance Lead
AU-10 | Customer interruption notices | Scotland | Completed | 2026-06-08 | 2026-06-08 | 2026-06-11 | Complete | Alderwick Acceptance Lead
AU-11 | Network sampling chain | England | Completed | 2026-06-22 | 2026-06-25 | 2026-06-29 | Complete | Alderwick Acceptance Lead
AU-12 | Escalation duty handover | Scotland | Completed | 2026-07-06 | 2026-07-07 | 2026-07-10 | Complete after partial receipt | Alderwick Acceptance Lead
AU-13 | Valve chamber inspection | England | Completed | 2026-07-20 | 2026-07-23 | 2026-07-27 | Complete | Alderwick Acceptance Lead
AU-14 | Winter readiness dispatch | Scotland | Completed | 2026-08-03 | 2026-08-04 | 2026-08-07 | Complete | Alderwick Acceptance Lead
AU-15 | Mains repair isolation | England | Remaining / in scope | 2026-09-15 |  |  | Confirmed—21 Aug | Alderwick Acceptance Lead
AU-16 | Telemetry alarm triage | Scotland | Remaining / in scope | 2026-09-22 |  |  | Confirmed—24 Aug | Alderwick Acceptance Lead
AU-17 | Reservoir drawdown brief | England | Remaining / in scope | 2026-09-24 |  |  | Unconfirmed—expected 25 Aug | Alderwick Acceptance Lead
AU-18 | Wastewater overflow response | Scotland | Remaining / in scope | 2026-09-29 |  |  | Confirmed—26 Aug | Alderwick Acceptance Lead
AU-19 | Archive footage tidy-up | England | Out of scope — deferred |  |  |  | n/a
Export note: AU-19 remains visible from the source system but is not in the recovery release.

## Activity evidence
Alderwick Utilities — activity timestamp extract
Events reproduced from PMO log; dates are working-day completion dates. Empty fields were not populated in the source system.
Module | Event | Date | Recorded by | Evidence / operational note
AU-01 | Asset handover complete | 2026-01-06 | Alderwick asset liaison
AU-01 | Script ready for SME | 2026-01-13 | Vantridge editorial lead
AU-01 | SME approval requested | 2026-01-13 | Vantridge producer | Single approval queue.
AU-01 | SME script approval | 2026-01-14 | Alderwick subject expert | Returned after queued review.
AU-01 | Edit complete | 2026-01-15 | Vantridge post supervisor
AU-01 | Colour grade complete | 2026-01-20 | Northline Colour
AU-01 | Editorial review complete | 2026-01-22 | Vantridge editorial lead
AU-01 | Client review record reconciled | 2026-01-23 | Vantridge producer
AU-01 | England accessibility complete | 2026-01-27 | Vantridge accessibility lead
AU-01 | England release QA complete | 2026-01-29 | Vantridge release manager
AU-01 | Accepted master | 2026-02-02 | Alderwick Acceptance Lead
AU-02 | Asset handover complete | 2026-01-16 | Alderwick asset liaison
AU-02 | Script ready for SME | 2026-01-23 | Vantridge editorial lead
AU-02 | SME approval requested | 2026-01-23 | Vantridge producer | Single approval queue.
AU-02 | SME script approval | 2026-01-26 | Alderwick subject expert | Returned after queued review.
AU-02 | Edit complete | 2026-01-27 | Vantridge post supervisor
AU-02 | Colour grade complete | 2026-01-30 | Northline Colour
AU-02 | Editorial review complete | 2026-02-03 | Vantridge editorial lead
AU-02 | Client review record reconciled | 2026-02-04 | Vantridge producer
AU-02 | Scotland accessibility adaptation complete | 2026-02-06 | Vantridge accessibility lead
AU-02 | Scotland release check complete | 2026-02-11 | Alderwick Scotland release lead
AU-02 | Accepted master | 2026-02-16 | Alderwick Acceptance Lead
AU-03 | Asset handover complete | 2026-02-03 | Alderwick asset liaison
AU-03 | Script ready for SME | 2026-02-10 | Vantridge editorial lead
AU-03 | SME approval requested | 2026-02-10 | Vantridge producer | Single approval queue.
AU-03 | SME script approval | 2026-02-11 | Alderwick subject expert | Returned after queued review.
AU-03 | Edit complete | 2026-02-12 | Vantridge post supervisor
AU-03 | Colour grade complete | 2026-02-17 | Northline Colour
AU-03 | Editorial review complete | 2026-02-19 | Vantridge editorial lead
AU-03 | Client review record reconciled | 2026-02-20 | Vantridge producer
AU-03 | England accessibility complete | 2026-02-24 | Vantridge accessibility lead
AU-03 | England release QA complete | 2026-02-26 | Vantridge release manager
AU-03 | Accepted master | 2026-03-02 | Alderwick Acceptance Lead
AU-04 | Asset handover complete | 2026-02-11 | Alderwick asset liaison
AU-04 | Script ready for SME | 2026-02-18 | Vantridge editorial lead
AU-04 | SME approval requested | 2026-02-18 | Vantridge producer | Single approval queue.
AU-04 | SME script approval | 2026-02-25 | Alderwick subject expert | Returned after queued review.
AU-04 | Edit complete | 2026-02-26 | Vantridge post supervisor
AU-04 | Colour grade complete | 2026-03-03 | Northline Colour
AU-04 | Editorial review complete | 2026-03-05 | Vantridge editorial lead
AU-04 | Client review record reconciled | 2026-03-06 | Vantridge producer
AU-04 | Scotland accessibility adaptation complete | 2026-03-10 | Vantridge accessibility lead
AU-04 | Scotland release check complete | 2026-03-13 | Alderwick Scotland release lead
AU-04 | Accepted master | 2026-03-18 | Alderwick Acceptance Lead
AU-05 | Asset handover received | 2026-03-03 | Alderwick asset liaison | Partial handover logged; missing stills supplied before script-ready date.
AU-05 | Asset handover completed | 2026-03-05 | Alderwick asset liaison | Completion recorded before script work became controlling.
AU-05 | Script ready for SME | 2026-03-06 | Vantridge editorial lead
AU-05 | SME approval requested | 2026-03-06 | Vantridge producer | Single approval queue.
AU-05 | SME script approval | 2026-03-16 | Alderwick subject expert | Returned after queued review.
AU-05 | Edit complete | 2026-03-17 | Vantridge post supervisor
AU-05 | Colour grade complete | 2026-03-20 | Northline Colour
AU-05 | Editorial review complete | 2026-03-24 | Vantridge editorial lead
AU-05 | Client review record reconciled | 2026-03-25 | Vantridge producer
AU-05 | England accessibility complete | 2026-03-27 | Vantridge accessibility lead
AU-05 | England release QA complete | 2026-03-31 | Vantridge release manager
AU-05 | Accepted master | 2026-04-02 | Alderwick Acceptance Lead
AU-06 | Asset handover complete | 2026-03-10 | Alderwick asset liaison
AU-06 | Script ready for SME | 2026-03-17 | Vantridge editorial lead
AU-06 | SME approval requested | 2026-03-17 | Vantridge producer | Single approval queue.
AU-06 | SME script approval | 2026-03-25 | Alderwick subject expert | Returned after queued review.
AU-06 | Edit complete | 2026-03-26 | Vantridge post supervisor
AU-06 | Colour grade complete | 2026-03-31 | Northline Colour
AU-06 | Editorial review complete | 2026-04-02 | Vantridge editorial lead
AU-06 | Client review record reconciled | 2026-04-07 | Vantridge producer
AU-06 | Scotland accessibility adaptation complete | 2026-04-09 | Vantridge accessibility lead
AU-06 | Scotland release check complete | 2026-04-14 | Alderwick Scotland release lead
AU-06 | Accepted master | 2026-04-17 | Alderwick Acceptance Lead
AU-07 | Asset handover complete | 2026-03-26 | Alderwick asset liaison
AU-07 | Script ready for SME | 2026-04-02 | Vantridge editorial lead
AU-07 | SME approval requested | 2026-04-02 | Vantridge producer | Single approval queue.
AU-07 | SME script approval | 2026-04-15 | Alderwick subject expert | Returned after queued review.
AU-07 | Edit complete | 2026-04-16 | Vantridge post supervisor
AU-07 | Colour grade complete | 2026-04-21 | Northline Colour | Block booking used after late approval; this moved grade to the next open block.
AU-07 | Editorial review complete | 2026-04-23 | Vantridge editorial lead
AU-07 | Client review record reconciled | 2026-04-24 | Vantridge producer
AU-07 | England accessibility complete | 2026-04-28 | Vantridge accessibility lead
AU-07 | England release QA complete | 2026-04-30 | Vantridge release manager
AU-07 | Accepted master | 2026-05-04 | Alderwick Acceptance Lead
AU-08 | Asset handover complete | 2026-04-08 | Alderwick asset liaison
AU-08 | Script ready for SME | 2026-04-15 | Vantridge editorial lead
AU-08 | SME approval requested | 2026-04-15 | Vantridge producer | Single approval queue.
AU-08 | SME script approval | 2026-04-22 | Alderwick subject expert | Returned after queued review.
AU-08 | Edit complete | 2026-04-23 | Vantridge post supervisor
AU-08 | Colour grade complete | 2026-04-28 | Northline Colour
AU-08 | Editorial review complete | 2026-04-30 | Vantridge editorial lead
AU-08 | Client review record reconciled | 2026-05-01 | Vantridge producer | Comments reconstructed from email for AU-08/AU-12.
AU-08 | Scotland accessibility adaptation complete | 2026-05-06 | Vantridge accessibility lead
AU-08 | Scotland release check complete | 2026-05-11 | Alderwick Scotland release lead
AU-08 | Accepted master | 2026-05-14 | Alderwick Acceptance Lead
AU-09 | Asset handover received | 2026-04-28 | Alderwick asset liaison | Partial handover logged; missing stills supplied before script-ready date.
AU-09 | Asset handover completed | 2026-04-30 | Alderwick asset liaison | Completion recorded before script work became controlling.
AU-09 | Script ready for SME | 2026-05-01 | Vantridge editorial lead
AU-09 | SME approval requested | 2026-05-01 | Vantridge producer | Single approval queue.
AU-09 | SME script approval | 2026-05-12 | Alderwick subject expert | Returned after queued review.
AU-09 | Edit complete | 2026-05-13 | Vantridge post supervisor
AU-09 | Colour grade complete | 2026-05-18 | Northline Colour
AU-09 | Editorial review complete | 2026-05-20 | Vantridge editorial lead
AU-09 | Client review record reconciled | 2026-05-21 | Vantridge producer
AU-09 | England accessibility complete | 2026-05-26 | Vantridge accessibility lead
AU-09 | England release QA complete | 2026-05-28 | Vantridge release manager
AU-09 | Accepted master | 2026-06-01 | Alderwick Acceptance Lead
AU-10 | Asset handover complete | 2026-05-01 | Alderwick asset liaison
AU-10 | Script ready for SME | 2026-05-11 | Vantridge editorial lead
AU-10 | SME approval requested | 2026-05-11 | Vantridge producer | Single approval queue.
AU-10 | SME script approval | 2026-05-20 | Alderwick subject expert | Returned after queued review.
AU-10 | Edit complete | 2026-05-21 | Vantridge post supervisor
AU-10 | Colour grade complete | 2026-05-27 | Northline Colour
AU-10 | Editorial review complete | 2026-05-29 | Vantridge editorial lead
AU-10 | Client review record reconciled | 2026-06-01 | Vantridge producer
AU-10 | Scotland accessibility adaptation complete | 2026-06-03 | Vantridge accessibility lead
AU-10 | Scotland release check complete | 2026-06-08 | Alderwick Scotland release lead
AU-10 | Accepted master | 2026-06-11 | Alderwick Acceptance Lead
AU-11 | Asset handover complete | 2026-05-27 | Alderwick asset liaison
AU-11 | Script ready for SME | 2026-06-03 | Vantridge editorial lead
AU-11 | SME approval requested | 2026-06-03 | Vantridge producer | Single approval queue.
AU-11 | SME script approval | 2026-06-10 | Alderwick subject expert | Returned after queued review.
AU-11 | Edit complete | 2026-06-11 | Vantridge post supervisor
AU-11 | Colour grade complete | 2026-06-16 | Northline Colour | Block booking used after late approval; this moved grade to the next open block.
AU-11 | Editorial review complete | 2026-06-18 | Vantridge editorial lead
AU-11 | Client review record reconciled | 2026-06-19 | Vantridge producer
AU-11 | England accessibility complete | 2026-06-23 | Vantridge accessibility lead
AU-11 | England release QA complete | 2026-06-25 | Vantridge release manager
AU-11 | Accepted master | 2026-06-29 | Alderwick Acceptance Lead
AU-12 | Asset handover received | 2026-06-08 | Alderwick asset liaison | Partial handover logged; missing stills supplied before script-ready date.
AU-12 | Asset handover completed | 2026-06-10 | Alderwick asset liaison | Completion recorded before script work became controlling.
AU-12 | Script ready for SME | 2026-06-11 | Vantridge editorial lead
AU-12 | SME approval requested | 2026-06-11 | Vantridge producer | Single approval queue.
AU-12 | SME script approval | 2026-06-19 | Alderwick subject expert | Returned after queued review.
AU-12 | Edit complete | 2026-06-22 | Vantridge post supervisor
AU-12 | Colour grade complete | 2026-06-25 | Northline Colour
AU-12 | Editorial review complete | 2026-06-29 | Vantridge editorial lead
AU-12 | Client review record reconciled | 2026-06-30 | Vantridge producer | Comments reconstructed from email for AU-08/AU-12.
AU-12 | Scotland accessibility adaptation complete | 2026-07-02 | Vantridge accessibility lead
AU-12 | Scotland release check complete | 2026-07-07 | Alderwick Scotland release lead
AU-12 | Accepted master | 2026-07-10 | Alderwick Acceptance Lead
AU-13 | Asset handover complete | 2026-06-22 | Alderwick asset liaison
AU-13 | Script ready for SME | 2026-06-29 | Vantridge editorial lead
AU-13 | SME approval requested | 2026-06-29 | Vantridge producer | Single approval queue.
AU-13 | SME script approval | 2026-07-08 | Alderwick subject expert | Returned after queued review.
AU-13 | Edit complete | 2026-07-09 | Vantridge post supervisor
AU-13 | Colour grade complete | 2026-07-14 | Northline Colour
AU-13 | Editorial review complete | 2026-07-16 | Vantridge editorial lead
AU-13 | Client review record reconciled | 2026-07-17 | Vantridge producer
AU-13 | England accessibility complete | 2026-07-21 | Vantridge accessibility lead
AU-13 | England release QA complete | 2026-07-23 | Vantridge release manager
AU-13 | Accepted master | 2026-07-27 | Alderwick Acceptance Lead
AU-14 | Asset handover complete | 2026-07-03 | Alderwick asset liaison
AU-14 | Script ready for SME | 2026-07-10 | Vantridge editorial lead
AU-14 | SME approval requested | 2026-07-10 | Vantridge producer | Single approval queue.
AU-14 | SME script approval | 2026-07-17 | Alderwick subject expert | Returned after queued review.
AU-14 | Edit complete | 2026-07-20 | Vantridge post supervisor
AU-14 | Colour grade complete | 2026-07-23 | Northline Colour
AU-14 | Editorial review complete | 2026-07-27 | Vantridge editorial lead
AU-14 | Client review record reconciled | 2026-07-28 | Vantridge producer
AU-14 | Scotland accessibility adaptation complete | 2026-07-30 | Vantridge accessibility lead
AU-14 | Scotland release check complete | 2026-08-04 | Alderwick Scotland release lead
AU-14 | Accepted master | 2026-08-07 | Alderwick Acceptance Lead
AU-15 | Asset handover target | 2026-08-21 | Alderwick asset liaison | Confirmed—21 Aug
AU-15 | Contract baseline: accepted master | 2026-09-15 | Contract schedule
AU-16 | Asset handover target | 2026-08-24 | Alderwick asset liaison | Confirmed—24 Aug
AU-16 | Contract baseline: accepted master | 2026-09-22 | Contract schedule
AU-17 | Asset handover target | 2026-08-25 | Alderwick asset liaison | Unconfirmed—expected 25 Aug
AU-17 | Contract baseline: accepted master | 2026-09-24 | Contract schedule
AU-18 | Asset handover target | 2026-08-26 | Alderwick asset liaison | Confirmed—26 Aug
AU-18 | Contract baseline: accepted master | 2026-09-29 | Contract schedule

## Planning basis
Recovery planning basis — issued 20 Aug 2026
Apply finish-to-start sequence. UK working days are Mon–Fri; 31 Aug bank holiday. Dates below are completion dates.
Control / resource | Rule or duration | Owner / evidence
Asset-readiness check | 1 working day; complete checklist required before script prep | Alderwick asset liaison / Vantridge producer
Script preparation | 2 working days after asset readiness | Vantridge editorial lead
Script approval | 2 working days; one Alderwick subject expert; maximum two completed modules per week | Alderwick subject expert
Edit | 3 working days after approval | Vantridge post supervisor
Colour grade | 2 working days after edit; Northline booked 07–08 Sep, 21–22 Sep, 05–06 Oct; capacity two modules each block | Northline Colour
Editorial review | 1 working day after grade | Vantridge editorial lead
Client review | 2 working days after editorial review; approval only when record is reconciled | Alderwick reviewer / Vantridge producer
England accessibility | 2 working days after client review | Vantridge accessibility lead
England release QA | 1 working day after England accessibility | Vantridge release manager
Scotland accessibility adaptation | 3 working days after client review | Vantridge accessibility lead
Scotland release check | 2 working days after Scotland accessibility adaptation | Alderwick Scotland release lead
Acceptance | 1 working day after jurisdiction release gate | Alderwick Acceptance Lead
Delivery terms | Review-copy delivery = upload of client review copy. Accepted-master delivery = acceptance recorded after all editorial, accessibility, jurisdiction release and acceptance checks. | Contract schedule §4.2
Commitment authority | A revised client commitment requires Alderwick change control signed by Nikolai Rosenthal. | Contract schedule §7.1
Current booking note | Northline cannot release extra colour-grade days outside these block bookings. | Booking desk, 18 Aug
Calendar note | No regional holiday differences apply in this recovery window. | PMO calendar

## Correspondence & notes
Selected correspondence and interview notes
Extracted into the project file by PMO; wording retained where material.
Date / source | Extract | Status
05 Aug 2026 — Camila Reinholt email to Alderwick | “We will deliver every remaining module by 30 September.” | Informal statement; no change-control reference
12 Aug 2026 — Nikolai Rosenthal email | “Service credits will begin next month unless I receive a credible revised schedule with a stated cause.” | Contract manager concern
14 Aug 2026 — post-production interview | “A script can be edit-ready inside a week. The recurring wait is for the same client subject expert to clear the scripts.” | Operations interview
15 Aug 2026 — asset liaison note | AU-05, AU-09 and AU-12 arrived as partial handovers; missing items were supplied before those scripts became controlling. AU-17 expected handover remains unconfirmed. | Project log
16 Aug 2026 — Northline booking desk | Grade work after late script approvals has had to wait for the next booked block on AU-07 and AU-11. | Supplier booking evidence
18 Aug 2026 — producer incident note | Review-platform comment threads vanished on AU-08 and AU-12. Comments were reconstructed from email; neither changed the recorded accepted-master date. | Control failure / audit risk
20 Aug 2026 — change-control log | No signed change control revises the accepted-master baselines or authorises the 30 September statement. | Current as-of evidence