TARGET FIELD-DATA ARCHITECTURE

Sheafield Mutual remediation framework | Decision for Malachy Oyelaran and technical assurance

# Decision at a glance

Approve one target: a managed field edge is the disconnected system of record. Managed and personally owned tablets are browser-only presentation/input endpoints to that local edge; they do not persist sample, location, observation or custody data. The edge synchronizes to Wrenfell central integration, which verifies the custody sequence and alone submits queued batches to Drakemoor through a maximum of two acknowledgement-held sessions.

| Planning baseline | Decision use |
| --- | --- |
| Framework / start | Four years; sampling starts 3 February 2027 |
| First wave | 12 crews, 18 sites; moves every 3–10 days |
| Coverage | 14 sites no dependable cellular; 4 intermittent |
| Fleet | 20 managed tablets; 28 BYOD Android/iPad, not MDM-enrollable |
| Lab boundary | At most 2 concurrent external API sessions; held until batch acknowledgement |
| Delivery envelope | 2 integration engineers × 6 weeks; security architect 8 review days; freeze 21 Dec–5 Jan |

# Scope, terms and decision criteria

Scope is field capture, custody evidence, synchronization and accepted Drakemoor receipt. Procurement and commercial renegotiation are excluded. “Operationally offline” means the crew can capture and record custody for a full shift without WAN. It does not mean data may be stored on a tablet. Under the schedule, persistent disconnected records can exist only on approved managed infrastructure, encrypted and access-logged.

Decision criteria: preserve field work under WAN loss; keep end-user devices out of the persistence trust boundary; produce inquiry-ready, attributable custody evidence; obey the two-session laboratory agreement; and fit configuration/integration inside the stated window.

# Accountabilities

| Accountable | Decision / delivery responsibility |
| --- | --- |
| Malachy Oyelaran | Architecture approval, assurance gates and readiness decision |
| Chidi Macaulay | Field workflow acceptance and pilot custody rehearsal |
| Maren Guerrero | Evidence, time and integrity assurance review |
| Kamil Dimitrov | Drakemoor interface coordination and acknowledgement test |
| Cecilia Gasparyan | Programme sponsor; receives readiness outcome |
| Integration engineers | Configuration, central integration, queue and test evidence |

# Selected target: managed-edge, browser-only field capture

One architecture is selected. Each active field location uses the existing approved managed-edge image as managed infrastructure. Its encrypted, access-logged local store is the only disconnected store. The current browser field form is configured to use the edge over a local field network; neither managed tablets nor BYOD are a system of record, custody authority or privileged trust anchor.

| UNMANAGED / END-USER ZONE | MANAGED FIELD INFRASTRUCTURE | WRENFELL CENTRAL SERVICES | DRAKEMOOR SUPPLY |
| --- | --- | --- | --- |
| 20 managed tablets + 28 BYOD Browser input only No durable sample/custody data No master keys | Approved managed-edge image Encrypted access-logged store Validation • controlled time append-only signed/hash-chained ledger | Sync verifier + central anchor Conflict/quarantine store Durable lab queue Two bounded session workers | External API Queued batch submission Status retrieval Batch acknowledgement |

Flow: ① actor signs into a short-lived browser session and scans/enters the stable sample identifier; ② browser sends over protected local transport to the edge; ③ edge locally accepts or rejects the record, creates custody evidence and returns status; ④ when WAN exists, edge sends idempotently to central verification; ⑤ central queues a lab batch; ⑥ one of at most two workers keeps its session allocated until acknowledgement, then records accepted receipt/status. All network boundaries use protected transport.

# Endpoint, identity and trust controls

Browser configuration must disable application cache/offline storage, downloads/exports, form autofill and saved credentials; prevent persistence of temporary files where the browser/OS permits; clear session data on logout; and be validated by device inspection on managed and BYOD representatives. The edge must reject any client mode that needs local durable storage.

BYOD is confined to an unprivileged browser role. It receives only the active screen and short-lived session; no reusable integration credential, edge administration capability, signing material or custody authority is resident solely on it. A separate authenticated actor action is recorded for each custody event; reauthenticate after configured inactivity, handover, or a device loss report.

Edge, central service and laboratory integration use distinct least-privilege service identities. Encryption at rest applies to the edge, central evidence store, conflict/quarantine store and laboratory queue. Keys/credentials are provisioned to managed components, rotated/replaced and revocable; loss triggers revocation and recovery without putting master secrets on BYOD.

# Record, custody and time design

| Object | Required content and control |
| --- | --- |
| Sample | Stable capture identifier (barcode/label scan where available); never renumber at a boundary. Required field checks and format/range checks occur at edge before local acceptance. |
| Custody event | Stable event ID; sample ID; authenticated responsible actor; action or transfer; UTC timestamp to one-second resolution; prior-event reference; integrity value; time-confidence indicator. |
| Immediate vs central validation | Edge enforces required fields, permitted actions, ID shape and workflow completeness. Central checks cross-site/duplicate/conflicting states and lab schema readiness. Incomplete or central-invalid records cannot silently progress: retain in exception/quarantine with owner. |
| Lifecycle | Locally accepted → centrally synchronized/verified → submitted to lab → acknowledged by lab. Rejected, conflict and acknowledgement-unavailable states remain visible—not reported as success. |

# Trusted time and tamper evidence

The managed edge—not the tablet clock—stamps event time in UTC at one-second resolution. Before departure and whenever service is available, the edge obtains a controlled time reference and records its time-confidence/drift state. During a WAN outage it continues from that controlled local basis; if confidence is degraded or a permitted drift bound is exceeded, it records the uncertainty, alerts the field workflow and requires controlled reconciliation. Upload time never replaces original event time.

Before reconnection, the edge appends each custody event to an append-only sequence linked to its predecessor and protected with edge-held signing/integrity material. Central synchronization verifies sequence continuity and integrity, retains the original history, and independently anchors the verified sequence/receipt. This makes later alteration or deletion detectable; it does not prove an observation was true, physical possession occurred as asserted, or an authorized actor did not misuse credentials.

# Synchronization, conflicts and evidence export

Each sample, event and synchronization envelope has a stable identifier. The edge retries safely after a timeout; central acknowledgement is keyed to those identifiers so retransmission converges on one logical sample and one custody sequence. Non-mergeable versions, sequence breaks, rejected updates and schema failures preserve both evidence and enter controlled conflict/quarantine resolution—never last-write-wins. Evidence export packages the custody history, integrity/anchor verification, sync receipts, time-confidence records, laboratory statuses and exception-resolution trail for inquiry without relying on a field device.

# Laboratory control and operational failure behavior

Central integration owns every Drakemoor connection. A durable central queue applies back-pressure so accepted field records remain controlled while the laboratory is slow or unavailable. Exactly two bounded workers may hold external sessions; a worker does not release capacity when it transmits a batch, only when the matching acknowledgement/status settles the batch. This topology prevents 12 crews from creating concurrent external API sessions.

| Condition | Required behavior / accountable owner |
| --- | --- |
| No WAN through full shift | Edge continues local acceptance, ledger and local status; browser remains non-persistent. Synchronization waits. Field lead follows custody procedure. |
| WAN returns / sync timeout | Retry idempotently; central verifies sequence and anchors it. Uncertain receipt stays “locally accepted” or “synchronized” until confirmed. Integration engineers monitor exceptions. |
| Delayed/unavailable lab acknowledgement | Batch remains queued/submitted; its worker session stays occupied until acknowledgement. Other work is buffered, never represented as accepted. Kamil coordinates interface response. |
| Lab schema/validation failure | Central retains payload and receipt evidence in quarantine; named integration engineer resolves with Kamil, then submits a controlled corrected/referenced update. |
| Integrity, time-confidence or conflict failure | Stop automatic progression; preserve original sequence and exception evidence. Maren directs evidence disposition; Malachy accepts/rejects readiness impact. |
| Lost BYOD or crew handover | Revoke browser session; actor reauthenticates on an available endpoint. No durable field record or master secret is recovered from the BYOD device. |

# Projected outcomes and explicit limits

Under the supplied coverage assumption, a crew can record a normal full disconnected shift at the managed edge, later obtaining verified central synchronization and then a distinct laboratory-acknowledged state. Under prolonged WAN loss, records remain locally accepted and inquiry evidence remains at the managed edge; central/lab status is delayed, not inferred. Under delayed lab acknowledgement, the central queue retains work and the two occupied sessions constrain dispatch; field capture continues independently. These are behavioral projections, not throughput or availability commitments.

Uncertainty to resolve during assurance: permitted managed-edge time-confidence/drift threshold, browser controls achievable on the actual BYOD variants, and Drakemoor’s exact response/error examples. These are validation inputs, not alternate target architectures or vendor commitments.

# Designs set aside — not part of the target

| Set-aside design | Why it is not carried forward |
| --- | --- |
| Cloud-only browser capture | Requires live WAN to record the field event; incompatible with 14 sites without dependable coverage, four intermittent sites, and full-shift disconnected operation. |
| Direct tablet-to-lab / per-crew connections | Cecilia’s simplification preference conflicts with a limit of two concurrent external API sessions for 12 crews. Sessions remain occupied until batch acknowledgement, so individual connections are neither licensed nor controllable. |
| Offline-first native tablet application with durable local store | Conflicts with the policy prohibition on identifiers, locations, observations and custody records at rest on end-user devices. A new native cross-platform build is also estimated beyond available delivery capacity before validation. |
| Treating BYOD as managed infrastructure | BYOD cannot join Wrenfell MDM and cannot inherit privileged trust, durable storage or custody authority. |
| Central receipt as the only custody evidence | A later receipt cannot explain disconnected possession or preserve event-time integrity during the outage. |

# Constraint-to-target trace

| Material source constraint | Target response / stated limitation |
| --- | --- |
| WAN loss; full shift | Managed edge holds encrypted records and ledger; endpoint browser does not. |
| No data at rest on end-user device | Persistence only in approved edge/central stores; cache/download/autofill/temp-path controls tested. |
| Mixed 20 managed / 28 BYOD fleet | All are browser endpoints; BYOD has unprivileged, short-lived access only. |
| Custody/inquiry and UTC seconds | Edge creates actor/action/sample/time evidence, chained before WAN; time confidence is recorded. |
| Two lab sessions, acknowledgement-held | Central durable queue and no-more-than-two workers; submitted is distinct from acknowledged. |
| 12 engineer-weeks; 8 review days; freeze | Configure existing browser form and approved edge, then integrate/test around freeze; no greenfield native build. |
| Limit of integrity claim | Detects sequence alteration/deletion; does not prove factual truth or prevent authorised credential misuse. |

# Delivery roadmap to mobilisation

The roadmap consumes no more than the available 12 integration engineer-weeks and eight security-architect review days. Dates below are planning dates derived from the fixed freeze and 3 February 2027 start; production change is not scheduled during the freeze.

| Dates | Milestone / dependency | Accountable owner | Capacity / exit evidence |
| --- | --- | --- | --- |
| 14–18 Dec | Assurance baseline and target specification; precedes configuration | Malachy; Maren | Security review days 1–2; target/control trace agreed |
| 21 Dec–5 Jan | Change freeze: no production change; prepare review material only | Malachy | No deployment; open decisions logged for post-freeze |
| 6–15 Jan | Configure browser form + approved managed edge; define IDs, ledger/time fields and local checks | Integration engineers | 4 engineer-weeks; configured build ready for integration |
| 11–20 Jan | Build central verification, idempotent sync, queue and two-session lifecycle; depends on field contract | Integration engineers; Kamil | 5 engineer-weeks; interface/status evidence |
| 18–22 Jan | Security/evidence review and remediate; depends on configured controls | Maren | Security review days 3–8; cache/storage, keys, time, ledger review |
| 25–27 Jan | Bounded field pilot/rehearsal; depends on integration and review | Chidi; Maren | 2 engineer-weeks support; pass evidence and field sign-off |
| 28–29 Jan | Readiness / go-no-go and controlled release; depends on pilot | Malachy; Cecilia | 1 engineer-week support; readiness before 3 Feb |
| 1–2 Feb | Crew briefing, operational handover and mobilisation check | Chidi; Malachy | No feature change; custody fallback confirmed |

# Pilot acceptance and fallback

| Prove in rehearsal | Observable pass evidence |
| --- | --- |
| Disconnected capture / no tablet persistence | Full-shift WAN simulation accepts records at edge; device inspection finds no sample/custody data in browser cache, downloads, autofill, app/temp paths or saved credentials. |
| Attribution, time and integrity | Actor/action/sample/UTC-second fields present; tablet clock change does not set authority; time-confidence degradation is visible; alteration/deletion breaks verification before reconnection. |
| Retry, conflict and lab boundary | Timeout retry creates no duplicate sample/event; non-mergeable update quarantines; concurrent dispatch never exceeds two acknowledgement-held sessions; delayed acknowledgement remains visible. |
| Go/no-go and fallback | Go only when all evidence passes and Malachy accepts. If not, do not release the target: use controlled existing custody procedure and retain paper/physical custody evidence for later controlled entry, preserving original dates/actors and exception record; no unverified electronic custody claim is substituted. |

# Assurance release statement

This decision deliberately uses available, approved components: configuration of the current browser field form and approved managed-edge image, plus bounded central integration. It does not assume a new product, a new vendor commitment, an extra laboratory connection, a universal device-management capability, or an unsupported performance figure. Readiness is conditional on the pilot evidence and the named reviews; the selected target does not conceal failure states behind upload or lab-submission timestamps.

# Architecture decision

For the Sheafield Mutual first-wave baseline of 12 crews across 18 sites, Wrenfell will implement the managed-edge, browser-only field-data architecture described here: the approved managed edge is the encrypted, access-logged disconnected system of record and creates controlled, tamper-evident custody evidence; tablets, including BYOD, remain non-persistent unprivileged endpoints; Wrenfell central integration verifies and anchors synchronization and queues laboratory traffic through no more than two acknowledgement-held Drakemoor API sessions. This is the single target architecture for mobilisation readiness before field sampling on 3 February 2027.