## Slide 1
HOLLOWPINE FIELD SERVICES
Target Site & Occupancy Recommendation
For Efua Sundqvist, Facilities Committee, and Legal Counsel | November decision
DECISION REQUEST
Approve conditional pursuit of Cedar Ridge Industrial Center - Building 4 as the single target site and phased occupancy configuration.
COMMERCIAL RECOMMENDATION
Cedar Ridge is the lowest projected 14-month option ($2.025M) and has documented 650 psf instrument-bay loading. Its exhaust retrofit creates the governing execution risk.
AUTHORITY BOUNDARY
Dagny Dunbar recommends commercial site, occupancy, cost, schedule, and contract gates. Callum Yamamoto retains biosafety and isotope-suite technical sign-off.
SOURCE FACT
ESTIMATE
PROJECTION / GATE
Recommendation is not approval: facilities committee action is requested; no biosafety or regulatory conclusion is made in this deck.
Source: candidate_site_evidence.xlsx | labels distinguish source facts, estimates, projections, and confirmations
CONFIDENTIAL

## Slide 2
OCCUPANCY MODEL
Recommended configuration: separate functions and permissions
2 / 8
General occupants | Cedar Ridge
Move to general-area fit-out only at the Month 6 projected milestone.
General occupancy access is distinct from laboratory access.
No general-user credential authorizes laboratory entry.
Commercial occupancy may begin before laboratory readiness; this is the phasing benefit.
Laboratory group | Cedar Ridge
Wet lab, analytical lab, prep, and instrument bay move only after the laboratory gates.
Controlled laboratory access for laboratory users.
Instrument bay: loading and vibration are separate acceptance tests.
Projected laboratory readiness is Month 11, subject to exhaust, access, and instrument acceptance.
Isotope suite | one lab room
A special controlled room inside the four-room laboratory program.
Further controlled isotope-suite permission, separate from general lab access.
Separate controls and occupancy confirmation; general lab fit-out is not proof of suitability.
Callum Yamamoto provides technical sign-off.
Modeled Month 12 gate, after laboratory readiness. Dagny does not authorize this occupancy.
Source: candidate_site_evidence.xlsx | labels distinguish source facts, estimates, projections, and confirmations
CONFIDENTIAL

## Slide 3
ALL CANDIDATES AGAINST SOURCE REQUIREMENTS
Comparison: Cedar Ridge has the strongest conditional fit
3 / 8
Candidate
14-mo cost
Schedule
Technical fit
Access / occupancy
Cedar Ridge RECOMMEND
$2.025M lowest
Month 13 projected 1 month float
650 psf documented vs 500 psf minimum. Vibration test required. Exhaust retrofit: 9 months after execution.
Can configure general / lab / isotope-suite permissions. Contract and commissioning gates required.
Harbor Point SET ASIDE
$2.197M
Turnkey / earliest readiness stated
550 psf documented, but landlord cannot demonstrate <=20 micrometers/sec RMS vibration.
No schedule advantage cures an un-demonstrated instrument-bay criterion.
Northline SET ASIDE
$2.120M
Duct extension: 2 months may run with fit-out
600 psf documented; vibration test would still be required.
Landlord will not commit in lease to separated badging: controlled lab population cannot be contractually protected.
Decision logic combines cost, schedule, technical fit, and access controls. A single favorable feature is not treated as an occupancy authorization.
Source: candidate_site_evidence.xlsx | labels distinguish source facts, estimates, projections, and confirmations
CONFIDENTIAL

## Slide 4
14-MONTH OCCUPANCY COST | LIKE-FOR-LIKE BASIS
Cost advantage is real; exhaust schedule risk remains the trade
4 / 8
Component
Cedar Ridge
Harbor Point
Northline
Evidence label
Base rent
$1,260,000
$1,712,000
$1,600,000
SOURCE FACT
Building preparation
$145,000
$90,000
$165,000
SOURCE FACT
Laboratory fit-out
$260,000
$310,000
$275,000
SOURCE FACT
Exhaust retrofit
$285,000
$0
$0
ESTIMATE
Relocation / commissioning
$75,000
$85,000
$80,000
ESTIMATE
Projected total
$2,025,000
$2,197,000
$2,120,000
CALCULATED
Cedar Ridge is $172,000 below Harbor Point and $95,000 below Northline on the stated 14-month basis. Its $285,000 exhaust allowance and $75,000 relocation/commissioning allowance are estimates, not fixed facts.
Scope basis: base rent + building preparation + general laboratory fit-out + exhaust retrofit + relocation/commissioning through the 14-month lease horizon. Isotope-suite suitability is not priced or presumed.
Source: candidate_site_evidence.xlsx | labels distinguish source facts, estimates, projections, and confirmations
CONFIDENTIAL

## Slide 5
14-MONTH LEASE HORIZON
Phased move fits only through parallel work and defined gates
5 / 8
1
2
3
4
5
6
7
8
9
10
11
12
13
14
Setup & access plan
Months 1-2
Exhaust retrofit
Months 3-11 | laboratory occupancy blocked
General fit-out
Months 3-6
Occupancy sequence
General
Lab gates
Isotope
Move complete
Float
Source model: sequential plan = 2 months setup + 9 months exhaust + 4 months fit-out + 1 isotope gate = 16 months, exceeding the 14-month lease horizon by 2 months. Parallel fit-out is an explicit assumption contingent on landlord interface release by Month 2.
Source: candidate_site_evidence.xlsx | labels distinguish source facts, estimates, projections, and confirmations
CONFIDENTIAL

## Slide 6
HARD GATES OUTWEIGH READINESS AND NOMINAL ALTERNATIVES
Why the alternatives are set aside
6 / 8
Cedar Ridge | acceptable only with gates
Principal downside: the required exhaust retrofit can consume the phased-move window.
Floor loading is documented: 650 psf against a 500 psf minimum.
Mitigation: parallel general fit-out, Month 2 interface-release commitment, and a bounded holdover contingency.
Vibration and exhaust evidence remain pre-occupancy gates.
Harbor Point | set aside
Turnkey readiness is not evidence of instrument-bay vibration compliance.
Landlord cannot demonstrate the <=20 micrometers/sec RMS criterion.
550 psf loading does not cure the separate vibration requirement.
Without evidence, laboratory occupancy would lack the required acceptance basis.
Northline | set aside
A non-committal landlord position cannot support controlled laboratory occupancy.
Landlord will not commit in the lease to separated badging.
This leaves general users and controlled laboratory users without a contractually protected separation.
A verbal assurance is not equivalent to a documented lease commitment.
Source: candidate_site_evidence.xlsx | labels distinguish source facts, estimates, projections, and confirmations
CONFIDENTIAL

## Slide 7
OWNERS, EVIDENCE, TIMING, CONSEQUENCE
Conditions before contracting and occupancy
7 / 8
Gate / evidence
Owner
When
Required confirmation
Consequence if unmet
Cedar Ridge lease commitments
Landlord + legal counsel
Before execution
Written exhaust scope, 9-month duration, and Month 2 interface release; documented access configuration.
Hold / do not execute Cedar Ridge lease; escalate to committee.
Instrument bay acceptance
Facilities + qualified verifier
Before lab occupancy
Confirm 650 psf location basis and measure vibration against <=20 micrometers/sec RMS.
No instrument-bay occupancy or equipment move.
Exhaust / laboratory readiness
Landlord + facilities
Before lab occupancy
Verify installed exhaust performance and completion of coordinated lab work.
Laboratory move remains blocked; use holdover contingency.
Isotope-suite control gate
Callum Yamamoto
Before isotope-suite occupancy
Separate controls, occupancy confirmation, and biosafety/isotope-suite technical sign-off.
Isotope suite remains unoccupied; general lab fit-out does not substitute.
Access commissioning
Facilities + landlord
Before each population moves
Separate general, laboratory, and isotope-suite permissions commissioned and documented.
Affected population does not move; access model is not assumed.
Source: candidate_site_evidence.xlsx | Owners shown are accountable parties for the confirmation, not delegated technical authorities
CONFIDENTIAL

## Slide 8
VOTE IN NOVEMBER
Decision requested from the facilities committee
8 / 8
VOTE REQUEST
Authorize conditional pursuit of Cedar Ridge Industrial Center - Building 4 as the one target site and the phased occupancy configuration.
Proceed gate
Before lease execution: legal documentation of exhaust scope, 9-month duration, Month 2 interface release, and separated access configuration.
Before laboratory occupancy: exhaust verification plus distinct instrument-bay loading and vibration acceptance.
Before isotope-suite occupancy: separate control confirmation and Callum Yamamoto sign-off.
Hold / fallback gate
If the Month 2 interface-release commitment is not documented, do not rely on the 13-month projection; the source sequential plan is 16 months.
Escalate to the committee and pursue a short negotiated holdover as the bounded continuity contingency.
Do not substitute turnkey readiness, general fit-out, or verbal assurances for the stated gates.
Dagny Dunbar’s recommendation supports the commercial decision only. The committee approves the site direction; Callum Yamamoto retains biosafety and isotope-suite technical authority.
Source: candidate_site_evidence.xlsx | labels distinguish source facts, estimates, projections, and confirmations
CONFIDENTIAL