## Decision Summary
Corrective-Action Retraining Calendar — Approval Summary
Prepared by Constance Ifeoma • For Rune Bergerson compliance sign-off
Recommendation: APPROVE — all 63 required clerical staff are assigned once to HIPAA and once to ADA-accommodation retraining before the 15 May corrective-action deadline.
Decision controls | Capacity convention: listed seats are TOTAL PARTICIPANT SEATS; the trainer is not counted against the listed seat count. Applied to every selected session.
Selected sessions | 26 | HIPAA sessions | 13 |  | ADA-accommodation sessions | 13
Required staff | 63 | Required completions | 126 |  | Unresolved exceptions | NONE
Selected source sessions | H-BR-01, A-BR-01, H-BR-02, A-BR-02, H-BR-03, A-BR-03, H-CA-01, A-CA-01, H-CA-02, A-CA-02, H-CA-03, A-CA-03, H-DU-01, A-DU-01, H-DU-02, A-DU-02, H-EL-01, A-EL-01, H-EL-02, A-EL-02, H-EL-03, A-EL-03, H-FA-01, A-FA-01, H-FA-02, A-FA-02
Operating margin | Weakest coverage margin: 0 staff. Maximum concurrent home-site release equals the permitted release at every tight cohort session (5 of 13 at 8-minimum sites; 6 of 12 at 6-minimum sites). Tightest seat margin: 0 seats in the six-attendee Dunlow and Faircross sessions.
Material alternatives rejected | H-CA-X1 and H-DU-X1 conflict with the recorded trainer route; A-EL-X1 and A-DU-X1 use Room B during recorded holds; H-BR-X1 and A-CA-X1 leave less than the 45-minute same-site changeover; A-FA-X1 follows documented late closings by less than eight hours. The selected paired slots preserve the strongest feasible release pattern while respecting the two-session daily ceiling.
Sign-off | Rune Bergerson, Compliance Approver |  |  | Approval: __________________ Date: __________

## Selected Calendar
Selected Four-Week Retraining Calendar
Selected source sessions only • HIPAA = blue • ADA-accommodation = green • attendee identifiers are shown in every calendar row
Date | Session ID | Module | Site | Room | Start | End | Trainer | Seats | Attendees | Home-site attendance | Capacity margin | Coverage margin | Status
2025-04-17 | H-BR-01 | HIPAA | Brookgate Clinic | Mobile Learning Suite A | 9:00 | 11:00 | Constance Ifeoma | 6 | AHA-C-001 — Tadeo Almeida AHA-C-002 — Mateo Quinn AHA-C-003 — Alba Santos AHA-C-004 — Frida Morrow AHA-C-005 — Sofia Farrow | Brookgate Clinic: 5 | 1 | 0 | SELECTED — READY
2025-04-17 | A-BR-01 | ADA-accommodation | Brookgate Clinic | Mobile Learning Suite A | 14:00 | 16:00 | Constance Ifeoma | 6 | AHA-C-001 — Tadeo Almeida AHA-C-002 — Mateo Quinn AHA-C-003 — Alba Santos AHA-C-004 — Frida Morrow AHA-C-005 — Sofia Farrow | Brookgate Clinic: 5 | 1 | 0 | SELECTED — READY
2025-04-18 | H-BR-02 | HIPAA | Brookgate Clinic | Mobile Learning Suite A | 9:00 | 11:00 | Constance Ifeoma | 6 | AHA-C-006 — Lena Shaw AHA-C-007 — Omar Guerrero AHA-C-008 — Priya Almeida AHA-C-009 — Jonas Quinn | Brookgate Clinic: 4 | 2 | 1 | SELECTED — READY
2025-04-18 | A-BR-02 | ADA-accommodation | Brookgate Clinic | Mobile Learning Suite A | 14:00 | 16:00 | Constance Ifeoma | 6 | AHA-C-006 — Lena Shaw AHA-C-007 — Omar Guerrero AHA-C-008 — Priya Almeida AHA-C-009 — Jonas Quinn | Brookgate Clinic: 4 | 2 | 1 | SELECTED — READY
2025-04-21 | H-BR-03 | HIPAA | Brookgate Clinic | Mobile Learning Suite A | 9:00 | 11:00 | Constance Ifeoma | 6 | AHA-C-010 — Mira Santos AHA-C-011 — Dario Morrow AHA-C-012 — Nia Farrow AHA-C-013 — Ravi Shaw | Brookgate Clinic: 4 | 2 | 1 | SELECTED — READY
2025-04-21 | A-BR-03 | ADA-accommodation | Brookgate Clinic | Mobile Learning Suite A | 14:00 | 16:00 | Constance Ifeoma | 6 | AHA-C-010 — Mira Santos AHA-C-011 — Dario Morrow AHA-C-012 — Nia Farrow AHA-C-013 — Ravi Shaw | Brookgate Clinic: 4 | 2 | 1 | SELECTED — READY
2025-04-22 | H-CA-01 | HIPAA | Casterbridge Clinic | Mobile Learning Suite A | 9:00 | 11:00 | Constance Ifeoma | 6 | AHA-C-014 — Elin Bhandari AHA-C-015 — Cora Voskresensky AHA-C-016 — Milan Solberg AHA-C-017 — Amara Kwan AHA-C-018 — Davin Patel | Casterbridge Clinic: 5 | 1 | 0 | SELECTED — READY
2025-04-22 | A-CA-01 | ADA-accommodation | Casterbridge Clinic | Mobile Learning Suite A | 14:00 | 16:00 | Constance Ifeoma | 6 | AHA-C-014 — Elin Bhandari AHA-C-015 — Cora Voskresensky AHA-C-016 — Milan Solberg AHA-C-017 — Amara Kwan AHA-C-018 — Davin Patel | Casterbridge Clinic: 5 | 1 | 0 | SELECTED — READY
2025-04-23 | H-CA-02 | HIPAA | Casterbridge Clinic | Mobile Learning Suite A | 9:00 | 11:00 | Constance Ifeoma | 6 | AHA-C-019 — Yara Kim AHA-C-020 — Noel Vale AHA-C-021 — Iris Bhandari AHA-C-022 — Tadeo Voskresensky | Casterbridge Clinic: 4 | 2 | 1 | SELECTED — READY
2025-04-23 | A-CA-02 | ADA-accommodation | Casterbridge Clinic | Mobile Learning Suite A | 14:00 | 16:00 | Constance Ifeoma | 6 | AHA-C-019 — Yara Kim AHA-C-020 — Noel Vale AHA-C-021 — Iris Bhandari AHA-C-022 — Tadeo Voskresensky | Casterbridge Clinic: 4 | 2 | 1 | SELECTED — READY
2025-04-24 | H-CA-03 | HIPAA | Casterbridge Clinic | Mobile Learning Suite A | 9:00 | 11:00 | Constance Ifeoma | 6 | AHA-C-023 — Mateo Solberg AHA-C-024 — Alba Kwan AHA-C-025 — Frida Patel AHA-C-026 — Sofia Kim | Casterbridge Clinic: 4 | 2 | 1 | SELECTED — READY
2025-04-24 | A-CA-03 | ADA-accommodation | Casterbridge Clinic | Mobile Learning Suite A | 14:00 | 16:00 | Constance Ifeoma | 6 | AHA-C-023 — Mateo Solberg AHA-C-024 — Alba Kwan AHA-C-025 — Frida Patel AHA-C-026 — Sofia Kim | Casterbridge Clinic: 4 | 2 | 1 | SELECTED — READY
2025-04-25 | H-DU-01 | HIPAA | Dunlow Clinic | Mobile Learning Suite A | 9:00 | 11:00 | Constance Ifeoma | 6 | AHA-C-027 — Lena Rowan AHA-C-028 — Omar Dalgaard AHA-C-029 — Priya Hart AHA-C-030 — Jonas Reed AHA-C-031 — Mira Ellis AHA-C-032 — Dario Byrne | Dunlow Clinic: 6 | 0 | 0 | SELECTED — READY
2025-04-25 | A-DU-01 | ADA-accommodation | Dunlow Clinic | Mobile Learning Suite A | 14:00 | 16:00 | Constance Ifeoma | 6 | AHA-C-027 — Lena Rowan AHA-C-028 — Omar Dalgaard AHA-C-029 — Priya Hart AHA-C-030 — Jonas Reed AHA-C-031 — Mira Ellis AHA-C-032 — Dario Byrne | Dunlow Clinic: 6 | 0 | 0 | SELECTED — READY
2025-04-28 | H-DU-02 | HIPAA | Dunlow Clinic | Mobile Learning Suite A | 9:00 | 11:00 | Constance Ifeoma | 6 | AHA-C-033 — Nia Alder AHA-C-034 — Ravi Rowan AHA-C-035 — Elin Dalgaard AHA-C-036 — Cora Hart AHA-C-037 — Milan Reed AHA-C-038 — Amara Ellis | Dunlow Clinic: 6 | 0 | 0 | SELECTED — READY
2025-04-28 | A-DU-02 | ADA-accommodation | Dunlow Clinic | Mobile Learning Suite A | 14:00 | 16:00 | Constance Ifeoma | 6 | AHA-C-033 — Nia Alder AHA-C-034 — Ravi Rowan AHA-C-035 — Elin Dalgaard AHA-C-036 — Cora Hart AHA-C-037 — Milan Reed AHA-C-038 — Amara Ellis | Dunlow Clinic: 6 | 0 | 0 | SELECTED — READY
2025-04-29 | H-EL-01 | HIPAA | Elmstead Clinic | Mobile Learning Suite A | 9:00 | 11:00 | Constance Ifeoma | 6 | AHA-C-039 — Davin Farrow AHA-C-040 — Yara Shaw AHA-C-041 — Noel Guerrero AHA-C-042 — Iris Almeida AHA-C-043 — Tadeo Quinn | Elmstead Clinic: 5 | 1 | 0 | SELECTED — READY
2025-04-29 | A-EL-01 | ADA-accommodation | Elmstead Clinic | Mobile Learning Suite A | 14:00 | 16:00 | Constance Ifeoma | 6 | AHA-C-039 — Davin Farrow AHA-C-040 — Yara Shaw AHA-C-041 — Noel Guerrero AHA-C-042 — Iris Almeida AHA-C-043 — Tadeo Quinn | Elmstead Clinic: 5 | 1 | 0 | SELECTED — READY
2025-04-30 | H-EL-02 | HIPAA | Elmstead Clinic | Mobile Learning Suite A | 9:00 | 11:00 | Constance Ifeoma | 6 | AHA-C-044 — Mateo Santos AHA-C-045 — Alba Morrow AHA-C-046 — Frida Farrow AHA-C-047 — Sofia Shaw | Elmstead Clinic: 4 | 2 | 1 | SELECTED — READY
2025-04-30 | A-EL-02 | ADA-accommodation | Elmstead Clinic | Mobile Learning Suite A | 14:00 | 16:00 | Constance Ifeoma | 6 | AHA-C-044 — Mateo Santos AHA-C-045 — Alba Morrow AHA-C-046 — Frida Farrow AHA-C-047 — Sofia Shaw | Elmstead Clinic: 4 | 2 | 1 | SELECTED — READY
2025-05-01 | H-EL-03 | HIPAA | Elmstead Clinic | Mobile Learning Suite A | 9:00 | 11:00 | Constance Ifeoma | 6 | AHA-C-048 — Lena Guerrero AHA-C-049 — Omar Almeida AHA-C-050 — Priya Quinn AHA-C-051 — Jonas Santos | Elmstead Clinic: 4 | 2 | 1 | SELECTED — READY
2025-05-01 | A-EL-03 | ADA-accommodation | Elmstead Clinic | Mobile Learning Suite A | 14:00 | 16:00 | Constance Ifeoma | 6 | AHA-C-048 — Lena Guerrero AHA-C-049 — Omar Almeida AHA-C-050 — Priya Quinn AHA-C-051 — Jonas Santos | Elmstead Clinic: 4 | 2 | 1 | SELECTED — READY
2025-05-02 | H-FA-01 | HIPAA | Faircross Clinic | Mobile Learning Suite A | 9:00 | 11:00 | Constance Ifeoma | 6 | AHA-C-052 — Mira Patel AHA-C-053 — Dario Kim AHA-C-054 — Nia Vale AHA-C-055 — Ravi Bhandari AHA-C-056 — Elin Voskresensky AHA-C-057 — Cora Solberg | Faircross Clinic: 6 | 0 | 0 | SELECTED — READY
2025-05-02 | A-FA-01 | ADA-accommodation | Faircross Clinic | Mobile Learning Suite A | 14:00 | 16:00 | Constance Ifeoma | 6 | AHA-C-052 — Mira Patel AHA-C-053 — Dario Kim AHA-C-054 — Nia Vale AHA-C-055 — Ravi Bhandari AHA-C-056 — Elin Voskresensky AHA-C-057 — Cora Solberg | Faircross Clinic: 6 | 0 | 0 | SELECTED — READY
2025-05-05 | H-FA-02 | HIPAA | Faircross Clinic | Mobile Learning Suite A | 9:00 | 11:00 | Constance Ifeoma | 6 | AHA-C-058 — Milan Kwan AHA-C-059 — Amara Patel AHA-C-060 — Davin Kim AHA-C-061 — Yara Vale AHA-C-062 — Noel Bhandari AHA-C-063 — Iris Voskresensky | Faircross Clinic: 6 | 0 | 0 | SELECTED — READY
2025-05-05 | A-FA-02 | ADA-accommodation | Faircross Clinic | Mobile Learning Suite A | 14:00 | 16:00 | Constance Ifeoma | 6 | AHA-C-058 — Milan Kwan AHA-C-059 — Amara Patel AHA-C-060 — Davin Kim AHA-C-061 — Yara Vale AHA-C-062 — Noel Bhandari AHA-C-063 — Iris Voskresensky | Faircross Clinic: 6 | 0 | 0 | SELECTED — READY

## Staff Completion
Staff-Level Completion View
All required staff • filter by site, assignment date, or module status
Staff identifier | Staff name | Site | HIPAA status | HIPAA session | HIPAA date | ADA-accommodation status | ADA session | ADA date | Overall release status
AHA-C-001 | Tadeo Almeida | Brookgate Clinic | ASSIGNED — required | H-BR-01 | 2025-04-17 | ASSIGNED — required | A-BR-01 | 2025-04-17 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-002 | Mateo Quinn | Brookgate Clinic | ASSIGNED — required | H-BR-01 | 2025-04-17 | ASSIGNED — required | A-BR-01 | 2025-04-17 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-003 | Alba Santos | Brookgate Clinic | ASSIGNED — required | H-BR-01 | 2025-04-17 | ASSIGNED — required | A-BR-01 | 2025-04-17 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-004 | Frida Morrow | Brookgate Clinic | ASSIGNED — required | H-BR-01 | 2025-04-17 | ASSIGNED — required | A-BR-01 | 2025-04-17 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-005 | Sofia Farrow | Brookgate Clinic | ASSIGNED — required | H-BR-01 | 2025-04-17 | ASSIGNED — required | A-BR-01 | 2025-04-17 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-006 | Lena Shaw | Brookgate Clinic | ASSIGNED — required | H-BR-02 | 2025-04-18 | ASSIGNED — required | A-BR-02 | 2025-04-18 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-007 | Omar Guerrero | Brookgate Clinic | ASSIGNED — required | H-BR-02 | 2025-04-18 | ASSIGNED — required | A-BR-02 | 2025-04-18 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-008 | Priya Almeida | Brookgate Clinic | ASSIGNED — required | H-BR-02 | 2025-04-18 | ASSIGNED — required | A-BR-02 | 2025-04-18 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-009 | Jonas Quinn | Brookgate Clinic | ASSIGNED — required | H-BR-02 | 2025-04-18 | ASSIGNED — required | A-BR-02 | 2025-04-18 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-010 | Mira Santos | Brookgate Clinic | ASSIGNED — required | H-BR-03 | 2025-04-21 | ASSIGNED — required | A-BR-03 | 2025-04-21 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-011 | Dario Morrow | Brookgate Clinic | ASSIGNED — required | H-BR-03 | 2025-04-21 | ASSIGNED — required | A-BR-03 | 2025-04-21 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-012 | Nia Farrow | Brookgate Clinic | ASSIGNED — required | H-BR-03 | 2025-04-21 | ASSIGNED — required | A-BR-03 | 2025-04-21 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-013 | Ravi Shaw | Brookgate Clinic | ASSIGNED — required | H-BR-03 | 2025-04-21 | ASSIGNED — required | A-BR-03 | 2025-04-21 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-014 | Elin Bhandari | Casterbridge Clinic | ASSIGNED — required | H-CA-01 | 2025-04-22 | ASSIGNED — required | A-CA-01 | 2025-04-22 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-015 | Cora Voskresensky | Casterbridge Clinic | ASSIGNED — required | H-CA-01 | 2025-04-22 | ASSIGNED — required | A-CA-01 | 2025-04-22 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-016 | Milan Solberg | Casterbridge Clinic | ASSIGNED — required | H-CA-01 | 2025-04-22 | ASSIGNED — required | A-CA-01 | 2025-04-22 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-017 | Amara Kwan | Casterbridge Clinic | ASSIGNED — required | H-CA-01 | 2025-04-22 | ASSIGNED — required | A-CA-01 | 2025-04-22 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-018 | Davin Patel | Casterbridge Clinic | ASSIGNED — required | H-CA-01 | 2025-04-22 | ASSIGNED — required | A-CA-01 | 2025-04-22 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-019 | Yara Kim | Casterbridge Clinic | ASSIGNED — required | H-CA-02 | 2025-04-23 | ASSIGNED — required | A-CA-02 | 2025-04-23 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-020 | Noel Vale | Casterbridge Clinic | ASSIGNED — required | H-CA-02 | 2025-04-23 | ASSIGNED — required | A-CA-02 | 2025-04-23 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-021 | Iris Bhandari | Casterbridge Clinic | ASSIGNED — required | H-CA-02 | 2025-04-23 | ASSIGNED — required | A-CA-02 | 2025-04-23 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-022 | Tadeo Voskresensky | Casterbridge Clinic | ASSIGNED — required | H-CA-02 | 2025-04-23 | ASSIGNED — required | A-CA-02 | 2025-04-23 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-023 | Mateo Solberg | Casterbridge Clinic | ASSIGNED — required | H-CA-03 | 2025-04-24 | ASSIGNED — required | A-CA-03 | 2025-04-24 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-024 | Alba Kwan | Casterbridge Clinic | ASSIGNED — required | H-CA-03 | 2025-04-24 | ASSIGNED — required | A-CA-03 | 2025-04-24 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-025 | Frida Patel | Casterbridge Clinic | ASSIGNED — required | H-CA-03 | 2025-04-24 | ASSIGNED — required | A-CA-03 | 2025-04-24 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-026 | Sofia Kim | Casterbridge Clinic | ASSIGNED — required | H-CA-03 | 2025-04-24 | ASSIGNED — required | A-CA-03 | 2025-04-24 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-027 | Lena Rowan | Dunlow Clinic | ASSIGNED — required | H-DU-01 | 2025-04-25 | ASSIGNED — required | A-DU-01 | 2025-04-25 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-028 | Omar Dalgaard | Dunlow Clinic | ASSIGNED — required | H-DU-01 | 2025-04-25 | ASSIGNED — required | A-DU-01 | 2025-04-25 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-029 | Priya Hart | Dunlow Clinic | ASSIGNED — required | H-DU-01 | 2025-04-25 | ASSIGNED — required | A-DU-01 | 2025-04-25 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-030 | Jonas Reed | Dunlow Clinic | ASSIGNED — required | H-DU-01 | 2025-04-25 | ASSIGNED — required | A-DU-01 | 2025-04-25 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-031 | Mira Ellis | Dunlow Clinic | ASSIGNED — required | H-DU-01 | 2025-04-25 | ASSIGNED — required | A-DU-01 | 2025-04-25 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-032 | Dario Byrne | Dunlow Clinic | ASSIGNED — required | H-DU-01 | 2025-04-25 | ASSIGNED — required | A-DU-01 | 2025-04-25 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-033 | Nia Alder | Dunlow Clinic | ASSIGNED — required | H-DU-02 | 2025-04-28 | ASSIGNED — required | A-DU-02 | 2025-04-28 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-034 | Ravi Rowan | Dunlow Clinic | ASSIGNED — required | H-DU-02 | 2025-04-28 | ASSIGNED — required | A-DU-02 | 2025-04-28 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-035 | Elin Dalgaard | Dunlow Clinic | ASSIGNED — required | H-DU-02 | 2025-04-28 | ASSIGNED — required | A-DU-02 | 2025-04-28 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-036 | Cora Hart | Dunlow Clinic | ASSIGNED — required | H-DU-02 | 2025-04-28 | ASSIGNED — required | A-DU-02 | 2025-04-28 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-037 | Milan Reed | Dunlow Clinic | ASSIGNED — required | H-DU-02 | 2025-04-28 | ASSIGNED — required | A-DU-02 | 2025-04-28 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-038 | Amara Ellis | Dunlow Clinic | ASSIGNED — required | H-DU-02 | 2025-04-28 | ASSIGNED — required | A-DU-02 | 2025-04-28 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-039 | Davin Farrow | Elmstead Clinic | ASSIGNED — required | H-EL-01 | 2025-04-29 | ASSIGNED — required | A-EL-01 | 2025-04-29 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-040 | Yara Shaw | Elmstead Clinic | ASSIGNED — required | H-EL-01 | 2025-04-29 | ASSIGNED — required | A-EL-01 | 2025-04-29 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-041 | Noel Guerrero | Elmstead Clinic | ASSIGNED — required | H-EL-01 | 2025-04-29 | ASSIGNED — required | A-EL-01 | 2025-04-29 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-042 | Iris Almeida | Elmstead Clinic | ASSIGNED — required | H-EL-01 | 2025-04-29 | ASSIGNED — required | A-EL-01 | 2025-04-29 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-043 | Tadeo Quinn | Elmstead Clinic | ASSIGNED — required | H-EL-01 | 2025-04-29 | ASSIGNED — required | A-EL-01 | 2025-04-29 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-044 | Mateo Santos | Elmstead Clinic | ASSIGNED — required | H-EL-02 | 2025-04-30 | ASSIGNED — required | A-EL-02 | 2025-04-30 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-045 | Alba Morrow | Elmstead Clinic | ASSIGNED — required | H-EL-02 | 2025-04-30 | ASSIGNED — required | A-EL-02 | 2025-04-30 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-046 | Frida Farrow | Elmstead Clinic | ASSIGNED — required | H-EL-02 | 2025-04-30 | ASSIGNED — required | A-EL-02 | 2025-04-30 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-047 | Sofia Shaw | Elmstead Clinic | ASSIGNED — required | H-EL-02 | 2025-04-30 | ASSIGNED — required | A-EL-02 | 2025-04-30 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-048 | Lena Guerrero | Elmstead Clinic | ASSIGNED — required | H-EL-03 | 2025-05-01 | ASSIGNED — required | A-EL-03 | 2025-05-01 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-049 | Omar Almeida | Elmstead Clinic | ASSIGNED — required | H-EL-03 | 2025-05-01 | ASSIGNED — required | A-EL-03 | 2025-05-01 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-050 | Priya Quinn | Elmstead Clinic | ASSIGNED — required | H-EL-03 | 2025-05-01 | ASSIGNED — required | A-EL-03 | 2025-05-01 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-051 | Jonas Santos | Elmstead Clinic | ASSIGNED — required | H-EL-03 | 2025-05-01 | ASSIGNED — required | A-EL-03 | 2025-05-01 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-052 | Mira Patel | Faircross Clinic | ASSIGNED — required | H-FA-01 | 2025-05-02 | ASSIGNED — required | A-FA-01 | 2025-05-02 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-053 | Dario Kim | Faircross Clinic | ASSIGNED — required | H-FA-01 | 2025-05-02 | ASSIGNED — required | A-FA-01 | 2025-05-02 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-054 | Nia Vale | Faircross Clinic | ASSIGNED — required | H-FA-01 | 2025-05-02 | ASSIGNED — required | A-FA-01 | 2025-05-02 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-055 | Ravi Bhandari | Faircross Clinic | ASSIGNED — required | H-FA-01 | 2025-05-02 | ASSIGNED — required | A-FA-01 | 2025-05-02 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-056 | Elin Voskresensky | Faircross Clinic | ASSIGNED — required | H-FA-01 | 2025-05-02 | ASSIGNED — required | A-FA-01 | 2025-05-02 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-057 | Cora Solberg | Faircross Clinic | ASSIGNED — required | H-FA-01 | 2025-05-02 | ASSIGNED — required | A-FA-01 | 2025-05-02 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-058 | Milan Kwan | Faircross Clinic | ASSIGNED — required | H-FA-02 | 2025-05-05 | ASSIGNED — required | A-FA-02 | 2025-05-05 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-059 | Amara Patel | Faircross Clinic | ASSIGNED — required | H-FA-02 | 2025-05-05 | ASSIGNED — required | A-FA-02 | 2025-05-05 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-060 | Davin Kim | Faircross Clinic | ASSIGNED — required | H-FA-02 | 2025-05-05 | ASSIGNED — required | A-FA-02 | 2025-05-05 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-061 | Yara Vale | Faircross Clinic | ASSIGNED — required | H-FA-02 | 2025-05-05 | ASSIGNED — required | A-FA-02 | 2025-05-05 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-062 | Noel Bhandari | Faircross Clinic | ASSIGNED — required | H-FA-02 | 2025-05-05 | ASSIGNED — required | A-FA-02 | 2025-05-05 | COMPLETE WHEN BOTH SESSIONS ATTENDED
AHA-C-063 | Iris Voskresensky | Faircross Clinic | ASSIGNED — required | H-FA-02 | 2025-05-05 | ASSIGNED — required | A-FA-02 | 2025-05-05 | COMPLETE WHEN BOTH SESSIONS ATTENDED