## Option calculations
Cranemoor recovery decision — calculation-backed plan
Source revision | 31 July 2026 | Recommended option | Silver tier
Option | Fixed monthly (£) | Packs | TB/pack | Capacity TB | Rate (£/TB-month) | Capacity monthly (£) | Monthly recurring (£) | Annual recurring (£) | Setup (£) | First-year (£) | Model exposure (min) | Doc exposure (min) | Authority result
Current baseline | 120 | 4 | 7.3 | 29.2 | 9.5 | 277.4 | 397.4 | 4768.8 | 0 | 4768.8 | 240 | 60 | Fail
Copper tier | 180 | 5 | 7.3 | 36.5 | 10 | 365 | 545 | 6540 | 850 | 7390 | 120 | 30 | Fail
Silver tier | 240 | 6 | 7.3 | 43.8 | 11 | 481.8 | 721.8 | 8661.6 | 1400 | 10061.6 | 60 | 15 | Pass
Gold tier | 320 | 7 | 7.3 | 51.1 | 13 | 664.3 | 984.3 | 11811.6 | 2200 | 14011.6 | 15 | 5 | Pass
Funding basis | Current baseline annual recurring (£) | 4768.8
Recommended annual recurring (£) |  | 8661.6
Recurring annual uplift (£) |  | 3892.8
Current baseline first-year (£) |  | 4768.8
Recommended first-year (£) |  | 10061.6
First-year uplift (£) |  | 5292.8

## Implementation roadmap
Silver tier implementation roadmap
Operational deadline | 2026-11-30 | Start convention | First working day after approval (21 Sep 2026)
ID | Priority | Activity | Owner | Duration (working days) | Predecessors | Planned start | Planned finish | Acceptance evidence | Next step
1 | P1 | Confirm member approval and issue purchase order | Thandiwe Kalinowski | 3 | — | 2026-09-21 | 2026-09-23 | Signed AGM minute and supplier order | Complete and attach evidence
2 | P1 | Provision protected storage capacity | Tamsin Yablonski | 5 | 1 | 2026-09-24 | 2026-09-30 | Capacity dashboard shows 43.8 TB allocated | Complete and attach evidence
3 | P1 | Configure model-server hourly protection | Tamsin Yablonski | 4 | 2 | 2026-10-01 | 2026-10-06 | Restore point list includes hourly completed jobs | Complete and attach evidence
4 | P1 | Configure document-store 15-minute versioning | Ragnhild Jelinek | 3 | 2 | 2026-10-01 | 2026-10-05 | Version history demonstrates 15-minute checkpoints | Complete and attach evidence
5 | P1 | Protect render inputs and publish rerun procedure | Ragnhild Jelinek | 3 | 2 | 2026-10-01 | 2026-10-05 | Input manifest plus signed rerun runbook | Complete and attach evidence
6 | P1 | Run restore and recovery evidence test | Thandiwe Kalinowski | 4 | 3,4,5 | 2026-10-07 | 2026-10-12 | Successful restore log and timed evidence pack | Complete and attach evidence
7 | P2 | Operational handover and member notice | Thandiwe Kalinowski | 2 | 6 | 2026-10-13 | 2026-10-14 | Handover checklist and notice issued | Complete and attach evidence
8 | P1 | Final acceptance before operational deadline | Thandiwe Kalinowski | 1 | 7 | 2026-10-15 | 2026-10-15 | Acceptance sign-off dated no later than 30 Nov 2026 | Complete and attach evidence
Assumptions / method | Keys are trimmed and compared case-insensitively. Capacity cost = packs × 7.3 TB × rate. Recurring uplift compares annual recurring costs; first-year includes setup. Render outputs are rerun, not treated as lost drawing edits. The historical draft error cell is excluded.
Compliance basis | Model server ≤60 min; document store ≤15 min; render farm protected inputs with rerun treatment. Requirements effective 31 July 2026.
Worked example | Interruption 15 Sep 2026 15:37; Silver latest model point 15:00 (37 min exposure); latest document checkpoint 15:30 (7 min); R-185 rerun, source inputs recoverable.