## Preferred
PREFERRED SCENARIO — FERNDYKE LOCALISATION PASS SCHEDULE
Base music clearance: 26 Nov 2027 13:00 GMT ¦ Platform freeze: 30 Nov 2027 18:00 GMT
Forecast: all 11 episodes ingested by 26 Nov 2027 13:30; remaining margin 6030 minutes.
Chronology is controlled by the alternating Mireya Santos language rota, single QC Bay 1, dated availability and release gates.
Seq | Episode ID | Episode title | Runtime (min) | Language | Activity | Responsible owner / resource | Planned start | Planned finish | Booked min | Handoff / release dependency | Forecast ingest finish
1 | FDK-201 | Salt Road Witnesses | 24.2 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-08 09:00 | 2027-11-08 09:35 | 35 | Source handoff / language review | 2027-11-09 10:45
2 | FDK-201 | Salt Road Witnesses | 24.2 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-08 09:35 | 2027-11-08 10:15 | 40 | Caption lock complete — same episode / language | 2027-11-09 10:45
3 | FDK-202 | The Quiet Hoist | 26.6 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-08 10:15 | 2027-11-08 10:50 | 35 | Source handoff / language review | 2027-11-09 12:10
4 | FDK-202 | The Quiet Hoist | 26.6 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-08 10:50 | 2027-11-08 11:35 | 45 | Caption lock complete — same episode / language | 2027-11-09 12:10
5 | FDK-201 | Salt Road Witnesses | 24.2 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-09 09:00 | 2027-11-09 09:35 | 35 | Source handoff / language review | 2027-11-09 10:45
6 | FDK-201 | Salt Road Witnesses | 24.2 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-09 09:35 | 2027-11-09 10:15 | 40 | Caption lock complete — same episode / language | 2027-11-09 10:45
7 | FDK-201 | Salt Road Witnesses | 24.2 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-09 10:15 | 2027-11-09 10:30 | 15 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-09 10:45
8 | FDK-202 | The Quiet Hoist | 26.6 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-09 10:15 | 2027-11-09 10:50 | 35 | Source handoff / language review | 2027-11-09 12:10
9 | FDK-201 | Salt Road Witnesses | 24.2 | All required | Ingest | Quillhaven Platform Relay | 2027-11-09 10:30 | 2027-11-09 10:45 | 15 | QC complete / release package complete | 2027-11-09 10:45
10 | FDK-202 | The Quiet Hoist | 26.6 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-09 10:50 | 2027-11-09 11:35 | 45 | Caption lock complete — same episode / language | 2027-11-09 12:10
11 | FDK-202 | The Quiet Hoist | 26.6 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-09 11:35 | 2027-11-09 11:55 | 20 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-09 12:10
12 | FDK-202 | The Quiet Hoist | 26.6 | All required | Ingest | Quillhaven Platform Relay | 2027-11-09 11:55 | 2027-11-09 12:10 | 15 | QC complete / release package complete | 2027-11-09 12:10
13 | FDK-203 | Milepost at Dawn | 27.4 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-10 09:00 | 2027-11-10 09:35 | 35 | Source handoff / language review | 2027-11-11 10:55
14 | FDK-203 | Milepost at Dawn | 27.4 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-10 09:35 | 2027-11-10 10:20 | 45 | Caption lock complete — same episode / language | 2027-11-11 10:55
15 | FDK-204 | Borrowed Water | 23.8 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-10 10:20 | 2027-11-10 10:55 | 35 | Source handoff / language review | 2027-11-26 13:15
16 | FDK-204 | Borrowed Water | 23.8 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-10 10:55 | 2027-11-10 11:35 | 40 | Caption lock complete — same episode / language | 2027-11-26 13:15
17 | FDK-203 | Milepost at Dawn | 27.4 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-11 09:00 | 2027-11-11 09:35 | 35 | Source handoff / language review | 2027-11-11 10:55
18 | FDK-203 | Milepost at Dawn | 27.4 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-11 09:35 | 2027-11-11 10:20 | 45 | Caption lock complete — same episode / language | 2027-11-11 10:55
19 | FDK-203 | Milepost at Dawn | 27.4 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-11 10:20 | 2027-11-11 10:40 | 20 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-11 10:55
20 | FDK-204 | Borrowed Water | 23.8 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-11 10:20 | 2027-11-11 10:55 | 35 | Source handoff / language review | 2027-11-26 13:15
21 | FDK-203 | Milepost at Dawn | 27.4 | All required | Ingest | Quillhaven Platform Relay | 2027-11-11 10:40 | 2027-11-11 10:55 | 15 | QC complete / release package complete | 2027-11-11 10:55
22 | FDK-204 | Borrowed Water | 23.8 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-11 10:55 | 2027-11-11 11:35 | 40 | Caption lock complete — same episode / language | 2027-11-26 13:15
23 | FDK-204 | Borrowed Water | 23.8 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-11 11:35 | 2027-11-11 11:50 | 15 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-26 13:15
24 | FDK-205 | Tin Roof Arithmetic | 25.5 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-12 13:17 | 2027-11-12 13:52 | 35 | Source handoff / language review | 2027-11-16 10:55
25 | FDK-205 | Tin Roof Arithmetic | 25.5 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-12 13:52 | 2027-11-12 14:37 | 45 | Caption lock complete — same episode / language | 2027-11-16 10:55
26 | FDK-206 | Northbound Ledger | 28.2 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-12 14:37 | 2027-11-12 15:17 | 40 | Source handoff / language review | 2027-11-16 12:25
27 | FDK-206 | Northbound Ledger | 28.2 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-12 15:17 | 2027-11-12 16:07 | 50 | Caption lock complete — same episode / language | 2027-11-16 12:25
28 | FDK-207 | The Glass Orchard | 24.7 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-12 16:07 | 2027-11-12 16:42 | 35 | Source handoff / language review | 2027-11-18 10:50
29 | FDK-207 | The Glass Orchard | 24.7 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-15 09:00 | 2027-11-15 09:45 | 45 | Caption lock complete — same episode / language | 2027-11-18 10:50
30 | FDK-208 | Lower Signal | 29.1 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-15 09:45 | 2027-11-15 10:25 | 40 | Source handoff / language review | 2027-11-18 12:25
31 | FDK-208 | Lower Signal | 29.1 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-15 10:25 | 2027-11-15 11:15 | 50 | Caption lock complete — same episode / language | 2027-11-18 12:25
32 | FDK-209 | The Amber Division | 26.3 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-15 11:15 | 2027-11-15 11:50 | 35 | Source handoff / language review | 2027-11-26 13:30
33 | FDK-205 | Tin Roof Arithmetic | 25.5 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-16 09:00 | 2027-11-16 09:35 | 35 | Source handoff / language review | 2027-11-16 10:55
34 | FDK-205 | Tin Roof Arithmetic | 25.5 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-16 09:35 | 2027-11-16 10:20 | 45 | Caption lock complete — same episode / language | 2027-11-16 10:55
35 | FDK-205 | Tin Roof Arithmetic | 25.5 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-16 10:20 | 2027-11-16 10:40 | 20 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-16 10:55
36 | FDK-206 | Northbound Ledger | 28.2 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-16 10:20 | 2027-11-16 11:00 | 40 | Source handoff / language review | 2027-11-16 12:25
37 | FDK-205 | Tin Roof Arithmetic | 25.5 | All required | Ingest | Quillhaven Platform Relay | 2027-11-16 10:40 | 2027-11-16 10:55 | 15 | QC complete / release package complete | 2027-11-16 10:55
38 | FDK-206 | Northbound Ledger | 28.2 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-16 11:00 | 2027-11-16 11:50 | 50 | Caption lock complete — same episode / language | 2027-11-16 12:25
39 | FDK-206 | Northbound Ledger | 28.2 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-16 11:50 | 2027-11-16 12:10 | 20 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-16 12:25
40 | FDK-206 | Northbound Ledger | 28.2 | All required | Ingest | Quillhaven Platform Relay | 2027-11-16 12:10 | 2027-11-16 12:25 | 15 | QC complete / release package complete | 2027-11-16 12:25
41 | FDK-209 | The Amber Division | 26.3 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-17 09:00 | 2027-11-17 09:45 | 45 | Caption lock complete — same episode / language | 2027-11-26 13:30
42 | FDK-210 | Flood Mark | 25.8 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-17 09:45 | 2027-11-17 10:20 | 35 | Source handoff / language review | 2027-11-24 08:15
43 | FDK-210 | Flood Mark | 25.8 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-17 10:20 | 2027-11-17 11:05 | 45 | Caption lock complete — same episode / language | 2027-11-24 08:15
44 | FDK-211 | Hearth Country | 27.1 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-17 11:05 | 2027-11-17 11:40 | 35 | Source handoff / language review | 2027-11-25 10:55
45 | FDK-207 | The Glass Orchard | 24.7 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-18 09:00 | 2027-11-18 09:35 | 35 | Source handoff / language review | 2027-11-18 10:50
46 | FDK-207 | The Glass Orchard | 24.7 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-18 09:35 | 2027-11-18 10:20 | 45 | Caption lock complete — same episode / language | 2027-11-18 10:50
47 | FDK-207 | The Glass Orchard | 24.7 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-18 10:20 | 2027-11-18 10:35 | 15 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-18 10:50
48 | FDK-208 | Lower Signal | 29.1 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-18 10:20 | 2027-11-18 11:00 | 40 | Source handoff / language review | 2027-11-18 12:25
49 | FDK-207 | The Glass Orchard | 24.7 | All required | Ingest | Quillhaven Platform Relay | 2027-11-18 10:35 | 2027-11-18 10:50 | 15 | QC complete / release package complete | 2027-11-18 10:50
50 | FDK-208 | Lower Signal | 29.1 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-18 11:00 | 2027-11-18 11:50 | 50 | Caption lock complete — same episode / language | 2027-11-18 12:25
51 | FDK-208 | Lower Signal | 29.1 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-18 11:50 | 2027-11-18 12:10 | 20 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-18 12:25
52 | FDK-208 | Lower Signal | 29.1 | All required | Ingest | Quillhaven Platform Relay | 2027-11-18 12:10 | 2027-11-18 12:25 | 15 | QC complete / release package complete | 2027-11-18 12:25
53 | FDK-211 | Hearth Country | 27.1 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-19 09:00 | 2027-11-19 09:45 | 45 | Caption lock complete — same episode / language | 2027-11-25 10:55
54 | FDK-209 | The Amber Division | 26.3 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-23 09:00 | 2027-11-23 09:35 | 35 | Source handoff / language review | 2027-11-26 13:30
55 | FDK-209 | The Amber Division | 26.3 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-23 09:35 | 2027-11-23 10:20 | 45 | Caption lock complete — same episode / language | 2027-11-26 13:30
56 | FDK-209 | The Amber Division | 26.3 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-23 10:20 | 2027-11-23 10:40 | 20 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-26 13:30
57 | FDK-210 | Flood Mark | 25.8 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-23 10:20 | 2027-11-23 10:55 | 35 | Source handoff / language review | 2027-11-24 08:15
58 | FDK-210 | Flood Mark | 25.8 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-23 10:55 | 2027-11-23 11:40 | 45 | Caption lock complete — same episode / language | 2027-11-24 08:15
59 | FDK-210 | Flood Mark | 25.8 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-23 11:40 | 2027-11-23 12:00 | 20 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-24 08:15
60 | FDK-210 | Flood Mark | 25.8 | All required | Ingest | Quillhaven Platform Relay | 2027-11-24 08:00 | 2027-11-24 08:15 | 15 | QC complete / release package complete | 2027-11-24 08:15
61 | FDK-211 | Hearth Country | 27.1 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-25 09:00 | 2027-11-25 09:35 | 35 | Source handoff / language review | 2027-11-25 10:55
62 | FDK-211 | Hearth Country | 27.1 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-25 09:35 | 2027-11-25 10:20 | 45 | Caption lock complete — same episode / language | 2027-11-25 10:55
63 | FDK-211 | Hearth Country | 27.1 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-25 10:20 | 2027-11-25 10:40 | 20 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-25 10:55
64 | FDK-211 | Hearth Country | 27.1 | All required | Ingest | Quillhaven Platform Relay | 2027-11-25 10:40 | 2027-11-25 10:55 | 15 | QC complete / release package complete | 2027-11-25 10:55
65 | FDK-204 | Borrowed Water | 23.8 | All required | Ingest | Quillhaven Platform Relay | 2027-11-26 13:00 | 2027-11-26 13:15 | 15 | QC complete + music cue clearance | 2027-11-26 13:15
66 | FDK-209 | The Amber Division | 26.3 | All required | Ingest | Quillhaven Platform Relay | 2027-11-26 13:15 | 2027-11-26 13:30 | 15 | QC complete + music cue clearance | 2027-11-26 13:30
DAILY QC LOAD / AVAILABLE CAPACITY
QC Date | Scheduled QC load (min) | Available QC capacity (min) | Utilisation | Headroom (min)
2027-11-08 | 0 | 480 | 0% | 480
2027-11-09 | 35 | 480 | 7.292% | 445
2027-11-10 | 0 | 480 | 0% | 480
2027-11-11 | 35 | 480 | 7.292% | 445
2027-11-12 | 0 | 480 | 0% | 480
2027-11-15 | 0 | 480 | 0% | 480
2027-11-16 | 40 | 480 | 8.333% | 440
2027-11-17 | 0 | 480 | 0% | 480
2027-11-18 | 35 | 480 | 7.292% | 445
2027-11-19 | 0 | 480 | 0% | 480
2027-11-21 | 0 | 0 | N/A | 0
2027-11-22 | 0 | 480 | 0% | 480
2027-11-23 | 40 | 480 | 8.333% | 440
2027-11-24 | 0 | 480 | 0% | 480
2027-11-25 | 20 | 480 | 4.167% | 460
2027-11-26 | 0 | 480 | 0% | 480
2027-11-29 | 0 | 480 | 0% | 480
2027-11-30 | 0 | 480 | 0% | 480

## Fallback
FALLBACK SCENARIO — FERNDYKE LOCALISATION PASS SCHEDULE
Delayed music clearance: 29 Nov 2027 11:00 GMT ¦ Platform freeze: 30 Nov 2027 18:00 GMT
Forecast: all 11 episodes ingested by 29 Nov 2027 11:30; remaining margin 1830 minutes.
Chronology is controlled by the alternating Mireya Santos language rota, single QC Bay 1, dated availability and release gates.
Seq | Episode ID | Episode title | Runtime (min) | Language | Activity | Responsible owner / resource | Planned start | Planned finish | Booked min | Handoff / release dependency | Forecast ingest finish
1 | FDK-201 | Salt Road Witnesses | 24.2 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-08 09:00 | 2027-11-08 09:35 | 35 | Source handoff / language review | 2027-11-09 10:45
2 | FDK-201 | Salt Road Witnesses | 24.2 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-08 09:35 | 2027-11-08 10:15 | 40 | Caption lock complete — same episode / language | 2027-11-09 10:45
3 | FDK-202 | The Quiet Hoist | 26.6 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-08 10:15 | 2027-11-08 10:50 | 35 | Source handoff / language review | 2027-11-09 12:10
4 | FDK-202 | The Quiet Hoist | 26.6 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-08 10:50 | 2027-11-08 11:35 | 45 | Caption lock complete — same episode / language | 2027-11-09 12:10
5 | FDK-201 | Salt Road Witnesses | 24.2 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-09 09:00 | 2027-11-09 09:35 | 35 | Source handoff / language review | 2027-11-09 10:45
6 | FDK-201 | Salt Road Witnesses | 24.2 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-09 09:35 | 2027-11-09 10:15 | 40 | Caption lock complete — same episode / language | 2027-11-09 10:45
7 | FDK-201 | Salt Road Witnesses | 24.2 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-09 10:15 | 2027-11-09 10:30 | 15 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-09 10:45
8 | FDK-202 | The Quiet Hoist | 26.6 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-09 10:15 | 2027-11-09 10:50 | 35 | Source handoff / language review | 2027-11-09 12:10
9 | FDK-201 | Salt Road Witnesses | 24.2 | All required | Ingest | Quillhaven Platform Relay | 2027-11-09 10:30 | 2027-11-09 10:45 | 15 | QC complete / release package complete | 2027-11-09 10:45
10 | FDK-202 | The Quiet Hoist | 26.6 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-09 10:50 | 2027-11-09 11:35 | 45 | Caption lock complete — same episode / language | 2027-11-09 12:10
11 | FDK-202 | The Quiet Hoist | 26.6 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-09 11:35 | 2027-11-09 11:55 | 20 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-09 12:10
12 | FDK-202 | The Quiet Hoist | 26.6 | All required | Ingest | Quillhaven Platform Relay | 2027-11-09 11:55 | 2027-11-09 12:10 | 15 | QC complete / release package complete | 2027-11-09 12:10
13 | FDK-203 | Milepost at Dawn | 27.4 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-10 09:00 | 2027-11-10 09:35 | 35 | Source handoff / language review | 2027-11-11 10:55
14 | FDK-203 | Milepost at Dawn | 27.4 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-10 09:35 | 2027-11-10 10:20 | 45 | Caption lock complete — same episode / language | 2027-11-11 10:55
15 | FDK-204 | Borrowed Water | 23.8 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-10 10:20 | 2027-11-10 10:55 | 35 | Source handoff / language review | 2027-11-29 11:15
16 | FDK-204 | Borrowed Water | 23.8 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-10 10:55 | 2027-11-10 11:35 | 40 | Caption lock complete — same episode / language | 2027-11-29 11:15
17 | FDK-203 | Milepost at Dawn | 27.4 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-11 09:00 | 2027-11-11 09:35 | 35 | Source handoff / language review | 2027-11-11 10:55
18 | FDK-203 | Milepost at Dawn | 27.4 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-11 09:35 | 2027-11-11 10:20 | 45 | Caption lock complete — same episode / language | 2027-11-11 10:55
19 | FDK-203 | Milepost at Dawn | 27.4 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-11 10:20 | 2027-11-11 10:40 | 20 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-11 10:55
20 | FDK-204 | Borrowed Water | 23.8 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-11 10:20 | 2027-11-11 10:55 | 35 | Source handoff / language review | 2027-11-29 11:15
21 | FDK-203 | Milepost at Dawn | 27.4 | All required | Ingest | Quillhaven Platform Relay | 2027-11-11 10:40 | 2027-11-11 10:55 | 15 | QC complete / release package complete | 2027-11-11 10:55
22 | FDK-204 | Borrowed Water | 23.8 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-11 10:55 | 2027-11-11 11:35 | 40 | Caption lock complete — same episode / language | 2027-11-29 11:15
23 | FDK-204 | Borrowed Water | 23.8 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-11 11:35 | 2027-11-11 11:50 | 15 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-29 11:15
24 | FDK-205 | Tin Roof Arithmetic | 25.5 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-12 13:17 | 2027-11-12 13:52 | 35 | Source handoff / language review | 2027-11-16 10:55
25 | FDK-205 | Tin Roof Arithmetic | 25.5 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-12 13:52 | 2027-11-12 14:37 | 45 | Caption lock complete — same episode / language | 2027-11-16 10:55
26 | FDK-206 | Northbound Ledger | 28.2 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-12 14:37 | 2027-11-12 15:17 | 40 | Source handoff / language review | 2027-11-16 12:25
27 | FDK-206 | Northbound Ledger | 28.2 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-12 15:17 | 2027-11-12 16:07 | 50 | Caption lock complete — same episode / language | 2027-11-16 12:25
28 | FDK-207 | The Glass Orchard | 24.7 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-12 16:07 | 2027-11-12 16:42 | 35 | Source handoff / language review | 2027-11-18 10:50
29 | FDK-207 | The Glass Orchard | 24.7 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-15 09:00 | 2027-11-15 09:45 | 45 | Caption lock complete — same episode / language | 2027-11-18 10:50
30 | FDK-208 | Lower Signal | 29.1 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-15 09:45 | 2027-11-15 10:25 | 40 | Source handoff / language review | 2027-11-18 12:25
31 | FDK-208 | Lower Signal | 29.1 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-15 10:25 | 2027-11-15 11:15 | 50 | Caption lock complete — same episode / language | 2027-11-18 12:25
32 | FDK-209 | The Amber Division | 26.3 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-15 11:15 | 2027-11-15 11:50 | 35 | Source handoff / language review | 2027-11-29 11:30
33 | FDK-205 | Tin Roof Arithmetic | 25.5 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-16 09:00 | 2027-11-16 09:35 | 35 | Source handoff / language review | 2027-11-16 10:55
34 | FDK-205 | Tin Roof Arithmetic | 25.5 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-16 09:35 | 2027-11-16 10:20 | 45 | Caption lock complete — same episode / language | 2027-11-16 10:55
35 | FDK-205 | Tin Roof Arithmetic | 25.5 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-16 10:20 | 2027-11-16 10:40 | 20 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-16 10:55
36 | FDK-206 | Northbound Ledger | 28.2 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-16 10:20 | 2027-11-16 11:00 | 40 | Source handoff / language review | 2027-11-16 12:25
37 | FDK-205 | Tin Roof Arithmetic | 25.5 | All required | Ingest | Quillhaven Platform Relay | 2027-11-16 10:40 | 2027-11-16 10:55 | 15 | QC complete / release package complete | 2027-11-16 10:55
38 | FDK-206 | Northbound Ledger | 28.2 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-16 11:00 | 2027-11-16 11:50 | 50 | Caption lock complete — same episode / language | 2027-11-16 12:25
39 | FDK-206 | Northbound Ledger | 28.2 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-16 11:50 | 2027-11-16 12:10 | 20 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-16 12:25
40 | FDK-206 | Northbound Ledger | 28.2 | All required | Ingest | Quillhaven Platform Relay | 2027-11-16 12:10 | 2027-11-16 12:25 | 15 | QC complete / release package complete | 2027-11-16 12:25
41 | FDK-209 | The Amber Division | 26.3 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-17 09:00 | 2027-11-17 09:45 | 45 | Caption lock complete — same episode / language | 2027-11-29 11:30
42 | FDK-210 | Flood Mark | 25.8 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-17 09:45 | 2027-11-17 10:20 | 35 | Source handoff / language review | 2027-11-24 08:15
43 | FDK-210 | Flood Mark | 25.8 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-17 10:20 | 2027-11-17 11:05 | 45 | Caption lock complete — same episode / language | 2027-11-24 08:15
44 | FDK-211 | Hearth Country | 27.1 | Spanish | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-17 11:05 | 2027-11-17 11:40 | 35 | Source handoff / language review | 2027-11-25 10:55
45 | FDK-207 | The Glass Orchard | 24.7 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-18 09:00 | 2027-11-18 09:35 | 35 | Source handoff / language review | 2027-11-18 10:50
46 | FDK-207 | The Glass Orchard | 24.7 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-18 09:35 | 2027-11-18 10:20 | 45 | Caption lock complete — same episode / language | 2027-11-18 10:50
47 | FDK-207 | The Glass Orchard | 24.7 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-18 10:20 | 2027-11-18 10:35 | 15 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-18 10:50
48 | FDK-208 | Lower Signal | 29.1 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-18 10:20 | 2027-11-18 11:00 | 40 | Source handoff / language review | 2027-11-18 12:25
49 | FDK-207 | The Glass Orchard | 24.7 | All required | Ingest | Quillhaven Platform Relay | 2027-11-18 10:35 | 2027-11-18 10:50 | 15 | QC complete / release package complete | 2027-11-18 10:50
50 | FDK-208 | Lower Signal | 29.1 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-18 11:00 | 2027-11-18 11:50 | 50 | Caption lock complete — same episode / language | 2027-11-18 12:25
51 | FDK-208 | Lower Signal | 29.1 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-18 11:50 | 2027-11-18 12:10 | 20 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-18 12:25
52 | FDK-208 | Lower Signal | 29.1 | All required | Ingest | Quillhaven Platform Relay | 2027-11-18 12:10 | 2027-11-18 12:25 | 15 | QC complete / release package complete | 2027-11-18 12:25
53 | FDK-211 | Hearth Country | 27.1 | Spanish | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-19 09:00 | 2027-11-19 09:45 | 45 | Caption lock complete — same episode / language | 2027-11-25 10:55
54 | FDK-209 | The Amber Division | 26.3 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-23 09:00 | 2027-11-23 09:35 | 35 | Source handoff / language review | 2027-11-29 11:30
55 | FDK-209 | The Amber Division | 26.3 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-23 09:35 | 2027-11-23 10:20 | 45 | Caption lock complete — same episode / language | 2027-11-29 11:30
56 | FDK-209 | The Amber Division | 26.3 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-23 10:20 | 2027-11-23 10:40 | 20 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-29 11:30
57 | FDK-210 | Flood Mark | 25.8 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-23 10:20 | 2027-11-23 10:55 | 35 | Source handoff / language review | 2027-11-24 08:15
58 | FDK-210 | Flood Mark | 25.8 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-23 10:55 | 2027-11-23 11:40 | 45 | Caption lock complete — same episode / language | 2027-11-24 08:15
59 | FDK-210 | Flood Mark | 25.8 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-23 11:40 | 2027-11-23 12:00 | 20 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-24 08:15
60 | FDK-210 | Flood Mark | 25.8 | All required | Ingest | Quillhaven Platform Relay | 2027-11-24 08:00 | 2027-11-24 08:15 | 15 | QC complete / release package complete | 2027-11-24 08:15
61 | FDK-211 | Hearth Country | 27.1 | Portuguese | Caption lock | Mireya Santos — bilingual reviewer | 2027-11-25 09:00 | 2027-11-25 09:35 | 35 | Source handoff / language review | 2027-11-25 10:55
62 | FDK-211 | Hearth Country | 27.1 | Portuguese | Dub-sync | Mireya Santos — bilingual reviewer | 2027-11-25 09:35 | 2027-11-25 10:20 | 45 | Caption lock complete — same episode / language | 2027-11-25 10:55
63 | FDK-211 | Hearth Country | 27.1 | All required | QC | Darius Cole — QC operator / QC Bay 1 | 2027-11-25 10:20 | 2027-11-25 10:40 | 20 | All Spanish + Portuguese caption and dub-sync complete | 2027-11-25 10:55
64 | FDK-211 | Hearth Country | 27.1 | All required | Ingest | Quillhaven Platform Relay | 2027-11-25 10:40 | 2027-11-25 10:55 | 15 | QC complete / release package complete | 2027-11-25 10:55
65 | FDK-204 | Borrowed Water | 23.8 | All required | Ingest | Quillhaven Platform Relay | 2027-11-29 11:00 | 2027-11-29 11:15 | 15 | QC complete + music cue clearance | 2027-11-29 11:15
66 | FDK-209 | The Amber Division | 26.3 | All required | Ingest | Quillhaven Platform Relay | 2027-11-29 11:15 | 2027-11-29 11:30 | 15 | QC complete + music cue clearance | 2027-11-29 11:30
DAILY QC LOAD / AVAILABLE CAPACITY
QC Date | Scheduled QC load (min) | Available QC capacity (min) | Utilisation | Headroom (min)
2027-11-08 | 0 | 480 | 0% | 480
2027-11-09 | 35 | 480 | 7.292% | 445
2027-11-10 | 0 | 480 | 0% | 480
2027-11-11 | 35 | 480 | 7.292% | 445
2027-11-12 | 0 | 480 | 0% | 480
2027-11-15 | 0 | 480 | 0% | 480
2027-11-16 | 40 | 480 | 8.333% | 440
2027-11-17 | 0 | 480 | 0% | 480
2027-11-18 | 35 | 480 | 7.292% | 445
2027-11-19 | 0 | 480 | 0% | 480
2027-11-21 | 0 | 0 | N/A | 0
2027-11-22 | 0 | 480 | 0% | 480
2027-11-23 | 40 | 480 | 8.333% | 440
2027-11-24 | 0 | 480 | 0% | 480
2027-11-25 | 20 | 480 | 4.167% | 460
2027-11-26 | 0 | 480 | 0% | 480
2027-11-29 | 0 | 480 | 0% | 480
2027-11-30 | 0 | 480 | 0% | 480

## Review
FERNDYKE LOCALISATION — COUNSEL & DELIVERY REVIEW
Osgood Thanapoulos factual series ¦ England and Wales engagement ¦ position as at 4 November 2027
Recommendation: proceed on Preferred while retaining the Fallback pass order as the controlled delayed-clearance option.
Decision measure | Preferred — Base clearance | Fallback — Delayed clearance | Operational reading | Owner | Timing
Cue release gate | 26 Nov 2027 13:00 GMT | 29 Nov 2027 11:00 GMT | FDK-204 and FDK-209 are held at the shared cue gate.
Latest forecast ingest | 2027-11-26 13:30 | 2027-11-29 11:30 | Both options complete before the 30 Nov 18:00 platform freeze.
Remaining schedule margin | 6030 minutes | 1830 minutes | Margin is freeze timestamp less final ingest completion.
QC resource pressure | Single Bay 1; see daily table | Single Bay 1; see daily table | No overlap; the plan uses only Darius Cole and the dated bay records.
Clearance risk | Base gate preserves earlier release of cue pair. | Later gate compresses final release sequence. | Preferred gives more recovery time if a late release issue emerges.
Recommended path | Preferred | Fallback held ready | Use Preferred for greater cue-clearance margin while the same constrained roster remains viable. | Naledi Fairbairn | Confirm at 04 Nov control call
INTERPRETATIONS & CALCULATION CONVENTIONS
Ambiguous reviewer timestamp | Mireya Santos availability recorded as “11/12/27 13:17” is interpreted as 12 November 2027 13:17 (month/day/year). It sits in the Friday / ES block and inside the November production window; a day/month reading would place it in December and outside both.
Effort and booking | Caption, dub-sync and QC minutes equal runtime × the rate in the register, rounded upward to the contractual 5-minute booking increment. The 1.275 caption rate is calculated numerically before rounding.
QC capacity | Daily load is the booked QC minutes starting on that source date. Headroom equals available capacity less scheduled load. Where source capacity is zero (21 November closure), utilisation is shown as N/A; no QC is booked.
Release sequence | Caption lock → same-language dub-sync → episode QC after both languages → ingest after QC and, for FDK-204 / FDK-209, the applicable music cue gate.
NEXT ACTIONS — EXECUTABLE CONTROL POINTS
Action | Named owner | Timing / deadline | Evidence / handoff | Preferred impact | Fallback impact
Confirm shared music cue clearance for FDK-204 and FDK-209 | Ivo Kettering — music-clearance owner | Base: by 26 Nov 12:30 GMT; delayed contingency: 29 Nov 10:30 GMT | Written clearance to Naledi before Relay release | Enables 26 Nov 13:00 cue release | Protects 29 Nov 11:00 cue release
Lock Spanish / Portuguese review bookings | Mireya Santos — bilingual reviewer | By 05 Nov 2027 12:00 GMT | Confirm alternating ES Mon/Wed/Fri and PT Tue/Thu slots | Protects all language handoffs | Protects same pass sequence
Reserve QC Bay 1 sequence | Darius Cole — QC operator | By 05 Nov 2027 15:00 GMT | Accept dated single-bay booking sequence in Preferred and Fallback | Retains controlled QC order | Retains controlled QC order
Release final ingest package | Naledi Fairbairn — localisation coordinator | At each QC completion; final cue pair per applicable gate | QC completion + cue clearance (where applicable) to Quillhaven Platform Relay | Final forecast 26 Nov 13:30 | Final forecast 29 Nov 11:30
DAILY QC CAPACITY CROSS-CHECK (same convention in both scenario tabs)
QC date | Preferred load / cap / util. | Fallback load / cap / util. | Zero-capacity convention | Freeze | Status
2027-11-08 | 0 / 480 / 0.0% | 0 / 480 / 0.0% |  |  | Available
2027-11-09 | 35 / 480 / 7.3% | 35 / 480 / 7.3% |  |  | Available
2027-11-10 | 0 / 480 / 0.0% | 0 / 480 / 0.0% |  |  | Available
2027-11-11 | 35 / 480 / 7.3% | 35 / 480 / 7.3% |  |  | Available
2027-11-12 | 0 / 480 / 0.0% | 0 / 480 / 0.0% |  |  | Available
2027-11-15 | 0 / 480 / 0.0% | 0 / 480 / 0.0% |  |  | Available
2027-11-16 | 40 / 480 / 8.3% | 40 / 480 / 8.3% |  |  | Available
2027-11-17 | 0 / 480 / 0.0% | 0 / 480 / 0.0% |  |  | Available
2027-11-18 | 35 / 480 / 7.3% | 35 / 480 / 7.3% |  |  | Available
2027-11-19 | 0 / 480 / 0.0% | 0 / 480 / 0.0% |  |  | Available
2027-11-21 | 0 / 0 / N/A | 0 / 0 / N/A | N/A where capacity = 0 |  | Closure — no QC
2027-11-22 | 0 / 480 / 0.0% | 0 / 480 / 0.0% |  |  | Available
2027-11-23 | 40 / 480 / 8.3% | 40 / 480 / 8.3% |  |  | Available
2027-11-24 | 0 / 480 / 0.0% | 0 / 480 / 0.0% |  |  | Available
2027-11-25 | 20 / 480 / 4.2% | 20 / 480 / 4.2% |  |  | Available
2027-11-26 | 0 / 480 / 0.0% | 0 / 480 / 0.0% |  |  | Available
2027-11-29 | 0 / 480 / 0.0% | 0 / 480 / 0.0% |  |  | Available
2027-11-30 | 0 / 480 / 0.0% | 0 / 480 / 0.0% |  | 2027-11-30 18:00 | Available