## Activity Register
Cobblemoor Provisions ¦ maintenance-access activity register
Site | Cobblemoor Provisions distribution depot |  | Jurisdiction | England |  | Policy snapshot | 2026-06-05
Register exported | 05/06/2026 16:42 |  |  |  |  | Work starts | 2026-06-16
Activity ID | Activity | Class | Required | Fixed block | Mins | Predecessor | Canonical location | Electrical zone | Electrician | Isolation dep. | Escort | Noisy | Allowed date | Earliest | Latest | Scheduler note
A01 | North lockout setup | Maintenance | Yes | No | 30 |  | North Electrical Room | North | Yes | No | 1 | No | 2026-06-16 | 8:00 | 14:30
A02 | North isolation | Maintenance | Yes | No | 60 | A01 | North Electrical Room | North | Yes | No | 1 | No | 2026-06-16 | 8:00 | 14:30
A03 | North isolation-dependent work | Maintenance | Yes | No | 60 | A02 | North Electrical Room | North | Yes | Yes | 1 | No | 2026-06-16 | 8:00 | 14:30
A04 | North re-energisation | Maintenance | Yes | No | 30 | A03 | North Electrical Room | North | Yes | No | 1 | No | 2026-06-16 | 8:00 | 14:30
A05 | South lockout setup | Maintenance | Yes | No | 30 |  | South Electrical Room | South | Yes | No | 1 | No | 2026-06-16 | 8:00 | 14:30
A06 | South isolation | Maintenance | Yes | No | 60 | A05 | South Electrical Room | South | Yes | No | 1 | No | 2026-06-16 | 8:00 | 14:30
A07 | South isolation-dependent work | Maintenance | Yes | No | 60 | A06 | South Electrical Room | South | Yes | Yes | 1 | No | 2026-06-16 | 8:00 | 14:30
A08 | South re-energisation | Maintenance | Yes | No | 30 | A07 | South Electrical Room | South | Yes | No | 1 | No | 2026-06-16 | 8:00 | 14:30
A09 | Noisy functional test 1 | Maintenance | Yes | No | 60 |  | Test Bay | Test | No | No | 1 | Yes | 2026-06-16 | 8:00 | 10:00
A10 | Barrier setup | Maintenance | Yes | No | 30 |  | Loading Entrance | None | No | No | 1 | No | 2026-06-17 | 8:00 | 9:00
A11 | Access inspection | Maintenance | Yes | No | 60 | A10 | Loading Entrance | None | No | No | 1 | No | 2026-06-17 | 9:00 | 10:00
A12 | Noisy functional test 2 | Maintenance | Yes | No | 60 | A11 | Test Bay | Test | No | No | 1 | Yes | 2026-06-17 | 15:00 | 17:00
P01 | Public counter - morning 16 June | Public-counter service | Yes | Yes | 150 |  | Public Counter | None | No | No | 0 | No | 2026-06-16 | 9:30 | 12:00 | Fixed operational commitment
P02 | Public counter - afternoon 16 June | Public-counter service | Yes | Yes | 120 |  | Public Counter | None | No | No | 0 | No | 2026-06-16 | 13:00 | 15:00 | Fixed operational commitment
P03 | Public counter - morning 17 June | Public-counter service | Yes | Yes | 150 |  | Public Counter | None | No | No | 0 | No | 2026-06-17 | 9:30 | 12:00 | Fixed operational commitment
P04 | Public counter - afternoon 17 June | Public-counter service | Yes | Yes | 120 |  | Public Counter | None | No | No | 0 | No | 2026-06-17 | 13:00 | 15:00 | Fixed operational commitment

## Candidate Schedules
Candidate maintenance-access schedules ¦ received 5 June 2026
Rows are retained in submission order. Submitted date and start placements are access commitments; only unambiguous parsing and mapped location names may be normalized during inspection.
Scheduler export: AC-CP-0605 ¦ received from Arjun Calderon
Candidate | Source row | Activity ID | Submitted activity | Submitted date | Start | Finish | Submitted room | Electrician | Revision | Entry note
Candidate A | A-001 | A01 | North lockout setup | 2026-06-16 | 08.00 | 8:30 | North Elec Room | Chidi Gauthier
Candidate A | A-002 | A02 | North isolation | 2026-06-16 | 8:30 | 09:30 hrs | N. Electrical Rm | Chidi Gauthier
Candidate A | A-003 | A03 | North isolation-dependent work | 2026-06-16 | 09h30 | 10:30 | North Electrical Room | Chidi Gauthier
Candidate A | A-004 | A04 | North re-energisation | 2026-06-16 | 10:30 | 11.00 | North electrical | Chidi Gauthier
Candidate A | A-005 | A05 | South lockout setup | 2026-06-16 | 11:30 hrs | 12:00 | South Elec Rm | Chidi Gauthier
Candidate A | A-006 | A06 | South isolation | 2026-06-16 | 12:00 | 13:00 | South Electrical Room | Chidi Gauthier
Candidate A | A-007 | A07 | South isolation-dependent work | 2026-06-16 | 13:00 | 14h00 | S Electrical | Chidi Gauthier
Candidate A | A-008 | A08 | South re-energisation | 2026-06-16 | 14:00 | 14:30 | South electrical | Chidi Gauthier
Candidate A | A-009 | A09 | Noisy functional test 1 | 2026-06-16 | 08.30 | 09:30 hrs | Test-bay
Candidate A | A-010 | A10 | Barrier setup | 2026-06-17 | 8:00 | 08.30 | Loading Dock Entrance
Candidate A | A-011 | A11 | Access inspection | 2026-06-17 | 9:00 | 10:00 | Loading Entrance
Candidate A | A-012 | A12 | Noisy functional test 2 | 2026-06-17 | 15h30 | 16:30 | Function test bay
Candidate A | A-013 | P01 | Public counter - morning 16 June | 2026-06-16 | 9:30 | 12:00 | Counter - Public
Candidate A | A-014 | P02 | Public counter - afternoon 16 June | 2026-06-16 | 13:00 | 15:00 | Public Counter
Candidate A | A-015 | P03 | Public counter - morning 17 June | 2026-06-17 | 9:30 | 12:00 | Public service counter
Candidate A | A-016 | P04 | Public counter - afternoon 17 June | 2026-06-17 | 13:00 | 15:00 | Public Counter
Candidate B | B-001 | A01 | North lockout setup | 2026-06-16 | 8:00 | 08.30 | North Elec Room | Chidi Gauthier
Candidate B | B-002 | A02 | North isolation | 2026-06-16 | 08:30 hrs | 9:30 | N. Electrical Rm | Chidi Gauthier
Candidate B | B-003 | A03 | North isolation-dependent work | 2026-06-16 | 9:30 | 10h30 | North Electrical Room | Chidi Gauthier
Candidate B | B-003X | A03 | North isolation-dependent work | 2026-06-16 | 9:30 | 10h30 | North Electrical Room | Chidi Gauthier
Candidate B | B-004 | A04 | North re-energisation | 2026-06-16 | 10.30 | 11:00 | North electrical | Chidi Gauthier
Candidate B | B-005 | A05 | South lockout setup | 2026-06-16 | 11h30 | 12:00 | South Elec Rm | Chidi Gauthier
Candidate B | B-006 | A06 | South isolation | 2026-06-16 | 12:00 | 13:00 hrs | South Electrical Room | Chidi Gauthier
Candidate B | B-007 | A07 | South isolation-dependent work | 2026-06-16 | 13:00 | 14.00 | S Electrical | Chidi Gauthier
Candidate B | B-008 | A08 | South re-energisation | 2026-06-16 | 14:00 | 14:30 | South electrical | Chidi Gauthier
Candidate B | B-009 | A09 | Noisy functional test 1 | 2026-06-16 | 08:00 hrs | 09h00 | Test-bay
Candidate B | B-010A | A10 | Barrier setup | 2026-06-17 | 08.00 | 08.30 | Loading Dock Entrance
Candidate B | B-010B | A10 | Barrier setup | 2026-06-17 | 8:30 | 9:00 | Barrier area
Candidate B | B-011 | A11 | Access inspection | 2026-06-17 | 9:00 | 10:00 hrs | Loading Entrance
Candidate B | B-012 | A12 | Noisy functional test 2 | 2026-06-17 | 15h30 | 16h30 | Function test bay
Candidate B | B-013 | P01 | Public counter - morning 16 June | 2026-06-16 | 9:30 | 12:00 | Counter - Public
Candidate B | B-014 | P02 | Public counter - afternoon 16 June | 2026-06-16 | 13:00 | 15:00 | Public Counter
Candidate B | B-015 | P03 | Public counter - morning 17 June | 2026-06-17 | 9:30 | 12:00 | Public service counter
Candidate B | B-016 | P04 | Public counter - afternoon 17 June | 2026-06-17 | 13:00 | 15:00 | Public Counter
Candidate C | C-001 | A01 | North lockout setup | 2026-06-16 | 8:00 | 08.30 | North Electrical Room | Chidi Gauthier
Candidate C | C-002 | A05 | South lockout setup | 2026-06-16 | 08.30 | 9:00 | South Elec Rm | Chidi Gauthier
Candidate C | C-003 | A02 | North isolation | 2026-06-16 | 09:00 hrs | 10:00 | N. Electrical Rm | Chidi Gauthier
Candidate C | C-004 | A06 | South isolation | 2026-06-16 | 10:00 | 11h00 | South Electrical Room | Chidi Gauthier
Candidate C | C-005 | A03 | North isolation-dependent work | 2026-06-16 | 11:00 | 12:00 | North electrical | Chidi Gauthier
Candidate C | C-006 | A07 | South isolation-dependent work | 2026-06-16 | 12h00 | 13:00 hrs | S Electrical | Chidi Gauthier
Candidate C | C-007 | A04 | North re-energisation | 2026-06-16 | 13:00 | 13.30 | North Elec Room | Chidi Gauthier
Candidate C | C-008 | A08 | South re-energisation | 2026-06-16 | 14:00 | 14:30 | South electrical | Chidi Gauthier
Candidate C | C-009 | A09 | Noisy functional test 1 | 2026-06-16 | 8:00 | 09h00 | Test-bay
Candidate C | C-010 | A10 | Barrier setup | 2026-06-17 | 08.00 | 8:30 | Loading Dock Entrance
Candidate C | C-011 | A11 | Access inspection | 2026-06-17 | 9:00 | 10:00 hrs | Loading Entrance
Candidate C | C-012 | A12 | Noisy functional test 2 | 2026-06-17 | 15h30 | 16:30 | Function test bay
Candidate C | C-013 | P01 | Public counter - morning 16 June | 2026-06-16 | 9:30 | 12:00 | Counter - Public
Candidate C | C-014 | P02 | Public counter - afternoon 16 June | 2026-06-16 | 13:00 | 15:00 | Public Counter
Candidate C | C-015 | P03 | Public counter - morning 17 June | 2026-06-17 | 9:30 | 12:00 | Public service counter
Candidate C | C-016 | P04 | Public counter - afternoon 17 June | 2026-06-17 | 13:00 | 15:00 | Public Counter

## Controls & Template
Cobblemoor Provisions ¦ submission controls and approval template
Submission controls
Site jurisdiction | England
Authorised work dates | 16 Jun 2026; 17 Jun 2026
Daily access | 08:00-18:00
Slot length | 30 minutes
Maintenance escorts available | 2
Authorised electrician | Chidi Gauthier
Electrician availability | 16 Jun 2026 08:00-14:30 only
Inspection deadline | 10 Jun 2026 12:00
Submission rule | No movement of a unique submitted date or start; resolve only uniquely parseable times and mapped locations.
Repeated activity rows | No revision marker was supplied; row order and formatting are not evidence of supersession.
Room-name mapping |  |  |  | Approval template
Submitted room | Canonical location | Electrical zone | Capacity | Controlled field | Permitted values / field purpose | Gold-free template note
North Electrical Room | North Electrical Room | North | 1 | Selected candidate | Candidate A; Candidate B; Candidate C | identify one submitted schedule
North Elec Room | North Electrical Room | North | 1 | Inspection result | Compliant; Non-compliant; Not assessed | factual inspection result
N. Electrical Rm | North Electrical Room | North | 1 | Overall status | Pending approval; Approved; Rejected | must remain Pending approval during inspection
North electrical | North Electrical Room | North | 1 | Issue type | Normalization; Duplicate disposition; Constraint blocker; Source observation | use in correction record
South Electrical Room | South Electrical Room | South | 1 | Disposition | Corrected; Retained by judgement; Excluded; Rejected candidate; No change | use in correction record
South Elec Rm | South Electrical Room | South | 1 | Prepared by | free text | administrative-services manager
S Electrical | South Electrical Room | South | 1 | Peer reviewer | free text | reviewer named in request
South electrical | South Electrical Room | South | 1 | Approval decision | Pending approval; Approved; Rejected | not for manager completion
Test Bay | Test Bay | Test | 1 | Summary definition | Maintenance minutes count the 12 maintenance activities once each and exclude public-counter service blocks. | repeat in inspection record
Test-bay | Test Bay | Test | 1
Function test bay | Test Bay | Test | 1
Loading Entrance | Loading Entrance | None | 1
Loading Dock Entrance | Loading Entrance | None | 1
Barrier area | Loading Entrance | None | 1
Public Counter | Public Counter | None | 1
Counter - Public | Public Counter | None | 1
Public service counter | Public Counter | None | 1
Source note | Blank revision cells are retained from the scheduler export. They do not establish which repeated row, if any, supersedes another.