## Work register
Cobblemoor Field Services - emissions monitoring recovery register
Export run: 11/05/2026 16:42 ¦ Filter: district-energy plant rooms ¦ owner set frozen
Effort is technician person-hours. Empty effort fields are as received from the field return.
Package No. | Plant room | Equipment family | Work description | Record type | Release status | Superseded by | Evidence grade | Confidence % | Permit coverage tags | Site ready | Access from | Access to | Permitted shift | Predecessor | Tech effort (hrs) | Fixed cost GBP | Engineer test? | Accountable | Comparable job ref | Register note
CG-101 | Crossgate | Horizon | Analyzer trim and telemetry prove-out | Implementation | Released |  | A | 92% | CG-AC, CG-TC | 2026-05-18 | 2026-05-18 | 2026-05-18 | PM |  | 8 | 3900 | Yes | Lorcan Ibarra |  | released work order
CG-102 | Crossgate | Horizon | Audit trail capture and witnessed evidence | Implementation | Released |  | B | 86% | CG-AW | 2026-05-18 | 2026-05-19 | 2026-05-19 | AM | CG-101 |  | 2350 | Yes | Lorcan Ibarra | HZN-AUD-02 | field duration not returned
CG-103 | Crossgate | Horizon | Alternate analyzer calibration with audit capture | Implementation | Released |  | A | 90% | CG-AC | 2026-05-18 | 2026-05-18 | 2026-05-18 | PM |  | 9 | 4200 | Yes | Lorcan Ibarra |  | alternate released method
CG-104 | Crossgate | Horizon | Alternate telemetry and witnessed evidence verification | Implementation | Released |  | B | 85% | CG-TC, CG-AW | 2026-05-18 | 2026-05-19 | 2026-05-19 | AM | CG-103 |  | 2450 | Yes | Lorcan Ibarra | HZN-AUD-02 | field duration not returned
MH-201 | Millhaven | Horizon | Analyzer calibration and evidence chain | Implementation | Released |  | A | 94% | MH-AC, MH-AW | 2026-05-20 | 2026-05-20 | 2026-05-20 | PM |  | 12 | 4800 | Yes | Lorcan Ibarra |  | occupied-site allocation held
MH-202 | Millhaven | Horizon | Telemetry continuity proving run | Implementation | Released |  | B | 88% | MH-TC | 2026-05-20 | 2026-05-21 | 2026-05-21 | AM | MH-201 | 6 | 2100 | Yes | Lorcan Ibarra |  | after analyzer handshake
MH-203 | Millhaven | Horizon | Alternate analyzer and telemetry set-up | Implementation | Released |  | A | 91% | MH-AC, MH-TC | 2026-05-20 | 2026-05-20 | 2026-05-20 | PM |  | 12 | 4950 | Yes | Lorcan Ibarra |  | alternate released method
MH-204 | Millhaven | Horizon | Alternate witnessed audit pack | Implementation | Released |  | B | 84% | MH-AW | 2026-05-20 | 2026-05-21 | 2026-05-21 | AM | MH-203 | 5 | 2300 | Yes | Lorcan Ibarra |  | paired with MH-203
DS-301 | Docksett | Kestrel | Analyzer trim and telemetry proving run | Implementation | Released |  | A | 93% | DS-AC, DS-TC | 2026-05-26 | 2026-05-26 | 2026-05-26 | PM |  | 12 | 4650 | Yes | Lorcan Ibarra |  | occupied-site allocation held
DS-302 | Docksett | Kestrel | Audit trail capture and witnessed evidence | Implementation | Released |  | B | 87% | DS-AW | 2026-05-26 | 2026-05-27 | 2026-05-27 | AM | DS-301 |  | 2450 | Yes | Lorcan Ibarra | KST-AUD-07 | field duration not returned
DS-303 | Docksett | Kestrel | Alternate analyzer calibration with audit capture | Implementation | Released |  | A | 90% | DS-AC, DS-AW | 2026-05-26 | 2026-05-26 | 2026-05-26 | PM |  | 12 | 5000 | Yes | Lorcan Ibarra |  | alternate released method
DS-304 | Docksett | Kestrel | Alternate telemetry continuity verification | Implementation | Released |  | B | 85% | DS-TC | 2026-05-26 | 2026-05-27 | 2026-05-27 | AM | DS-303 | 5 | 2300 | Yes | Lorcan Ibarra |  | paired with DS-303
LF-401 | Larkfield | Kestrel | Integrated analyzer, telemetry and witness close-out | Implementation | Released |  | A | 95% | LF-AC, LF-TC, LF-AW | 2026-05-28 | 2026-05-28 | 2026-05-28 | PM |  | 18 | 5100 | Yes | Lorcan Ibarra |  | full plant-room close-out
LF-402 | Larkfield | Kestrel | Analyzer-only intervention | Implementation | Released |  | B | 89% | LF-AC | 2026-05-28 | 2026-05-28 | 2026-05-28 | PM |  | 6 | 1650 | Yes | Lorcan Ibarra |  | partial released scope
LF-403 | Larkfield | Kestrel | Telemetry-only intervention | Implementation | Released |  | B | 88% | LF-TC | 2026-05-28 | 2026-05-28 | 2026-05-28 | PM |  | 6 | 1580 | Yes | Lorcan Ibarra |  | partial released scope
LF-404 | Larkfield | Kestrel | Witness evidence-only intervention | Implementation | Released |  | B | 83% | LF-AW | 2026-05-28 | 2026-05-28 | 2026-05-28 | PM |  | 6 | 1740 | Yes | Lorcan Ibarra |  | partial released scope
LF-405 | Larkfield | Kestrel | Analyzer and telemetry partial intervention | Implementation | Released |  | A | 90% | LF-AC, LF-TC | 2026-05-28 | 2026-05-28 | 2026-05-28 | PM |  | 12 | 3120 | Yes | Lorcan Ibarra |  | would still require a separate audit package
LF-406 | Larkfield | Kestrel | Trace-only witness evidence intervention | Implementation | Released |  | B | 82% | LF-AW | 2026-05-28 | 2026-05-28 | 2026-05-28 | PM |  | 6 | 1810 | Yes | Lorcan Ibarra |  | partial released scope
CG-105 | Crossgate | Horizon | Combined analyzer, telemetry and witness recovery | Implementation | Released |  | A | 79% | CG-AC, CG-TC, CG-AW | 2026-05-18 | 2026-05-18 | 2026-05-18 | PM |  | 10 | 3350 | Yes | Lorcan Ibarra |  | confidence pending final review
MH-205 | Millhaven | Horizon | Low-cost combined recovery package | Implementation | Released |  | C | 93% | MH-AC, MH-TC, MH-AW | 2026-05-20 | 2026-05-20 | 2026-05-20 | PM |  | 10 | 3250 | Yes | Lorcan Ibarra |  | evidence source is grade C
DS-305 | Docksett | Kestrel | Broad close-out pack | Implementation | Released | DS-301 | A | 96% | DS-AC, DS-TC, DS-AW | 2026-05-26 | 2026-05-26 | 2026-05-26 | PM |  | 11 | 3850 | Yes | Lorcan Ibarra |  | replaced after field issue review
LF-407 | Larkfield | Kestrel | Integrated close-out package | Implementation | Hold - not released |  | B | 91% | LF-AC, LF-TC, LF-AW | 2026-05-28 | 2026-05-28 | 2026-05-28 | PM |  | 16 | 3450 | Yes | Lorcan Ibarra |  | technical content complete; release not granted

## Plant calendar
Plant access calendar and operating restrictions
Recovered from weekly field plan; 25 May is not an available workday in this issue.
Blackout log
Date | Day | Workday | Permitted shifts | Tech cap (hrs) | Occupied site? | Engineer available | Plant room | Date | Shift | Restriction
2026-05-18 | Mon | Yes | AM / PM | 18 | No | PM | Crossgate | 2026-05-18 | AM | resident heat-demand changeover
2026-05-19 | Tue | Yes | AM / PM | 18 | No | AM | Crossgate | 2026-05-19 | PM | boiler proving window
2026-05-20 | Wed | Yes | AM / PM | 12 | Yes | PM | Millhaven | 2026-05-20 | AM | occupied-site pump inspection
2026-05-21 | Thu | Yes | AM / PM | 18 | No | AM | Millhaven | 2026-05-21 | PM | landlord access restriction
2026-05-22 | Fri | Yes | AM / PM | 18 | No | AM | Docksett | 2026-05-26 | AM | occupied-site water treatment
2026-05-26 | Tue | Yes | AM / PM | 12 | Yes | PM | Docksett | 2026-05-27 | PM | district-load peak
2026-05-27 | Wed | Yes | AM / PM | 18 | No | AM | Larkfield | 2026-05-28 | AM | safety-system monthly check
2026-05-28 | Thu | Yes | AM / PM | 18 | No | PM
2026-05-29 | Fri | Yes | AM only | 18 | No

## Comparable jobs
Completed comparable effort records
Ranges are technician person-hours from closed field returns; no overtime included.
Job ref | Equipment family | Comparable scope | Low hrs | Typical hrs | High hrs | Close-out comment
HZN-AUD-02 | Horizon | Audit / witnessed commissioning evidence | 4 | 5 | 6 | same cabinet class; completed 17 Feb
KST-AUD-07 | Kestrel | Audit / witnessed commissioning evidence | 5 | 6 | 7 | same recorder revision; completed 03 Mar
KST-TRACE-02 | Kestrel | Trace capture / witness evidence | 5 | 6 | 7 | single-room trace capture; completed 11 Jan
HZN-CAL-11 | Horizon | Analyzer and telemetry proving run | 7 | 8 | 10 | two-person field task; completed 26 Feb
KST-CAL-04 | Kestrel | Analyzer and telemetry proving run | 10 | 12 | 14 | occupied-site method; completed 08 Apr

## Responsibility log
Recovery responsibility extract
Named accountability is limited to the project instruction and current field-service release.
Person | Organisation | Recorded role | Accountability boundary
Lorcan Ibarra | Cobblemoor Field Services | Field delivery lead / certified commissioning engineer | Accountable for released implementation package execution and commissioning evidence
Magda Villanueva | Ambergate Housing Trust | Project Management Specialist | Accountable for recovery approval, quality review and regulator submission