## Slide 1
CINDERHALL LOGISTICS BOARD | DECISION BRIEF
Authorize the Thursday Everstead high-risk chemical delivery operating plan
Full-capacity hybrid serves current 8-vehicle capacity; positive verification is non-waivable.
BOARD ACTION
Authorize Plan A - Full-capacity hybrid - for Thursday 23 Oct 2025; approve activation by 05:15.
Event
Everstead delivery
Venue
Gate 3 controlled area
Movement window
06:30-10:30
Coverage / closeout
05:45-12:15
Operating audience
Board members; watch commanders; dispatch; Gate 3 personnel; escort/response personnel; and staff new to mobile dispatch.
Operational owner: Jelena Skarsgard, Watch Operations Lieutenant.
Governing frame
Maryland jurisdiction
Maryland and Cinderhall local-policy snapshot frozen as of 15 Oct 2025
Decision purpose: authorize an executable delivery operation, not a later study. This deck gives the Board and posts one operating model and one control boundary.
Maryland snapshot frozen as of 15 Oct 2025
1
Notes: Recommendation: authorize the full-capacity hybrid plan. The following slides explain the current vehicle capacity assumption, evidence, staffing, transition procedure, and exception controls.

## Slide 2
DECISION BASIS
Capacity planning has one source; admission has a separate authority
02
CURRENT CLIENT RECORD
8 vehicles
Everstead client manifest, Revision 3
Received from Everstead Industries Dispatch: 15 Oct 2025 16:20. Owner: Everstead Industries Dispatch.
FROZEN POLICE RECORD
6 vehicles
CLPD logistics sheet, Revision 1
Cinderhall Logistics Police Division logistics sheet, frozen 13 Oct 2025 14:00. Owner: Watch Operations logistics desk. The frozen sheet was prepared before the current client Revision 3 was received.
AUTHORIZED PLANNING RULE
Plan capacity to the current eight-vehicle client manifest.
Revision currency and client ownership avoid under-planning. The older police sheet stays in the reconciliation file.
Planning capacity does not grant entry
At 05:45, the Watch Commander and Everstead Dispatch reconcile Revision 3 into the final gate roster. Each arriving vehicle and driver must still positively link to the authorized current delivery record before Gate Cleared or Released status. A planned eighth vehicle is not automatically admitted.
Informal assurance
Rhodri Gauthier's no-delay assurance is not operational authority to waive verification.
Service objective: orderly staged arrivals and the fastest practical verified processing - not zero delay at any cost.
Record discipline
The forwarded 14 Oct chain is one correspondence source, not independent corroboration. Revision 3 is the operative planning revision; the reconciled gate roster controls an individual arrival.
Packet refs: client manifest Rev 3; frozen CLPD logistics Rev 1; correspondence; Gate 3 record
2
Notes: The plan deliberately selects the current client revision for capacity, not admission. The Board is not being asked to choose between six and eight after approval.

## Slide 3
OPTIONS COMPARED
Authorize the full-capacity hybrid; preserve verified flow through the transition
03
MODEL
CAPACITY / STAFFING
CHECK-IN MODEL
CONTROL + SERVICE EFFECT
THURSDAY / STEADY STATE
SELECTED
Full-capacity hybrid
8 planned
8 (7 sworn + 1 dispatcher)
1 dispatcher; mobile receipt/assignment plus radio parallel and fallback
Two gate verifiers can work while staging and relief remain available. No overtime needed.
Thursday: mobile + radio. Later: mobile primary, radio fallback; control boundary unchanged.
VIABLE, NOT SELECTED
Six-vehicle base + verified surge
6 base; 7th/8th staged until supervisor activates on-site reserve as second gate verifier
7 (6 sworn + 1 dispatcher)
1 dispatcher; mixed radio/mobile
Feasible when arrivals stay sequenced. It preserves a surge path but delays the seventh/eighth vehicle while the reserve changes post.
Thursday workable, but a seventh/eighth waits for post change. Later remains a surge model.
DO NOT AUTHORIZE
Lean mobile-dependent
8 nominal
5 (4 sworn + 1 dispatcher)
1 dispatcher; mobile used as principal arrival workflow; radio only after failure
Uses fewer people but has no relief or second verifier. A mismatch or mobile issue consumes the combined post.
Fast on paper, but depends on mobile interpretation and a combined post during a known transition risk.
Why the lean mobile-dependent model is rejected: the pilot's 4/6 exception/rework count includes accepted-as-clearance rework and connectivity fallback; it also has no relief or second verifier. The six-vehicle surge model is viable, but full eight-vehicle staffing avoids holding verified added vehicles for a post conversion.
Packet refs: Thursday resources and coverage alternatives; operating-record comparison
3
Notes: At least two staffing/check-in alternatives are viable. The selected model is Plan A. The deck does not make the apparent speed of the lean option a substitute for safety or legal controls.

## Slide 4
TRANSITION EVIDENCE
Mobile improves timeliness, but the pilot does not prove a mobile-only control model
04
RADIO BASELINE
01 Sep 2025 00:00 through 14 Sep 2025 23:59 | n=6 eligible arrivals
MOBILE PILOT
22 Sep 2025 00:00 through 05 Oct 2025 23:59 | n=6 eligible arrivals
INTERPRETATION
Use mobile for faster dispatch acknowledgement, while retaining separate verification, gate, release, and fallback controls.
Median dispatch acknowledgement
Same metric definition in both periods
Radio
8.0min
Mobile
2.5min
Lower is faster
Median check-in to positive verification
Same metric definition in both periods
Radio
18.0min
Mobile
15.5min
Lower is faster
Exception / mismatch / rework
Same metric definition in both periods
Radio
17.0%
Mobile
67.0%
1/6 vs 4/6 eligible events
Cleaning treatment and limitation
Normalized vehicle, checkpoint, channel, and acknowledgement labels; removed 1 radio and 2 mobile duplicate/near-duplicate rows; excluded training/demo/cancelled/unrelated rows and the one malformed 07:1? start. Check-in = start through positive verification. Accepted alone is not an exception or clearance. Small pilot workflow and data-quality limits prevent inferring full steady-state safety.
Packet refs: radio baseline and mobile-pilot event exports; derived after stated cleaning treatment
4
Notes: The metric comparison is deliberately not a claim that mobile is uniformly better. It supports a hybrid transition: faster acknowledgement with stronger closed-loop controls.

## Slide 5
CONTROL BOUNDARY
Mandatory access-control steps stay separate from preferred efficiency practices
05
MANDATORY - no waiver by service assurance, escort, emergency equipment, or Accepted status
PREFERRED - use when feasible; never a substitute for a required step
ACCEPTED
Dispatch received or assigned the report. NOT gate clearance, verification, entry approval, or movement release.
VERIFIED
Gate verifier positively links vehicle + driver to the authorized current delivery record.
GATE CLEARED
Gate officer permits controlled entry only after VERIFIED and the dispatch record is updated.
RELEASED
Watch Commander authorizes escort / movement only after all required checks are complete.
HOLD
Keep vehicle in controlled staging; dispatcher logs it; commander resolves mismatch before any entry or release.
Every time
- Positive vehicle/driver linkage before controlled entry - Controlled staging for unresolved records - Supervisor decision for a mismatch or substitution - One accountable dispatch record - Radio fallback and record reconciliation
Use when feasible
- Advance roster reconciliation - Spaced arrivals and queue updates - Mobile-first convenience once trained - Service-oriented staging management
Closed-loop rule
Sender reports status; dispatcher repeats and records it; the role owning the next status confirms its own action.
Authority: MFAR 8.4, 8.6, 8.7; CLPD GO-4.12; CD-2.7; Gate Post Order G-3 | frozen 15 Oct 2025
5
Notes: This is the must-versus-preferred boundary. Accepted is actively prohibited as a clearance status.

## Slide 6
AUTHORIZED STAFFING
Plan A uses the confirmed full-capacity hybrid: eight positions from briefing through closeout
06
8 (7 sworn + 1 dispatcher) | 8 planned | 05:45-12:15 | two marked police utility units | no overtime required
1
Watch Commander
Exception decisions; movement release; keeps command authority
2
Gate verification
Positive vehicle/driver/current-record link; issue VERIFIED and GATE CLEARED
1
Staging / traffic
Protect controlled queue and keep discrepancy work off the roadway
2
Escort / response
Operate the two marked police utility units; escort and initial response
1
Relief / reserve
Relieve gate/staging; backfill a key post during an exception
1
Dispatch coordinator
Accountable event log; mobile/radio acknowledgement; fallback record
Break / loss-of-post continuity
During breaks, relief/reserve covers Gate or staging before a break. If a key post is lost, commander freezes new Gate Cleared / Released actions, stages arrivals, and backfills with relief/reserve.
Resource check
Matches packet availability: seven sworn, one dispatcher, two utility units, one Gate 3/staging lane. The commander is not counted as a verifier; dispatch is not duplicated.
Packet refs: Thursday resources and coverage alternatives; current delivery record and Gate 3 posts
6
Notes: The staffing sum is 7 sworn plus 1 dispatcher = 8 positions. It provides the functions required across the full operating window, including practical relief.

## Slide 7
THURSDAY PROCEDURE
Pre-arrival reconciliation and controlled arrival sequence
07
05:15
BOARD AUTHORIZATION
Board approves Plan A. Jelena Skarsgard activates the plan and posts the briefing.
05:45
RECONCILE
Watch Commander + Everstead Dispatch reconcile the current 8-vehicle Revision 3 into the final gate roster. Send one roster to Gate and Dispatch.
06:15
OPEN STAGING
Staging/traffic officer opens the controlled lane; dispatcher opens the accountable event record.
06:30-10:30
SEQUENCED ARRIVALS
Gate verification, gate clearance, and command release occur as separate closed-loop decisions.
1
STAGE
Every arrival goes to controlled staging. Dispatcher logs ARRIVED/STAGED. Mobile may show ACCEPTED; that does not permit entry.
2
VERIFY
Two gate verifiers positively match vehicle ID and driver record to the final current delivery record. Then report VERIFIED.
3
CLEAR GATE
Gate officer records GATE CLEARED only after VERIFIED. The vehicle may enter the controlled area; a mismatch never resolves at the roadway.
4
RELEASE MOVEMENT
Watch Commander confirms required checks and the dispatch record, then authorizes RELEASED for escort / convoy movement.
Late change rule
A late manifest revision, unlisted vehicle, driver mismatch, or substitution does not inherit clearance. Gate officer keeps it in staging, dispatcher records HOLD, and the Watch Commander decides only after Everstead Dispatch provides a current record and the gate repeats positive verification.
Authority: MFAR 8.4, 8.7; CLPD GO-4.12; CD-2.7; Gate Post Order G-3
7
Notes: This slide is the procedural sequence for a normal planned vehicle, including the separate gate and movement release decisions. It also establishes the pre-arrival owner and timing.

## Slide 8
TRANSITION AND EXCEPTIONS
Mixed mobile/radio operation on Thursday; defined fallback and safety-critical branch
08
THURSDAY: TRANSITION MODE
- Trained personnel may use mobile for receipt/assignment and status reporting. - Dispatcher mirrors mobile and radio actions in one accountable event record. - Personnel not trained on mobile use radio. - ACCEPTED stays dispatch acknowledgement only.
RADIO FALLBACK
Trigger: mobile outage, failed acknowledgement, device failure, or an untrained user. Dispatcher declares RADIO FALLBACK, logs time/reason, and repeats closed-loop radio statuses. On restoration, dispatcher reconciles the radio record before resuming mobile.
LATER: MOBILE STANDARD
Upon formal CLPD activation, mobile becomes the primary dispatch workflow. Radio remains fallback. The same VERIFED, GATE CLEARED, RELEASED, HOLD, and supervisor controls do not change.
Mismatch / count / substitution branch
1. Gate officer: HOLD in controlled staging; do not admit or reject based on a promise. 2. Dispatcher: record HOLD and notify Watch Commander. 3. Watch Commander: obtain current record from Everstead Dispatch and resolve the count/identity discrepancy. 4. Gate: repeat positive vehicle/driver linkage. Only then VERIFIED -> GATE CLEARED -> RELEASED.
Safety-critical interruption
Spill, security threat, disabled vehicle, or comparable safety interruption: STOP routine movement; protect the gate/staging area; dispatcher notifies the Watch Commander; transfer to incident command under GO-4.12. Keep the emergency response separate from ordinary delay handling. Resume only on commander authorization.
Closed-loop language prevents confusion: dispatch acknowledgement, verification, physical gate clearance, and movement release are different events with different owners.
Authority: CLPD Communications Directive CD-2.7; GO-4.12; Gate Post Order G-3
8
Notes: The fallback is not simply leaving a radio on. It has triggers, a declaration, ownership, record handling, and a way to reconcile back into mobile.

## Slide 9
AUTHORIZATION, CHANGE, AND CLOSEOUT
The Board authorizes one operation for Thursday and a controlled path to mobile standard
09
ACTIVATION STATEMENT
On Board approval by 05:15 Thursday 23 Oct 2025, Jelena Skarsgard activates Plan A - Full-capacity hybrid - for the Everstead delivery. It replaces the interim radio-only / inconsistent mobile-pilot practice for this operation.
WHAT CHANGES THURSDAY
- Capacity and posts are set for the current eight-vehicle manifest. - 05:45 reconciliation creates one final gate roster. - Trained users may use mobile; dispatcher maintains radio continuity. - ACCEPTED cannot be treated as clearance. - Gate and movement release stay separate decisions.
WHAT CHANGES AFTER MOBILE STANDARD
- Mobile becomes primary only after formal CLPD activation. - Radio stays the declared fallback. - Dispatcher still maintains one accountable record. - Positive vehicle/driver linkage, HOLD, commander decision, GATE CLEARED, and RELEASED do not change.
CLOSEOUT / ACCOUNTABILITY
Dispatcher closes and reconciles the dispatch event record; Gate 3 closes the final gate roster; Watch Commander documents any HOLD, exception, late change, or staffing change. Jelena Skarsgard owns the after-action review due Friday 24 Oct 2025 by 16:00.
Packet refs: dated delivery brief; current transition terms; local authority snapshot
9
Notes: This is the Board-facing authorization language. It identifies activation, plan owner, the practice being modified, two workflow horizons, and concrete closeout accountability.

## Slide 10
EXECUTION CARD AND SOURCE TRAIL
Four common situations have one unambiguous path
10
Planned vehicle
STAGE -> ACCEPTED -> VERIFY -> GATE CLEARED -> RELEASED
Vehicle and driver match final roster; normal queue flow continues.
Additional verified vehicle
Use Plan A eight-vehicle capacity; follow the same status sequence
It remains subject to final roster + positive link. Capacity is not automatic admission.
Unlisted / mismatch
HOLD in staging -> dispatcher log -> commander decision -> re-verify
No entry or release from an informal assurance, a prior list position, or Accepted.
Mobile outage
Dispatcher declares RADIO FALLBACK -> closed-loop radio -> reconcile
Untrained personnel use the same radio path; resume mobile only after reconciliation.
Controlling record trail
Capacity: Everstead client manifest Revision 3, received 15 Oct 2025 16:20. Entry: final 05:45 reconciled gate roster + gate positive verification. Baseline reference: CLPD logistics Revision 1, frozen 13 Oct 2025 14:00.
Mandatory authority trail
Maryland Freight Facility Access Regulation (MFAR) 8.4, 8.6, 8.7; CLPD General Order GO-4.12; CLPD Communications Directive CD-2.7; Gate Post Order G-3. Frozen Maryland/local snapshot current as of 15 Oct 2025.
Source packet only: manifest/logistics revisions, correspondence, Gate 3 exports, resources, and frozen authority snapshot
10
Notes: This final execution card is intended for the supervisor, dispatcher, and gate post. It resolves the normal, additional, mismatch, and outage cases without needing clarification.