## Revised Schedule
Kingsferry Regional Office – Revised Move Plan & Estimate
Booking basis for Leonie Sandoval ¦ Authorized revision by Priya Demirci ¦ Continuing-clock premium branch
Weekend | Package ID | Department | Stage | Origin | Destination | Start | Finish | Duration (min) | Crew | Elevator start | Elevator finish | Elevator min | Freight blocks | Loading start | Loading finish | Vault? | Swing occupancy start | Swing occupancy release | Regular crew h | Premium crew h | Labor $ | Freight $ | Elevator $ | Escort $ | Package total $
1 | FIN-01 | Finance | Final move | Floor 1 | Annex Floor 1 | 2026-02-07 08:00 | 2026-02-07 11:00 | 180 | Crew A | 2026-02-07 08:00 | 2026-02-07 10:15 | 135 | 1 | 2026-02-07 08:00 | 2026-02-07 08:30 | No |  |  | 3 | 0 | 540 | 900 | 375 | 0 | 1815
1 | IT-01A | IT | Stage to swing | Floor 2 | Swing Floor S | 2026-02-07 11:00 | 2026-02-07 12:30 | 90 | Crew A | 2026-02-07 10:30 | 2026-02-07 12:15 | 105 | 1 | 2026-02-07 11:00 | 2026-02-07 11:30 | No | 2026-02-07 12:30 | 2026-02-14 08:00 | 1 | 0.5 | 315 | 900 | 300 | 0 | 1515
1 | HR-01 | People Services | Final move | Floor 1 | Annex Floor 2 | 2026-02-08 08:00 | 2026-02-08 10:30 | 150 | Crew A | 2026-02-08 08:00 | 2026-02-08 09:45 | 105 | 1 | 2026-02-08 08:00 | 2026-02-08 08:30 | No |  |  | 2.5 | 0 | 450 | 900 | 300 | 0 | 1650
2 | IT-01B | IT | Final move from swing | Swing Floor S | Annex Floor 3 | 2026-02-14 08:00 | 2026-02-14 10:00 | 120 | Crew B | 2026-02-14 08:00 | 2026-02-14 09:45 | 105 | 1 | 2026-02-14 08:00 | 2026-02-14 08:30 | No | 2026-02-07 12:30 | 2026-02-14 08:00 | 2 | 0 | 360 | 900 | 300 | 0 | 1560
2 | REC-01 | Records | Vault move | Floor 2 Vault | Annex Floor 2 | 2026-02-14 10:00 | 2026-02-14 12:00 | 120 | Crew B | 2026-02-14 10:00 | 2026-02-14 11:45 | 105 | 1 | 2026-02-14 10:00 | 2026-02-14 10:30 | Yes |  |  | 2 | 0 | 360 | 900 | 300 | 240 | 1800
3 | OPS-01 | Operations | Final move | Floor 1 | Annex Floor 1 | 2026-02-21 08:00 | 2026-02-21 12:00 | 240 | Crew C | 2026-02-21 08:00 | 2026-02-21 11:45 | 225 | 2 | 2026-02-21 08:00 | 2026-02-21 09:30 | No |  |  | 4 | 0 | 720 | 1800 | 600 | 0 | 3120
3 | LEG-01 | Legal | Final move | Floor 2 | Annex Floor 3 | 2026-02-21 12:00 | 2026-02-21 13:30 | 90 | Crew C | 2026-02-21 12:15 | 2026-02-21 14:00 | 105 | 1 | 2026-02-21 12:00 | 2026-02-21 12:30 | No |  |  | 0 | 1.5 | 405 | 900 | 300 | 0 | 1605
3 | COM-01 | Communications | Final move | Floor 1 | Annex Floor 2 | 2026-02-21 13:30 | 2026-02-21 15:00 | 90 | Crew C | 2026-02-21 14:15 | 2026-02-21 16:00 | 105 | 1 | 2026-02-21 13:30 | 2026-02-21 14:00 | No |  |  | 0 | 1.5 | 405 | 900 | 300 | 0 | 1605

## Weekend Cost
Weekend | Regular labor $ | Premium labor $ | Mobilization $ | Freight $ | Elevator $ | Escort $ | Weekend subtotal $
Weekend 1 (2026-02-07) | 1170 | 135 | 700 | 2700 | 975 | 0 | 5680
Weekend 2 (2026-02-14) | 720 | 0 | 350 | 1800 | 600 | 240 | 3710
Weekend 3 (2026-02-21) | 720 | 810 | 350 | 3600 | 1200 | 0 | 6680
Revised headline estimate | [6 empty] | 16070
Valid prior-draft baseline (detail rows only) | [6 empty] | 33900
Overall change | [6 empty] | -17830
Overall change % | [6 empty] | -0.52596

## Draft Comparison
Period | Valid draft baseline $ | Revised $ | Variance $ | Interpretation
Weekend 1 | 13300 | 5680 | -7620 | Resequencing and changed rates/quantities
Weekend 2 | 7700 | 3710 | -3990 | Resequencing and changed rates/quantities
Weekend 3 | 12900 | 6680 | -6220 | Resequencing and changed rates/quantities
Total | 33900 | 16070 | -17830 | Draft headline error excluded; continuing-clock branch used

## Assumptions & Actions
Topic | Decision / assumption | Owner | Due date | Status / effect
Premium edge case | Paid 1.0h IT staging on 7 Feb continues the consecutive-hours clock; IT-01A has 0.5h premium after 4 paid hours. | Priya Demirci | 2026-01-02 | Selected branch; +$135 versus reset branch
Access windows | Building/loading 07:00–18:00; annex 08:00–19:00; dates only 7–8,14–15,21–22 Feb. | Leonie Sandoval | 2026-01-02 | Applied to every activity
Elevator | One E1 reservation at a time, 45m trip + 15m turnover; attendant billed per 30m block. | Leonie Sandoval | 2026-01-02 | Sequential reservations shown
Swing floor | IT occupies S from 7 Feb 12:30 until departure 14 Feb 08:00; no overlap. | Maren Chakraborty | 2026-01-05 | Persistent occupancy
Vault escort | REC-01 14 Feb 10:00–12:00 within Linnea Laurent window 09:00–12:00. | Linnea Laurent | 2026-01-16 | 2.00 escorted hours
Network cutover confirmation | Confirm Annex Floor 3 cutover before IT-01B final placement. | Maren Chakraborty | 2026-02-06 | Outstanding
Freight booking | Reserve 7 vehicle blocks (one each package except OPS-01 two). | Leonie Sandoval | 2026-01-02 | Outstanding
Client sign-off | Send client brief and obtain Magda Carmody acknowledgement. | Priya Demirci | 2026-01-06 | Outstanding

## Review Disposition
Comment ID | Review point | Disposition | Owner | Due
C-01 | Leonie Sandoval must have a bookable sequence on 2 January. | Incorporated: this revised workpaper is the booking basis. | Leonie Sandoval | 2026-01-02
C-02 | IT must stage on S on Weekend 1 and finish in Annex Floor 3 on Weekend 2 after network cutover. | Incorporated as IT-01A / IT-01B split with persistent S occupancy. | Maren Chakraborty | 2026-01-05
C-03 | Records vault work must use the amended escorted windows. | Incorporated: REC-01 scheduled 14 Feb within 09:00–12:00 escort. | Linnea Laurent | 2026-01-16
C-04 | Legal final destination is Annex Floor 3, not Floor 2. | Incorporated: LEG-01 destination changed to Annex Floor 3. | Priya Demirci | 2026-01-09
C-05 | Freight capacity is 600 cu ft per vehicle block. | Incorporated: OPS-01 uses two blocks; all other loads fit one. | Leonie Sandoval | 2026-01-02
C-06 | Single-elevator conflict in draft must be removed by resequencing. | Incorporated: reservations are sequential and displayed explicitly. | Leonie Sandoval | 2026-01-02
C-07 | Confirm Annex Floor 3 network cutover before IT final placement. | Outstanding action: confirm cutover slot before IT-01B. | Maren Chakraborty | 2026-02-06
C-08 | Client-ready summary required for Magda Carmody. | Incorporated: accompanying brief issued with this plan. | Priya Demirci | 2026-01-06