CROWNRIDGE HOUSING TRUST

Major Repairs Communications Roadmap

Executive decision version | Executive briefing and staged resident updates

| Version | Issue state | Issue date | Change in this version |
| --- | --- | --- | --- |
| v0.1 | Decision draft | 16 Aug 2026 | Initial integrated roadmap: status model, decision gates, late-review route and date controls. |

Executive decision

DECISION FOR RAFAEL CASTELLANOS BY FRIDAY [DECISION DEADLINE - NOT A RELEASE DATE] Record whether Zeynep Quintero may schedule a conditional executive briefing once Gate E evidence is complete; nominate the stakeholder approval and operational release authorities; and confirm how an incomplete contributor review will be handled if triggered. This decision does not authorise resident publication.

Objective: give Rafael a safe, truthful scheduling decision for the executive briefing and staged resident updates. Current position: PLANNING / decision draft. A contributor approval may miss normal review, and draft dates are being treated as commitments. No state beyond Planning is asserted until its gate record exists. Proceeding incorrectly could send unvalidated information, an unworkable delivery route or an implied commitment to residents or delivery partners.

DATE CONTROL Draft, provisional and indicative dates are planning signals only - never confirmed resident release commitments. A calendar hold, circulated draft, attendance at a briefing or an invitation is not approval. Flintridge Freight must not produce or distribute resident packs without the written Gate O release confirmation.

Scope, audience and timing logic

| Stream | Audience / use | Material / channel | Timing status |
| --- | --- | --- | --- |
| Executive briefing | Rafael and senior decision-makers; supports an explicit schedule / hold decision. | Controlled briefing pack and meeting. It covers readiness, choices, open issues and evidence only; it does not substitute for resident release approval. | After Gate E [CONDITIONAL]. A calendar entry becomes Scheduled only when Rafael's recorded decision permits Zeynep to issue it. |
| Staged resident updates | Residents; distinct external audience. Give only approved, plain-language material and access routes. | Approved copy, printed packs via Flintridge Freight and confirmed accessible / alternative access arrangements. Include an approved route for questions, feedback or concerns. | Each stage follows Gate O [CONDITIONAL]. It is Scheduled only after written release confirmation; it is Released only after distribution occurs. |

Status model - the state must travel with every date

| PLANNED | EDITORIALLY READY | APPROVED | SCHEDULED | RELEASED |
| --- | --- | --- | --- | --- |
| Work or indicative window being considered; no commitment. | Content complete for a stated review; not stakeholder-approved. | Stakeholder decision recorded with conditions; not released. | A Gate O-confirmed release window or recorded briefing booking. | Distributed / delivered; follow-up and feedback active. |

Accountability and planning assumptions

| Accountability / handoffs - Producer-director: single accountable owner; maintains the roadmap, evidence and decision log; presents status to Rafael; owns the Flintridge interface. - Rafael Castellanos: Friday scheduling decision and final escalation for overdue approval or blocked dependency. - Zeynep Quintero: may schedule the executive briefing only against the recorded Gate E condition; labels any invitation conditional. - Sigrid Zalewski / Ivo Laurent: contributor reviewers; Paloma Bhandari is stakeholder liaison, not an implied approver. | Assumptions requiring validation - A1 ¦ Producer-director at Step 0: the available information can support a clearly bounded briefing and resident draft; unknowns remain visible. - A2 ¦ Rafael by Friday [Decision]: a named stakeholder approval authority, operational release authority and resident-support lead will be recorded. - A3 ¦ Producer-director + Flintridge before G3 [Conditional]: pack lead time, proof/handoff requirements and accessible-format needs can be confirmed. - A4 ¦ Resident-support lead before G3 [Conditional]: an approved questions / feedback route and response capacity will be available. |
| --- | --- |

NORMAL PATH

Sequenced roadmap and decision gates

TIMING BASIS T0 = Friday's executive decision deadline, not a release date. Every future window below is labelled [PLANNING], [CONDITIONAL] or [SCHEDULED] as applicable. Critical path: information position -> contributor and operational review -> stakeholder approval -> controlled production / Flintridge handoff -> operational release confirmation -> resident stage and feedback.

Gate evidence is recorded before state changes. Any open material issue, missing approval or changed condition remains visible at the next gate; silence, circulation or attendance cannot close it.

| Stage / state | Timing / status | Accountable owner | Entry condition, decision output and next dependency |
| --- | --- | --- | --- |
| 0. Confirm brief and information position | Now to T0 [PLANNING] | Producer-director | Confirm objective, audiences, available information, unknowns, resident access needs, decision roles and evidence sources before anything is treated as review-ready. Output: bounded communication brief and open-issue list. |
| 1A. Build / edit executive briefing pack | Now to T0 [PLANNING] | Producer-director | Use only confirmed material from Step 0. Show choices, risks, assumptions and readiness evidence. Output: controlled draft for contributor review; no final briefing booking yet. |
| 1B. Develop staged resident messages | Now to T0 [PLANNING] | Producer-director + resident-support lead (to be named) | Prepare plain-language, accessible resident-facing draft and a questions / feedback route. Separate it from internal approval material. Output: controlled draft, not a production file. |
| 2. Contributor / subject review | Before G1 / G2 cut-offs [CONDITIONAL] | Sigrid Zalewski and Ivo Laurent; Producer-director tracks | Review the relevant draft before final approval; flag accuracy gaps and any content not validated. Output: recorded comments / confirmation. Missing review at cut-off invokes EX1, never an implied pass. |
| 3. Operational validation | Before G2 [CONDITIONAL] | Designated operational readiness lead + Producer-director | Check the proposed resident route can be delivered: support / feedback ownership, accessible alternatives, approved pack handoff requirements and Flintridge lead time. Output: evidence or a hold / revision. |
| G1 / Gate E. Editorial readiness and briefing schedule decision | At T0 / Friday [DECISION, not release] | Rafael records decision; Zeynep acts only on record | Input: controlled briefing pack, contributor status, open issues and exception record if any. PASS: editorial readiness is recorded and Rafael may let Zeynep schedule / invite conditionally. HOLD: revise, defer or escalate. This gate never approves resident release. |
| 4. Executive briefing delivery | After G1 [CONDITIONAL -> SCHEDULED only on record] | Zeynep Quintero | Use the controlled pack version and state its status in the invitation. End state: briefing held and its decisions / conditions recorded. It cannot convert resident material to Approved or Released. |
| G2. Stakeholder approval | After Steps 2-3 [CONDITIONAL] | Designated stakeholder approval authority; Paloma Bhandari is stakeholder liaison | Input: editorially ready resident content, contributor record, operational validation, open issues and accessible-format plan. PASS: named authority records approval and conditions. FAIL: hold, revise / defer, or Rafael resolves blocked dependency. |
| 5. Production preparation and controlled handoff | After G2 [CONDITIONAL] | Producer-director -> Flintridge Freight | Prepare only the recorded Approved version for chosen channels. Confirm proof, pack, lead-time and handoff needs with Flintridge. Handoff is marked 'no produce / no distribute' until Gate O written release confirmation. |
| G3 / Gate O. Operational release confirmation | Before any resident release [CONDITIONAL] | Designated operational release authority (separate from editorial readiness) | Input: G2 approval evidence, final controlled version, confirmed Flintridge readiness / lead time, accessible routes and resident questions owner. PASS: written release confirmation names scope and window; state becomes Scheduled. FAIL: hold and notify affected owners. |
| 6. Release each resident stage | Gate O-confirmed window [SCHEDULED only after written confirmation] | Operational release authority; Flintridge executes printed-pack instruction | Distribute only the released version and only for the authorised stage. End state: stage marked Released with evidence of distribution; any later stage returns to Gate O rather than inheriting approval. |
| 7. Post-release feedback and next-stage decision | After each release [CONDITIONAL] | Resident-support lead + Producer-director | Monitor questions, feedback, access issues and corrections; feed material changes into the controlled draft and re-run affected gates. End state: each stage is monitored, formally held, or closed in the decision log. |

CONTROLLED EXCEPTION AND CLOSE

Late review, date misuse and decision record

EX1 - incomplete contributor-review route

| Control point | Required action / owner | Status or schedule result |
| --- | --- | --- |
| Trigger / time-box | A contributor approval is unavailable, or the stated review cut-off passes before G1 or G2 [CONDITIONAL]. Producer-director records it immediately and escalates to Rafael before the affected gate; if unresolved by that decision point, apply HOLD. | No automatic progression; timing remains conditional. |
| Assess and contain | Producer-director and an available qualified alternative reviewer assess whether the missing contribution affects accuracy, safety, resident understanding or release readiness. Remove, hold or clearly mark every unvalidated claim / section; do not silently carry it forward. | Affected scope is held; only validated material may be considered. |
| Alternative review and authorisation | Use a delegated qualified reviewer where one is named; otherwise Rafael decides the escalation route. Proceeding under the exception needs explicit, attributable authorisation: Rafael for conditional briefing planning, plus the designated stakeholder / operational authority for any relevant downstream gate. | Exception authorisation is a recorded decision, never inferred from silence, circulation or attendance. |
| Hard stop, schedule impact and notice | If required authority or safety-critical review is unresolved, resident release stays HOLD: no final vendor production or distribution. Zeynep may retain or withdraw only a conditional briefing hold. Producer-director notifies Rafael, Zeynep, contributors, Paloma, resident-support owner and Flintridge as scope / timing requires. | Briefing may be conditionally planned; affected resident stage waits for normal controls. |
| Record and re-enter normal path | Record missing approval, reason, impact assessment, alternative review, compensating control, authorisation, conditions and changed timing. When available, complete the normal contributor review and repeat every affected G1 / G2 / G3 check before release. | Exception closes only after normal review and affected decisions are complete. |

Risks, records and correction control

| Risk | Trigger | Mitigation / accountable owner |
| --- | --- | --- |
| Missing review | Review cut-off missed / contributor unavailable. | EX1, content containment and Rafael escalation; owner: Producer-director. |
| Provisional date treated as commitment | Draft calendar, pack or vendor query is presented as a release promise. | Producer-director corrects the affected record promptly, tells Rafael, Zeynep and Flintridge / recipients as relevant, marks the old date withdrawn / Planning, resets the controlled schedule, and logs reason and impact. |
| Delivery or support not ready | Flintridge lead time, accessible route or questions capacity is not confirmed. | Operational release authority holds G3; Producer-director communicates the changed status truthfully and seeks a revised conditional window. |
| Inconsistent or unsupported audience messaging | Different copies, unvalidated claim, or unclear resident access / feedback route. | Hold affected copy; align a single controlled version and re-run the relevant review / approval gate. Owner: Producer-director. |

Control record

SOURCE OF TRUTH The Producer-director maintains this controlled roadmap and decision log. The log keeps planning assumptions, open issues and recorded authorisations distinct. For every gate, retain the decision-maker, date / timing, rationale, conditions and evidence of contributor approval, stakeholder approval or release authorisation. For any message, owner, timing or status change, record the reason and impact, then update the executive summary, roadmap and release-facing / Flintridge instruction together so no conflicting copy survives.

Current decision position

CURRENT STATE: PLANNING / DECISION DRAFT No approval or release outcome is claimed. By Friday [DECISION DEADLINE - NOT A RELEASE DATE], Rafael should record whether Zeynep may arrange only a conditional executive briefing once Gate E evidence exists, identify the approval / release authorities, and decide the exception route if it is triggered. The next concrete decision is G2 stakeholder approval [CONDITIONAL] once Steps 2-3 evidence exists - not a resident release date. Until then, resident updates and any Flintridge activity remain PLANNED or HOLD, never a confirmed release.