## Start Here
Cross-Store Inspection Model
April-May 2026 ¦ Oregon rules current as of 15 January 2026
How to use
1. Change yellow cells only: Late Oregon swaps here, then inspector and planned date decisions on Assignments.
2. Green cells calculate. A red FAIL is a mandatory issue; N/A means the Oregon-only rule does not apply to Washington.
3. Compare options below. Recommendation selects the lowest-cost feasible option; ties choose the first listed option.
4. Final Roster refreshes from the live recommendation and prints as one monthly posting page per month.
Legend
Yellow = editable decision or assumption |  | Green = formula result |  | Red = failed mandatory check
Scenario controls
Late Oregon swaps | 2 | Whole number 0+; ordinary planning band is 0-5. Higher test values are accepted.
Option comparison
Option | Projected total | Failed checks | Coverage | Feasible? | Travel miles | Decision
Option 1 ¦ Lean route | 8479.968 | 1 | Complete | INFEASIBLE | 2410.4 | Excluded
Option 2 ¦ Compliant balance | 9053.56 | 0 | Complete | FEASIBLE | 2668 | Eligible
Option 3 ¦ Long-haul cover | 10259.416 | 0 | Complete | FEASIBLE | 3164.8 | Eligible
Recommended option | Option 2 ¦ Compliant balance
Recommendation rationale
Option 2 is recommended: it is feasible, avoids the rest failure in the lean route, and costs $9,053.56 versus $10,259.42 for the longer-haul feasible cover plan. Option 1 is excluded despite its lower cost because it has 1 failed mandatory check(s).
Model rule and cost guide
Self-store | FAIL when the supervisor home store equals the inspected store.
Certified | PASS only when sourced certification is Active and the planned date is within effective/expiry dates.
Availability | PASS only when the full travel-inclusive work period fits the sourced available period.
Window | PASS only when planned date is within that store-month opening and closing date, inclusive.
Rest | Oregon only: both adjacent gaps must be at least 10.00 hours. Washington = N/A. A short gap creates shortfall-hours x regular-rate premium.
Posting | Oregon only: plan finalization must be on/before the month deadline. Washington = N/A.
Cost | Labor = work-period hours x sourced rate. Travel = sourced reimbursable miles x $/mile. Rest premium and option-level late Oregon swaps follow the Oregon brief.
Feasibility | Complete April and May coverage plus zero failed mandatory row checks. The final roster returns one record per store-month from the lowest-cost feasible option.
Sources
goldfinch_inspection_inputs.xlsx ¦ imported on Source Data
oregon_schedule_brief.pdf ¦ Gildenhall Alliance; Oregon rules current as of 15 January 2026

## Source Data
Imported source data ¦ goldfinch_inspection_inputs.xlsx
Rules cross-checked to oregon_schedule_brief.pdf (current as of 15 January 2026)
Store ID | Store | State | Team |  | Supervisor | Home store | Status | Effective | Expiry | Rate
OR-ROS | Roseburg Farm & Field | OR | 72 |  | Avery Lane | OR-ROS | Active | 2025-01-01 | 2026-12-31 | 32
OR-SAL | Salem Ag Supply | OR | 84 |  | Bianca Chen | OR-SAL | Active | 2025-03-01 | 2026-11-30 | 34
OR-BEN | Bend Tractor & Turf | OR | 68 |  | Darnell Fox | OR-BEN | Active | 2025-06-01 | 2026-10-31 | 31
OR-ONT | Ontario Equipment Depot | OR | 51 |  | Elena Ruiz | OR-ONT | Active | 2025-02-01 | 2026-12-31 | 35
OR-MED | Medford Farm Center | OR | 76 |  | Malik Brooks | WA-YAK | Active | 2025-01-01 | 2027-01-31 | 33
OR-PEN | Pendleton Ranch Supply | OR | 49
WA-YAK | Yakima Orchard & Field | WA | 63
WA-VAN | Vancouver Farm Supply | WA | 57
WA-WAL | Walla Walla Tractor Co. | WA | 46
Window Key | Month | Store ID | Opens | Closes |  | Avail Key | Supervisor | Date | Status | From | Through | Prior ends | Next begins | Travel Key | Home | Destination | One-way hrs | Miles
April¦OR-ROS | April | OR-ROS | 2026-04-06 | 2026-04-28 |  | Avery Lane¦2026-04-07 | Avery Lane | 2026-04-07 | Available | 2026-04-07 05:00 | 2026-04-07 21:00 | 2026-04-06 19:00 | 2026-04-08 07:00 | OR-ROS¦OR-ROS | OR-ROS | OR-ROS | 0 | 0
April¦OR-SAL | April | OR-SAL | 2026-04-06 | 2026-04-28 |  | Avery Lane¦2026-04-14 | Avery Lane | 2026-04-14 | Available | 2026-04-14 05:00 | 2026-04-14 21:00 | 2026-04-13 19:00 | 2026-04-15 07:00 | OR-ROS¦OR-SAL | OR-ROS | OR-SAL | 0.66667 | 36.8
April¦OR-BEN | April | OR-BEN | 2026-04-06 | 2026-04-28 |  | Avery Lane¦2026-04-21 | Avery Lane | 2026-04-21 | Available | 2026-04-21 05:00 | 2026-04-21 21:00 | 2026-04-20 19:00 | 2026-04-22 07:00 | OR-ROS¦OR-BEN | OR-ROS | OR-BEN | 2.6667 | 147.2
April¦OR-ONT | April | OR-ONT | 2026-04-06 | 2026-04-28 |  | Avery Lane¦2026-04-28 | Avery Lane | 2026-04-28 | Available | 2026-04-28 05:00 | 2026-04-28 21:00 | 2026-04-27 19:00 | 2026-04-29 07:00 | OR-ROS¦OR-ONT | OR-ROS | OR-ONT | 3.5 | 193.2
April¦OR-MED | April | OR-MED | 2026-04-06 | 2026-04-28 |  | Avery Lane¦2026-05-05 | Avery Lane | 2026-05-05 | Available | 2026-05-05 05:00 | 2026-05-05 21:00 | 2026-05-04 19:00 | 2026-05-06 07:00 | OR-ROS¦OR-MED | OR-ROS | OR-MED | 4 | 220.8
April¦OR-PEN | April | OR-PEN | 2026-04-06 | 2026-04-28 |  | Avery Lane¦2026-05-12 | Avery Lane | 2026-05-12 | Available | 2026-05-12 05:00 | 2026-05-12 21:00 | 2026-05-11 19:00 | 2026-05-13 07:00 | OR-ROS¦OR-PEN | OR-ROS | OR-PEN | 5 | 276
April¦WA-YAK | April | WA-YAK | 2026-04-06 | 2026-04-28 |  | Avery Lane¦2026-05-19 | Avery Lane | 2026-05-19 | Available | 2026-05-19 05:00 | 2026-05-19 21:00 | 2026-05-18 19:00 | 2026-05-20 07:00 | OR-ROS¦WA-YAK | OR-ROS | WA-YAK | 3 | 165.6
April¦WA-VAN | April | WA-VAN | 2026-04-06 | 2026-04-28 |  | Avery Lane¦2026-05-26 | Avery Lane | 2026-05-26 | Available | 2026-05-26 05:00 | 2026-05-26 21:00 | 2026-05-25 19:00 | 2026-05-27 07:00 | OR-ROS¦WA-VAN | OR-ROS | WA-VAN | 3.3333 | 184
April¦WA-WAL | April | WA-WAL | 2026-04-06 | 2026-04-28 |  | Bianca Chen¦2026-04-07 | Bianca Chen | 2026-04-07 | Available | 2026-04-07 05:00 | 2026-04-07 21:00 | 2026-04-06 19:00 | 2026-04-08 07:00 | OR-ROS¦WA-WAL | OR-ROS | WA-WAL | 4.3333 | 239.2
May¦OR-ROS | May | OR-ROS | 2026-05-04 | 2026-05-26 |  | Bianca Chen¦2026-04-14 | Bianca Chen | 2026-04-14 | Available | 2026-04-14 05:00 | 2026-04-14 21:00 | 2026-04-13 19:00 | 2026-04-15 07:00 | OR-SAL¦OR-ROS | OR-SAL | OR-ROS | 0.66667 | 36.8
May¦OR-SAL | May | OR-SAL | 2026-05-04 | 2026-05-26 |  | Bianca Chen¦2026-04-21 | Bianca Chen | 2026-04-21 | Available | 2026-04-21 05:00 | 2026-04-21 21:00 | 2026-04-20 19:00 | 2026-04-22 07:00 | OR-SAL¦OR-SAL | OR-SAL | OR-SAL | 0 | 0
May¦OR-BEN | May | OR-BEN | 2026-05-04 | 2026-05-26 |  | Bianca Chen¦2026-04-28 | Bianca Chen | 2026-04-28 | Available | 2026-04-28 05:00 | 2026-04-28 21:00 | 2026-04-27 19:00 | 2026-04-29 07:00 | OR-SAL¦OR-BEN | OR-SAL | OR-BEN | 2.1667 | 119.6
May¦OR-ONT | May | OR-ONT | 2026-05-04 | 2026-05-26 |  | Bianca Chen¦2026-05-05 | Bianca Chen | 2026-05-05 | Available | 2026-05-05 05:00 | 2026-05-05 21:00 | 2026-05-04 19:00 | 2026-05-06 07:00 | OR-SAL¦OR-ONT | OR-SAL | OR-ONT | 3 | 165.6
May¦OR-MED | May | OR-MED | 2026-05-04 | 2026-05-26 |  | Bianca Chen¦2026-05-12 | Bianca Chen | 2026-05-12 | Available | 2026-05-12 05:00 | 2026-05-12 21:00 | 2026-05-11 19:00 | 2026-05-13 07:00 | OR-SAL¦OR-MED | OR-SAL | OR-MED | 3.6667 | 202.4
May¦OR-PEN | May | OR-PEN | 2026-05-04 | 2026-05-26 |  | Bianca Chen¦2026-05-19 | Bianca Chen | 2026-05-19 | Available | 2026-05-19 05:00 | 2026-05-19 21:00 | 2026-05-18 19:00 | 2026-05-20 07:00 | OR-SAL¦OR-PEN | OR-SAL | OR-PEN | 4.5833 | 253
May¦WA-YAK | May | WA-YAK | 2026-05-04 | 2026-05-26 |  | Bianca Chen¦2026-05-26 | Bianca Chen | 2026-05-26 | Available | 2026-05-26 05:00 | 2026-05-26 21:00 | 2026-05-25 19:00 | 2026-05-27 07:00 | OR-SAL¦WA-YAK | OR-SAL | WA-YAK | 3.1667 | 174.8
May¦WA-VAN | May | WA-VAN | 2026-05-04 | 2026-05-26 |  | Darnell Fox¦2026-04-07 | Darnell Fox | 2026-04-07 | Available | 2026-04-07 05:00 | 2026-04-07 21:00 | 2026-04-06 19:00 | 2026-04-08 07:00 | OR-SAL¦WA-VAN | OR-SAL | WA-VAN | 3.0833 | 170.2
May¦WA-WAL | May | WA-WAL | 2026-05-04 | 2026-05-26 |  | Darnell Fox¦2026-04-14 | Darnell Fox | 2026-04-14 | Available | 2026-04-14 05:00 | 2026-04-14 21:00 | 2026-04-13 22:00 | 2026-04-15 07:00 | OR-SAL¦WA-WAL | OR-SAL | WA-WAL | 4.1667 | 230
[6 empty] | Darnell Fox¦2026-04-21 | Darnell Fox | 2026-04-21 | Available | 2026-04-21 05:00 | 2026-04-21 21:00 | 2026-04-20 19:00 | 2026-04-22 07:00 | OR-BEN¦OR-ROS | OR-BEN | OR-ROS | 2.6667 | 147.2
[6 empty] | Darnell Fox¦2026-04-28 | Darnell Fox | 2026-04-28 | Available | 2026-04-28 05:00 | 2026-04-28 21:00 | 2026-04-27 19:00 | 2026-04-29 07:00 | OR-BEN¦OR-SAL | OR-BEN | OR-SAL | 2.1667 | 119.6
[6 empty] | Darnell Fox¦2026-05-05 | Darnell Fox | 2026-05-05 | Available | 2026-05-05 05:00 | 2026-05-05 21:00 | 2026-05-04 19:00 | 2026-05-06 07:00 | OR-BEN¦OR-BEN | OR-BEN | OR-BEN | 0 | 0
[6 empty] | Darnell Fox¦2026-05-12 | Darnell Fox | 2026-05-12 | Available | 2026-05-12 05:00 | 2026-05-12 21:00 | 2026-05-11 19:00 | 2026-05-13 07:00 | OR-BEN¦OR-ONT | OR-BEN | OR-ONT | 3 | 165.6
[6 empty] | Darnell Fox¦2026-05-19 | Darnell Fox | 2026-05-19 | Available | 2026-05-19 05:00 | 2026-05-19 21:00 | 2026-05-18 19:00 | 2026-05-20 07:00 | OR-BEN¦OR-MED | OR-BEN | OR-MED | 3.5 | 193.2
[6 empty] | Darnell Fox¦2026-05-26 | Darnell Fox | 2026-05-26 | Available | 2026-05-26 05:00 | 2026-05-26 21:00 | 2026-05-25 19:00 | 2026-05-27 07:00 | OR-BEN¦OR-PEN | OR-BEN | OR-PEN | 3.25 | 179.4
[6 empty] | Elena Ruiz¦2026-04-07 | Elena Ruiz | 2026-04-07 | Available | 2026-04-07 05:00 | 2026-04-07 21:00 | 2026-04-06 19:00 | 2026-04-08 07:00 | OR-BEN¦WA-YAK | OR-BEN | WA-YAK | 4.3333 | 239.2
[6 empty] | Elena Ruiz¦2026-04-14 | Elena Ruiz | 2026-04-14 | Available | 2026-04-14 05:00 | 2026-04-14 21:00 | 2026-04-13 19:00 | 2026-04-15 07:00 | OR-BEN¦WA-VAN | OR-BEN | WA-VAN | 4.75 | 262.2
[6 empty] | Elena Ruiz¦2026-04-21 | Elena Ruiz | 2026-04-21 | Available | 2026-04-21 05:00 | 2026-04-21 21:00 | 2026-04-20 19:00 | 2026-04-22 07:00 | OR-BEN¦WA-WAL | OR-BEN | WA-WAL | 4.5833 | 253
[6 empty] | Elena Ruiz¦2026-04-28 | Elena Ruiz | 2026-04-28 | Available | 2026-04-28 05:00 | 2026-04-28 21:00 | 2026-04-27 19:00 | 2026-04-29 07:00 | OR-ONT¦OR-ROS | OR-ONT | OR-ROS | 3.5 | 193.2
[6 empty] | Elena Ruiz¦2026-05-05 | Elena Ruiz | 2026-05-05 | Available | 2026-05-05 05:00 | 2026-05-05 21:00 | 2026-05-04 19:00 | 2026-05-06 07:00 | OR-ONT¦OR-SAL | OR-ONT | OR-SAL | 3 | 165.6
[6 empty] | Elena Ruiz¦2026-05-12 | Elena Ruiz | 2026-05-12 | Available | 2026-05-12 05:00 | 2026-05-12 21:00 | 2026-05-11 19:00 | 2026-05-13 07:00 | OR-ONT¦OR-BEN | OR-ONT | OR-BEN | 3 | 165.6
[6 empty] | Elena Ruiz¦2026-05-19 | Elena Ruiz | 2026-05-19 | Available | 2026-05-19 05:00 | 2026-05-19 21:00 | 2026-05-18 19:00 | 2026-05-20 07:00 | OR-ONT¦OR-ONT | OR-ONT | OR-ONT | 0 | 0
[6 empty] | Elena Ruiz¦2026-05-26 | Elena Ruiz | 2026-05-26 | Available | 2026-05-26 05:00 | 2026-05-26 21:00 | 2026-05-25 19:00 | 2026-05-27 07:00 | OR-ONT¦OR-MED | OR-ONT | OR-MED | 5.1667 | 285.2
[6 empty] | Malik Brooks¦2026-04-07 | Malik Brooks | 2026-04-07 | Available | 2026-04-07 05:00 | 2026-04-07 21:00 | 2026-04-06 19:00 | 2026-04-08 07:00 | OR-ONT¦OR-PEN | OR-ONT | OR-PEN | 2.25 | 124.2
[6 empty] | Malik Brooks¦2026-04-14 | Malik Brooks | 2026-04-14 | Available | 2026-04-14 05:00 | 2026-04-14 21:00 | 2026-04-13 19:00 | 2026-04-15 07:00 | OR-ONT¦WA-YAK | OR-ONT | WA-YAK | 5.1667 | 285.2
[6 empty] | Malik Brooks¦2026-04-21 | Malik Brooks | 2026-04-21 | Available | 2026-04-21 05:00 | 2026-04-21 21:00 | 2026-04-20 19:00 | 2026-04-22 07:00 | OR-ONT¦WA-VAN | OR-ONT | WA-VAN | 5.8333 | 322
[6 empty] | Malik Brooks¦2026-04-28 | Malik Brooks | 2026-04-28 | Available | 2026-04-28 05:00 | 2026-04-28 21:00 | 2026-04-27 19:00 | 2026-04-29 07:00 | OR-ONT¦WA-WAL | OR-ONT | WA-WAL | 4.75 | 262.2
[6 empty] | Malik Brooks¦2026-05-05 | Malik Brooks | 2026-05-05 | Available | 2026-05-05 05:00 | 2026-05-05 21:00 | 2026-05-04 19:00 | 2026-05-06 07:00 | WA-YAK¦OR-ROS | WA-YAK | OR-ROS | 3 | 165.6
[6 empty] | Malik Brooks¦2026-05-12 | Malik Brooks | 2026-05-12 | Available | 2026-05-12 05:00 | 2026-05-12 21:00 | 2026-05-11 19:00 | 2026-05-13 07:00 | WA-YAK¦OR-SAL | WA-YAK | OR-SAL | 3.1667 | 174.8
[6 empty] | Malik Brooks¦2026-05-19 | Malik Brooks | 2026-05-19 | Available | 2026-05-19 05:00 | 2026-05-19 21:00 | 2026-05-18 19:00 | 2026-05-20 07:00 | WA-YAK¦OR-BEN | WA-YAK | OR-BEN | 4.3333 | 239.2
[6 empty] | Malik Brooks¦2026-05-26 | Malik Brooks | 2026-05-26 | Available | 2026-05-26 05:00 | 2026-05-26 21:00 | 2026-05-25 19:00 | 2026-05-27 07:00 | WA-YAK¦OR-ONT | WA-YAK | OR-ONT | 5.1667 | 285.2
[14 empty] | WA-YAK¦OR-MED | WA-YAK | OR-MED | 5 | 276
[14 empty] | WA-YAK¦OR-PEN | WA-YAK | OR-PEN | 4.3333 | 239.2
[14 empty] | WA-YAK¦WA-YAK | WA-YAK | WA-YAK | 0 | 0
[14 empty] | WA-YAK¦WA-VAN | WA-YAK | WA-VAN | 3.25 | 179.4
[14 empty] | WA-YAK¦WA-WAL | WA-YAK | WA-WAL | 2.8333 | 156.4
Rule | Value | Unit | Note |  | Planning constants
Employer Oregon headcount | 640 | workers | Oregon retail scope met at 500+ |  | Inspection hours | 4
Inspection duration | 4 | hours | field inspection time |  | Mileage rate | 0.67
Mileage reimbursement | 0.67 | $/mile | reimbursable round-trip miles |  | Rest hours | 10
Rest interval | 10 | hours | both adjacent gaps; boundary passes |  | Late swap rate | 75
Late Oregon swap charge | 75 | $/swap | per recorded late Oregon schedule swap |  | April deadline | 2026-03-01
April posting deadline | 2026-03-01 | date | Oregon April posting |  | May deadline | 2026-04-01
May posting deadline | 2026-04-01 | date | Oregon May posting |  | Plan final date | 2026-02-15
Plan finalization date | 2026-02-15 | date | planned assignment timing

## Assignments
Candidate assignment decisions and live checks
Edit yellow inspector/date cells. All green/white results are locked formulas; failed mandatory tests flag red.
Option | Month | Store ID | Store | State | Window opens | Window closes | Inspector | Planned date | Home store | Cert status | Cert expiry | One-way hrs | Miles | Work begins | Work ends | Availability | Window | Self-store | Certified | Rest | Posting | Labor | Travel | Rest premium | Late change | Projected total | Failed checks | Row feasible | Record key
Option 1 ¦ Lean route | April | OR-ROS | Roseburg Farm & Field | OR | 2026-04-06 | 2026-04-28 | Bianca Chen | 2026-04-07 | OR-SAL | Active | 2026-11-30 | 0.66667 | 36.8 | 2026-04-07 08:20 | 2026-04-07 14:20 | PASS | PASS | PASS | PASS | PASS | PASS | 204 | 24.656 | 0 | 0 | 228.656 | 0 | PASS | Option 1 ¦ Lean route¦April¦OR-ROS
Option 1 ¦ Lean route | April | OR-SAL | Salem Ag Supply | OR | 2026-04-06 | 2026-04-28 | Avery Lane | 2026-04-21 | OR-ROS | Active | 2026-12-31 | 0.66667 | 36.8 | 2026-04-21 08:20 | 2026-04-21 14:20 | PASS | PASS | PASS | PASS | PASS | PASS | 192 | 24.656 | 0 | 0 | 216.656 | 0 | PASS | Option 1 ¦ Lean route¦April¦OR-SAL
Option 1 ¦ Lean route | April | OR-BEN | Bend Tractor & Turf | OR | 2026-04-06 | 2026-04-28 | Bianca Chen | 2026-04-28 | OR-SAL | Active | 2026-11-30 | 2.1667 | 119.6 | 2026-04-28 06:50 | 2026-04-28 17:20 | PASS | PASS | PASS | PASS | PASS | PASS | 357 | 80.132 | 0 | 0 | 437.132 | 0 | PASS | Option 1 ¦ Lean route¦April¦OR-BEN
Option 1 ¦ Lean route | April | OR-ONT | Ontario Equipment Depot | OR | 2026-04-06 | 2026-04-28 | Darnell Fox | 2026-04-14 | OR-BEN | Active | 2026-10-31 | 3 | 165.6 | 2026-04-14 06:00 | 2026-04-14 19:00 | PASS | PASS | PASS | PASS | FAIL | PASS | 403 | 110.952 | 62 | 0 | 575.952 | 1 | FAIL | Option 1 ¦ Lean route¦April¦OR-ONT
Option 1 ¦ Lean route | April | OR-MED | Medford Farm Center | OR | 2026-04-06 | 2026-04-28 | Avery Lane | 2026-04-07 | OR-ROS | Active | 2026-12-31 | 4 | 220.8 | 2026-04-07 05:00 | 2026-04-07 21:00 | PASS | PASS | PASS | PASS | PASS | PASS | 512 | 147.936 | 0 | 0 | 659.936 | 0 | PASS | Option 1 ¦ Lean route¦April¦OR-MED
Option 1 ¦ Lean route | April | OR-PEN | Pendleton Ranch Supply | OR | 2026-04-06 | 2026-04-28 | Elena Ruiz | 2026-04-21 | OR-ONT | Active | 2026-12-31 | 2.25 | 124.2 | 2026-04-21 06:45 | 2026-04-21 17:30 | PASS | PASS | PASS | PASS | PASS | PASS | 376.25 | 83.214 | 0 | 0 | 459.464 | 0 | PASS | Option 1 ¦ Lean route¦April¦OR-PEN
Option 1 ¦ Lean route | April | WA-YAK | Yakima Orchard & Field | WA | 2026-04-06 | 2026-04-28 | Avery Lane | 2026-04-14 | OR-ROS | Active | 2026-12-31 | 3 | 165.6 | 2026-04-14 06:00 | 2026-04-14 19:00 | PASS | PASS | PASS | PASS | N/A | N/A | 416 | 110.952 | 0 | 0 | 526.952 | 0 | PASS | Option 1 ¦ Lean route¦April¦WA-YAK
Option 1 ¦ Lean route | April | WA-VAN | Vancouver Farm Supply | WA | 2026-04-06 | 2026-04-28 | Malik Brooks | 2026-04-28 | WA-YAK | Active | 2027-01-31 | 3.25 | 179.4 | 2026-04-28 05:45 | 2026-04-28 19:30 | PASS | PASS | PASS | PASS | N/A | N/A | 453.75 | 120.198 | 0 | 0 | 573.948 | 0 | PASS | Option 1 ¦ Lean route¦April¦WA-VAN
Option 1 ¦ Lean route | April | WA-WAL | Walla Walla Tractor Co. | WA | 2026-04-06 | 2026-04-28 | Malik Brooks | 2026-04-21 | WA-YAK | Active | 2027-01-31 | 2.8333 | 156.4 | 2026-04-21 06:10 | 2026-04-21 18:40 | PASS | PASS | PASS | PASS | N/A | N/A | 412.5 | 104.788 | 0 | 0 | 517.288 | 0 | PASS | Option 1 ¦ Lean route¦April¦WA-WAL
Option 1 ¦ Lean route | May | OR-ROS | Roseburg Farm & Field | OR | 2026-05-04 | 2026-05-26 | Bianca Chen | 2026-05-05 | OR-SAL | Active | 2026-11-30 | 0.66667 | 36.8 | 2026-05-05 08:20 | 2026-05-05 14:20 | PASS | PASS | PASS | PASS | PASS | PASS | 204 | 24.656 | 0 | 0 | 228.656 | 0 | PASS | Option 1 ¦ Lean route¦May¦OR-ROS
Option 1 ¦ Lean route | May | OR-SAL | Salem Ag Supply | OR | 2026-05-04 | 2026-05-26 | Avery Lane | 2026-05-12 | OR-ROS | Active | 2026-12-31 | 0.66667 | 36.8 | 2026-05-12 08:20 | 2026-05-12 14:20 | PASS | PASS | PASS | PASS | PASS | PASS | 192 | 24.656 | 0 | 0 | 216.656 | 0 | PASS | Option 1 ¦ Lean route¦May¦OR-SAL
Option 1 ¦ Lean route | May | OR-BEN | Bend Tractor & Turf | OR | 2026-05-04 | 2026-05-26 | Bianca Chen | 2026-05-19 | OR-SAL | Active | 2026-11-30 | 2.1667 | 119.6 | 2026-05-19 06:50 | 2026-05-19 17:20 | PASS | PASS | PASS | PASS | PASS | PASS | 357 | 80.132 | 0 | 0 | 437.132 | 0 | PASS | Option 1 ¦ Lean route¦May¦OR-BEN
Option 1 ¦ Lean route | May | OR-ONT | Ontario Equipment Depot | OR | 2026-05-04 | 2026-05-26 | Darnell Fox | 2026-05-26 | OR-BEN | Active | 2026-10-31 | 3 | 165.6 | 2026-05-26 06:00 | 2026-05-26 19:00 | PASS | PASS | PASS | PASS | PASS | PASS | 403 | 110.952 | 0 | 0 | 513.952 | 0 | PASS | Option 1 ¦ Lean route¦May¦OR-ONT
Option 1 ¦ Lean route | May | OR-MED | Medford Farm Center | OR | 2026-05-04 | 2026-05-26 | Avery Lane | 2026-05-05 | OR-ROS | Active | 2026-12-31 | 4 | 220.8 | 2026-05-05 05:00 | 2026-05-05 21:00 | PASS | PASS | PASS | PASS | PASS | PASS | 512 | 147.936 | 0 | 0 | 659.936 | 0 | PASS | Option 1 ¦ Lean route¦May¦OR-MED
Option 1 ¦ Lean route | May | OR-PEN | Pendleton Ranch Supply | OR | 2026-05-04 | 2026-05-26 | Elena Ruiz | 2026-05-19 | OR-ONT | Active | 2026-12-31 | 2.25 | 124.2 | 2026-05-19 06:45 | 2026-05-19 17:30 | PASS | PASS | PASS | PASS | PASS | PASS | 376.25 | 83.214 | 0 | 0 | 459.464 | 0 | PASS | Option 1 ¦ Lean route¦May¦OR-PEN
Option 1 ¦ Lean route | May | WA-YAK | Yakima Orchard & Field | WA | 2026-05-04 | 2026-05-26 | Avery Lane | 2026-05-12 | OR-ROS | Active | 2026-12-31 | 3 | 165.6 | 2026-05-12 06:00 | 2026-05-12 19:00 | PASS | PASS | PASS | PASS | N/A | N/A | 416 | 110.952 | 0 | 0 | 526.952 | 0 | PASS | Option 1 ¦ Lean route¦May¦WA-YAK
Option 1 ¦ Lean route | May | WA-VAN | Vancouver Farm Supply | WA | 2026-05-04 | 2026-05-26 | Malik Brooks | 2026-05-26 | WA-YAK | Active | 2027-01-31 | 3.25 | 179.4 | 2026-05-26 05:45 | 2026-05-26 19:30 | PASS | PASS | PASS | PASS | N/A | N/A | 453.75 | 120.198 | 0 | 0 | 573.948 | 0 | PASS | Option 1 ¦ Lean route¦May¦WA-VAN
Option 1 ¦ Lean route | May | WA-WAL | Walla Walla Tractor Co. | WA | 2026-05-04 | 2026-05-26 | Malik Brooks | 2026-05-19 | WA-YAK | Active | 2027-01-31 | 2.8333 | 156.4 | 2026-05-19 06:10 | 2026-05-19 18:40 | PASS | PASS | PASS | PASS | N/A | N/A | 412.5 | 104.788 | 0 | 0 | 517.288 | 0 | PASS | Option 1 ¦ Lean route¦May¦WA-WAL
Option 2 ¦ Compliant balance | April | OR-ROS | Roseburg Farm & Field | OR | 2026-04-06 | 2026-04-28 | Bianca Chen | 2026-04-07 | OR-SAL | Active | 2026-11-30 | 0.66667 | 36.8 | 2026-04-07 08:20 | 2026-04-07 14:20 | PASS | PASS | PASS | PASS | PASS | PASS | 204 | 24.656 | 0 | 0 | 228.656 | 0 | PASS | Option 2 ¦ Compliant balance¦April¦OR-ROS
Option 2 ¦ Compliant balance | April | OR-SAL | Salem Ag Supply | OR | 2026-04-06 | 2026-04-28 | Darnell Fox | 2026-04-21 | OR-BEN | Active | 2026-10-31 | 2.1667 | 119.6 | 2026-04-21 06:50 | 2026-04-21 17:20 | PASS | PASS | PASS | PASS | PASS | PASS | 325.5 | 80.132 | 0 | 0 | 405.632 | 0 | PASS | Option 2 ¦ Compliant balance¦April¦OR-SAL
Option 2 ¦ Compliant balance | April | OR-BEN | Bend Tractor & Turf | OR | 2026-04-06 | 2026-04-28 | Elena Ruiz | 2026-04-28 | OR-ONT | Active | 2026-12-31 | 3 | 165.6 | 2026-04-28 06:00 | 2026-04-28 19:00 | PASS | PASS | PASS | PASS | PASS | PASS | 455 | 110.952 | 0 | 0 | 565.952 | 0 | PASS | Option 2 ¦ Compliant balance¦April¦OR-BEN
Option 2 ¦ Compliant balance | April | OR-ONT | Ontario Equipment Depot | OR | 2026-04-06 | 2026-04-28 | Darnell Fox | 2026-04-07 | OR-BEN | Active | 2026-10-31 | 3 | 165.6 | 2026-04-07 06:00 | 2026-04-07 19:00 | PASS | PASS | PASS | PASS | PASS | PASS | 403 | 110.952 | 0 | 0 | 513.952 | 0 | PASS | Option 2 ¦ Compliant balance¦April¦OR-ONT
Option 2 ¦ Compliant balance | April | OR-MED | Medford Farm Center | OR | 2026-04-06 | 2026-04-28 | Avery Lane | 2026-04-14 | OR-ROS | Active | 2026-12-31 | 4 | 220.8 | 2026-04-14 05:00 | 2026-04-14 21:00 | PASS | PASS | PASS | PASS | PASS | PASS | 512 | 147.936 | 0 | 0 | 659.936 | 0 | PASS | Option 2 ¦ Compliant balance¦April¦OR-MED
Option 2 ¦ Compliant balance | April | OR-PEN | Pendleton Ranch Supply | OR | 2026-04-06 | 2026-04-28 | Elena Ruiz | 2026-04-21 | OR-ONT | Active | 2026-12-31 | 2.25 | 124.2 | 2026-04-21 06:45 | 2026-04-21 17:30 | PASS | PASS | PASS | PASS | PASS | PASS | 376.25 | 83.214 | 0 | 0 | 459.464 | 0 | PASS | Option 2 ¦ Compliant balance¦April¦OR-PEN
Option 2 ¦ Compliant balance | April | WA-YAK | Yakima Orchard & Field | WA | 2026-04-06 | 2026-04-28 | Avery Lane | 2026-04-14 | OR-ROS | Active | 2026-12-31 | 3 | 165.6 | 2026-04-14 06:00 | 2026-04-14 19:00 | PASS | PASS | PASS | PASS | N/A | N/A | 416 | 110.952 | 0 | 0 | 526.952 | 0 | PASS | Option 2 ¦ Compliant balance¦April¦WA-YAK
Option 2 ¦ Compliant balance | April | WA-VAN | Vancouver Farm Supply | WA | 2026-04-06 | 2026-04-28 | Malik Brooks | 2026-04-28 | WA-YAK | Active | 2027-01-31 | 3.25 | 179.4 | 2026-04-28 05:45 | 2026-04-28 19:30 | PASS | PASS | PASS | PASS | N/A | N/A | 453.75 | 120.198 | 0 | 0 | 573.948 | 0 | PASS | Option 2 ¦ Compliant balance¦April¦WA-VAN
Option 2 ¦ Compliant balance | April | WA-WAL | Walla Walla Tractor Co. | WA | 2026-04-06 | 2026-04-28 | Malik Brooks | 2026-04-21 | WA-YAK | Active | 2027-01-31 | 2.8333 | 156.4 | 2026-04-21 06:10 | 2026-04-21 18:40 | PASS | PASS | PASS | PASS | N/A | N/A | 412.5 | 104.788 | 0 | 0 | 517.288 | 0 | PASS | Option 2 ¦ Compliant balance¦April¦WA-WAL
Option 2 ¦ Compliant balance | May | OR-ROS | Roseburg Farm & Field | OR | 2026-05-04 | 2026-05-26 | Bianca Chen | 2026-05-05 | OR-SAL | Active | 2026-11-30 | 0.66667 | 36.8 | 2026-05-05 08:20 | 2026-05-05 14:20 | PASS | PASS | PASS | PASS | PASS | PASS | 204 | 24.656 | 0 | 0 | 228.656 | 0 | PASS | Option 2 ¦ Compliant balance¦May¦OR-ROS
Option 2 ¦ Compliant balance | May | OR-SAL | Salem Ag Supply | OR | 2026-05-04 | 2026-05-26 | Darnell Fox | 2026-05-12 | OR-BEN | Active | 2026-10-31 | 2.1667 | 119.6 | 2026-05-12 06:50 | 2026-05-12 17:20 | PASS | PASS | PASS | PASS | PASS | PASS | 325.5 | 80.132 | 0 | 0 | 405.632 | 0 | PASS | Option 2 ¦ Compliant balance¦May¦OR-SAL
Option 2 ¦ Compliant balance | May | OR-BEN | Bend Tractor & Turf | OR | 2026-05-04 | 2026-05-26 | Elena Ruiz | 2026-05-19 | OR-ONT | Active | 2026-12-31 | 3 | 165.6 | 2026-05-19 06:00 | 2026-05-19 19:00 | PASS | PASS | PASS | PASS | PASS | PASS | 455 | 110.952 | 0 | 0 | 565.952 | 0 | PASS | Option 2 ¦ Compliant balance¦May¦OR-BEN
Option 2 ¦ Compliant balance | May | OR-ONT | Ontario Equipment Depot | OR | 2026-05-04 | 2026-05-26 | Darnell Fox | 2026-05-26 | OR-BEN | Active | 2026-10-31 | 3 | 165.6 | 2026-05-26 06:00 | 2026-05-26 19:00 | PASS | PASS | PASS | PASS | PASS | PASS | 403 | 110.952 | 0 | 0 | 513.952 | 0 | PASS | Option 2 ¦ Compliant balance¦May¦OR-ONT
Option 2 ¦ Compliant balance | May | OR-MED | Medford Farm Center | OR | 2026-05-04 | 2026-05-26 | Avery Lane | 2026-05-05 | OR-ROS | Active | 2026-12-31 | 4 | 220.8 | 2026-05-05 05:00 | 2026-05-05 21:00 | PASS | PASS | PASS | PASS | PASS | PASS | 512 | 147.936 | 0 | 0 | 659.936 | 0 | PASS | Option 2 ¦ Compliant balance¦May¦OR-MED
Option 2 ¦ Compliant balance | May | OR-PEN | Pendleton Ranch Supply | OR | 2026-05-04 | 2026-05-26 | Elena Ruiz | 2026-05-19 | OR-ONT | Active | 2026-12-31 | 2.25 | 124.2 | 2026-05-19 06:45 | 2026-05-19 17:30 | PASS | PASS | PASS | PASS | PASS | PASS | 376.25 | 83.214 | 0 | 0 | 459.464 | 0 | PASS | Option 2 ¦ Compliant balance¦May¦OR-PEN
Option 2 ¦ Compliant balance | May | WA-YAK | Yakima Orchard & Field | WA | 2026-05-04 | 2026-05-26 | Avery Lane | 2026-05-12 | OR-ROS | Active | 2026-12-31 | 3 | 165.6 | 2026-05-12 06:00 | 2026-05-12 19:00 | PASS | PASS | PASS | PASS | N/A | N/A | 416 | 110.952 | 0 | 0 | 526.952 | 0 | PASS | Option 2 ¦ Compliant balance¦May¦WA-YAK
Option 2 ¦ Compliant balance | May | WA-VAN | Vancouver Farm Supply | WA | 2026-05-04 | 2026-05-26 | Malik Brooks | 2026-05-26 | WA-YAK | Active | 2027-01-31 | 3.25 | 179.4 | 2026-05-26 05:45 | 2026-05-26 19:30 | PASS | PASS | PASS | PASS | N/A | N/A | 453.75 | 120.198 | 0 | 0 | 573.948 | 0 | PASS | Option 2 ¦ Compliant balance¦May¦WA-VAN
Option 2 ¦ Compliant balance | May | WA-WAL | Walla Walla Tractor Co. | WA | 2026-05-04 | 2026-05-26 | Malik Brooks | 2026-05-19 | WA-YAK | Active | 2027-01-31 | 2.8333 | 156.4 | 2026-05-19 06:10 | 2026-05-19 18:40 | PASS | PASS | PASS | PASS | N/A | N/A | 412.5 | 104.788 | 0 | 0 | 517.288 | 0 | PASS | Option 2 ¦ Compliant balance¦May¦WA-WAL
Option 3 ¦ Long-haul cover | April | OR-ROS | Roseburg Farm & Field | OR | 2026-04-06 | 2026-04-28 | Elena Ruiz | 2026-04-07 | OR-ONT | Active | 2026-12-31 | 3.5 | 193.2 | 2026-04-07 05:30 | 2026-04-07 20:00 | PASS | PASS | PASS | PASS | PASS | PASS | 507.5 | 129.444 | 0 | 0 | 636.944 | 0 | PASS | Option 3 ¦ Long-haul cover¦April¦OR-ROS
Option 3 ¦ Long-haul cover | April | OR-SAL | Salem Ag Supply | OR | 2026-04-06 | 2026-04-28 | Malik Brooks | 2026-04-21 | WA-YAK | Active | 2027-01-31 | 3.1667 | 174.8 | 2026-04-21 05:50 | 2026-04-21 19:20 | PASS | PASS | PASS | PASS | PASS | PASS | 445.5 | 117.116 | 0 | 0 | 562.616 | 0 | PASS | Option 3 ¦ Long-haul cover¦April¦OR-SAL
Option 3 ¦ Long-haul cover | April | OR-BEN | Bend Tractor & Turf | OR | 2026-04-06 | 2026-04-28 | Bianca Chen | 2026-04-28 | OR-SAL | Active | 2026-11-30 | 2.1667 | 119.6 | 2026-04-28 06:50 | 2026-04-28 17:20 | PASS | PASS | PASS | PASS | PASS | PASS | 357 | 80.132 | 0 | 0 | 437.132 | 0 | PASS | Option 3 ¦ Long-haul cover¦April¦OR-BEN
Option 3 ¦ Long-haul cover | April | OR-ONT | Ontario Equipment Depot | OR | 2026-04-06 | 2026-04-28 | Avery Lane | 2026-04-07 | OR-ROS | Active | 2026-12-31 | 3.5 | 193.2 | 2026-04-07 05:30 | 2026-04-07 20:00 | PASS | PASS | PASS | PASS | PASS | PASS | 464 | 129.444 | 0 | 0 | 593.444 | 0 | PASS | Option 3 ¦ Long-haul cover¦April¦OR-ONT
Option 3 ¦ Long-haul cover | April | OR-MED | Medford Farm Center | OR | 2026-04-06 | 2026-04-28 | Avery Lane | 2026-04-14 | OR-ROS | Active | 2026-12-31 | 4 | 220.8 | 2026-04-14 05:00 | 2026-04-14 21:00 | PASS | PASS | PASS | PASS | PASS | PASS | 512 | 147.936 | 0 | 0 | 659.936 | 0 | PASS | Option 3 ¦ Long-haul cover¦April¦OR-MED
Option 3 ¦ Long-haul cover | April | OR-PEN | Pendleton Ranch Supply | OR | 2026-04-06 | 2026-04-28 | Darnell Fox | 2026-04-21 | OR-BEN | Active | 2026-10-31 | 3.25 | 179.4 | 2026-04-21 05:45 | 2026-04-21 19:30 | PASS | PASS | PASS | PASS | PASS | PASS | 426.25 | 120.198 | 0 | 0 | 546.448 | 0 | PASS | Option 3 ¦ Long-haul cover¦April¦OR-PEN
Option 3 ¦ Long-haul cover | April | WA-YAK | Yakima Orchard & Field | WA | 2026-04-06 | 2026-04-28 | Avery Lane | 2026-04-14 | OR-ROS | Active | 2026-12-31 | 3 | 165.6 | 2026-04-14 06:00 | 2026-04-14 19:00 | PASS | PASS | PASS | PASS | N/A | N/A | 416 | 110.952 | 0 | 0 | 526.952 | 0 | PASS | Option 3 ¦ Long-haul cover¦April¦WA-YAK
Option 3 ¦ Long-haul cover | April | WA-VAN | Vancouver Farm Supply | WA | 2026-04-06 | 2026-04-28 | Malik Brooks | 2026-04-28 | WA-YAK | Active | 2027-01-31 | 3.25 | 179.4 | 2026-04-28 05:45 | 2026-04-28 19:30 | PASS | PASS | PASS | PASS | N/A | N/A | 453.75 | 120.198 | 0 | 0 | 573.948 | 0 | PASS | Option 3 ¦ Long-haul cover¦April¦WA-VAN
Option 3 ¦ Long-haul cover | April | WA-WAL | Walla Walla Tractor Co. | WA | 2026-04-06 | 2026-04-28 | Malik Brooks | 2026-04-21 | WA-YAK | Active | 2027-01-31 | 2.8333 | 156.4 | 2026-04-21 06:10 | 2026-04-21 18:40 | PASS | PASS | PASS | PASS | N/A | N/A | 412.5 | 104.788 | 0 | 0 | 517.288 | 0 | PASS | Option 3 ¦ Long-haul cover¦April¦WA-WAL
Option 3 ¦ Long-haul cover | May | OR-ROS | Roseburg Farm & Field | OR | 2026-05-04 | 2026-05-26 | Elena Ruiz | 2026-05-05 | OR-ONT | Active | 2026-12-31 | 3.5 | 193.2 | 2026-05-05 05:30 | 2026-05-05 20:00 | PASS | PASS | PASS | PASS | PASS | PASS | 507.5 | 129.444 | 0 | 0 | 636.944 | 0 | PASS | Option 3 ¦ Long-haul cover¦May¦OR-ROS
Option 3 ¦ Long-haul cover | May | OR-SAL | Salem Ag Supply | OR | 2026-05-04 | 2026-05-26 | Malik Brooks | 2026-05-12 | WA-YAK | Active | 2027-01-31 | 3.1667 | 174.8 | 2026-05-12 05:50 | 2026-05-12 19:20 | PASS | PASS | PASS | PASS | PASS | PASS | 445.5 | 117.116 | 0 | 0 | 562.616 | 0 | PASS | Option 3 ¦ Long-haul cover¦May¦OR-SAL
Option 3 ¦ Long-haul cover | May | OR-BEN | Bend Tractor & Turf | OR | 2026-05-04 | 2026-05-26 | Bianca Chen | 2026-05-19 | OR-SAL | Active | 2026-11-30 | 2.1667 | 119.6 | 2026-05-19 06:50 | 2026-05-19 17:20 | PASS | PASS | PASS | PASS | PASS | PASS | 357 | 80.132 | 0 | 0 | 437.132 | 0 | PASS | Option 3 ¦ Long-haul cover¦May¦OR-BEN
Option 3 ¦ Long-haul cover | May | OR-ONT | Ontario Equipment Depot | OR | 2026-05-04 | 2026-05-26 | Avery Lane | 2026-05-26 | OR-ROS | Active | 2026-12-31 | 3.5 | 193.2 | 2026-05-26 05:30 | 2026-05-26 20:00 | PASS | PASS | PASS | PASS | PASS | PASS | 464 | 129.444 | 0 | 0 | 593.444 | 0 | PASS | Option 3 ¦ Long-haul cover¦May¦OR-ONT
Option 3 ¦ Long-haul cover | May | OR-MED | Medford Farm Center | OR | 2026-05-04 | 2026-05-26 | Avery Lane | 2026-05-05 | OR-ROS | Active | 2026-12-31 | 4 | 220.8 | 2026-05-05 05:00 | 2026-05-05 21:00 | PASS | PASS | PASS | PASS | PASS | PASS | 512 | 147.936 | 0 | 0 | 659.936 | 0 | PASS | Option 3 ¦ Long-haul cover¦May¦OR-MED
Option 3 ¦ Long-haul cover | May | OR-PEN | Pendleton Ranch Supply | OR | 2026-05-04 | 2026-05-26 | Darnell Fox | 2026-05-19 | OR-BEN | Active | 2026-10-31 | 3.25 | 179.4 | 2026-05-19 05:45 | 2026-05-19 19:30 | PASS | PASS | PASS | PASS | PASS | PASS | 426.25 | 120.198 | 0 | 0 | 546.448 | 0 | PASS | Option 3 ¦ Long-haul cover¦May¦OR-PEN
Option 3 ¦ Long-haul cover | May | WA-YAK | Yakima Orchard & Field | WA | 2026-05-04 | 2026-05-26 | Avery Lane | 2026-05-12 | OR-ROS | Active | 2026-12-31 | 3 | 165.6 | 2026-05-12 06:00 | 2026-05-12 19:00 | PASS | PASS | PASS | PASS | N/A | N/A | 416 | 110.952 | 0 | 0 | 526.952 | 0 | PASS | Option 3 ¦ Long-haul cover¦May¦WA-YAK
Option 3 ¦ Long-haul cover | May | WA-VAN | Vancouver Farm Supply | WA | 2026-05-04 | 2026-05-26 | Malik Brooks | 2026-05-26 | WA-YAK | Active | 2027-01-31 | 3.25 | 179.4 | 2026-05-26 05:45 | 2026-05-26 19:30 | PASS | PASS | PASS | PASS | N/A | N/A | 453.75 | 120.198 | 0 | 0 | 573.948 | 0 | PASS | Option 3 ¦ Long-haul cover¦May¦WA-VAN
Option 3 ¦ Long-haul cover | May | WA-WAL | Walla Walla Tractor Co. | WA | 2026-05-04 | 2026-05-26 | Malik Brooks | 2026-05-19 | WA-YAK | Active | 2027-01-31 | 2.8333 | 156.4 | 2026-05-19 06:10 | 2026-05-19 18:40 | PASS | PASS | PASS | PASS | N/A | N/A | 412.5 | 104.788 | 0 | 0 | 517.288 | 0 | PASS | Option 3 ¦ Long-haul cover¦May¦WA-WAL
Formulas:
Window opens = VLOOKUP([Month]&"¦"&[Store ID],'Source Data'!$A17:E34,4,FALSE())
Window closes = VLOOKUP([Month]&"¦"&[Store ID],'Source Data'!$A17:E34,5,FALSE())
Cert expiry = VLOOKUP([Inspector],'Source Data'!$F5:K9,5,FALSE())
Work begins = [Planned date]+TIME(9,0,0)-[One-way hrs]/24
Work ends = [Planned date]+TIME(9,0,0)+('Source Data'!$G92+([One-way hrs]*2))/24

## Final Roster
Goldfinch Agricultural ¦ Final Inspection Roster
APRIL 2026
Oregon posting deadline: 1 March 2026 ¦ Selected by live model recommendation
Recommended option | Option 2 ¦ Compliant balance
Store ID | Store | State | Assigned supervisor | Planned inspection date | Work period | Status
OR-ROS | Roseburg Farm & Field | OR | Bianca Chen | 2026-04-07 | 4/7 8:20 AM - 2:20 PM | PASS
OR-SAL | Salem Ag Supply | OR | Darnell Fox | 2026-04-21 | 4/21 6:50 AM - 5:20 PM | PASS
OR-BEN | Bend Tractor & Turf | OR | Elena Ruiz | 2026-04-28 | 4/28 6:00 AM - 7:00 PM | PASS
OR-ONT | Ontario Equipment Depot | OR | Darnell Fox | 2026-04-07 | 4/7 6:00 AM - 7:00 PM | PASS
OR-MED | Medford Farm Center | OR | Avery Lane | 2026-04-14 | 4/14 5:00 AM - 9:00 PM | PASS
OR-PEN | Pendleton Ranch Supply | OR | Elena Ruiz | 2026-04-21 | 4/21 6:45 AM - 5:30 PM | PASS
WA-YAK | Yakima Orchard & Field | WA | Avery Lane | 2026-04-14 | 4/14 6:00 AM - 7:00 PM | PASS
WA-VAN | Vancouver Farm Supply | WA | Malik Brooks | 2026-04-28 | 4/28 5:45 AM - 7:30 PM | PASS
WA-WAL | Walla Walla Tractor Co. | WA | Malik Brooks | 2026-04-21 | 4/21 6:10 AM - 6:40 PM | PASS
Store teams: prepare recalled-product records and a clear display route before the listed work period.
Goldfinch Agricultural ¦ Final Inspection Roster
MAY 2026
Oregon posting deadline: 1 April 2026 ¦ Selected by live model recommendation
Recommended option | Option 2 ¦ Compliant balance
Store ID | Store | State | Assigned supervisor | Planned inspection date | Work period | Status
OR-ROS | Roseburg Farm & Field | OR | Bianca Chen | 2026-05-05 | 5/5 8:20 AM - 2:20 PM | PASS
OR-SAL | Salem Ag Supply | OR | Darnell Fox | 2026-05-12 | 5/12 6:50 AM - 5:20 PM | PASS
OR-BEN | Bend Tractor & Turf | OR | Elena Ruiz | 2026-05-19 | 5/19 6:00 AM - 7:00 PM | PASS
OR-ONT | Ontario Equipment Depot | OR | Darnell Fox | 2026-05-26 | 5/26 6:00 AM - 7:00 PM | PASS
OR-MED | Medford Farm Center | OR | Avery Lane | 2026-05-05 | 5/5 5:00 AM - 9:00 PM | PASS
OR-PEN | Pendleton Ranch Supply | OR | Elena Ruiz | 2026-05-19 | 5/19 6:45 AM - 5:30 PM | PASS
WA-YAK | Yakima Orchard & Field | WA | Avery Lane | 2026-05-12 | 5/12 6:00 AM - 7:00 PM | PASS
WA-VAN | Vancouver Farm Supply | WA | Malik Brooks | 2026-05-26 | 5/26 5:45 AM - 7:30 PM | PASS
WA-WAL | Walla Walla Tractor Co. | WA | Malik Brooks | 2026-05-19 | 5/19 6:10 AM - 6:40 PM | PASS
Store teams: prepare recalled-product records and a clear display route before the listed work period.
Formulas:
Planned inspection date = INDEX(Assignments!$I5:I58,MATCH(B5&"¦April¦"&[Store ID],Assignments!$AD5:AD58,0))
Planned inspection date = INDEX(Assignments!$I5:I58,MATCH(B32&"¦May¦"&[Store ID],Assignments!$AD5:AD58,0))