## Recovery dashboard
Retrofit recovery plan
Ambergate Housing Trust ¦ decision position at 11 May 2026
Authorisation status | READY FOR AUTHORISATION
Recovery position |  |  |  | Regulatory milestones
Selected packages | 7 | Maximum permitted: 7 |  | Milestone | Planned timestamp | Accountable | Status
Permit criteria covered | 12 | Required: 12 |  | Final commissioning evidence | 2026-05-28 22:00 | Lorcan Ibarra | ON TIME
Engineer shifts used | 8 | Listed availability: 8 |  | Quality review | 2026-05-29 09:00 | Magda Villanueva | OK
Daily capacity | WITHIN LIMIT | 20 May and 26 May are 12h limits |  | Regulator submission | 2026-05-29 13:30 | Magda Villanueva | OK
Delivery cost | 46224 | Delivery cap excludes exposure |  | Submission deadline | 2026-05-29 14:00 | Magda Villanueva | ON TIME
Forecast exposure | 47655 | Inclusive calendar-day convention
Combined financial impact | 93879 | Delivery cost plus exposure
Formula-driven compliance checks
Control | Status | Formula evidence | Meeting focus
Selection eligibility and cap | PASS | Selected count, eligibility and source conditions | No ineligible or excess package
Permit coverage | PASS | All twelve tag rows recompute from source mapping | Every unit has three closures
Access, readiness, dependency and blackout | PASS | Selected package validation columns | Dates must remain in their source windows
Engineer allocation and recalibration | PASS | Eight listed engineer shifts and family-transition controls | One dedicated recalibration shift
Daily field capacity | PASS | Daily scheduled technician effort vs capacity | Occupied-site caps bind on 20 and 26 May
Testing cutoff | PASS | Intrusive commissioning completion by 23:00 on 28 May | Final test must stay before review
Quality review and submission | PASS | Review sequence, workday and deadline formula checks | Quality review before regulator submission
Delivery-cost cap | PASS | Fixed, technician, engineer and recalibration components | Exposure remains outside this cap
Decision | Authorise the grouped Horizon-then-Kestrel portfolio; it closes all permit tags with seven tests and one recalibration shift.

## Package decision
Package decision
Authorise only the seven released implementation packages that close all permit tags; inputs are shaded
Selection, plan date and plan shift are the calculation drivers. Source fields are retained for traceability.
Package ID | Select? | Plant room | Equipment family | Work description | Record type | Release status | Superseded by | Evidence | Confidence | Permit tags | Site ready | Access from | Access to | Permitted shift | Predecessor | Source tech h | Assumption h | Effective tech h | Fixed cost | Engineer test? | Accountable | Comparable ref | Plan date | Plan shift | Source eligibility | Window / readiness | Dependency | Blackout | Completion timestamp | Decision rationale
CG-101 | Yes | Crossgate | Horizon | Analyzer trim and telemetry prove-out | Implementation | Released |  | A | 92% | CG-AC, CG-TC | 2026-05-18 | 2026-05-18 | 2026-05-18 | PM |  | 8 |  | 8 | 3900 | Yes | Lorcan Ibarra |  | 2026-05-18 | PM | Eligible | OK | n/a | OK | 2026-05-18 22:00 | Selected: released A-grade opening Horizon test closes Crossgate analyzer and telemetry tags.
CG-102 | Yes | Crossgate | Horizon | Audit trail capture and witnessed evidence | Implementation | Released |  | B | 86% | CG-AW | 2026-05-18 | 2026-05-19 | 2026-05-19 | AM | CG-101 |  | 5 | 5 | 2350 | Yes | Lorcan Ibarra | HZN-AUD-02 | 2026-05-19 | AM | Eligible | OK | OK | OK | 2026-05-19 13:00 | Selected: released B-grade witness package closes Crossgate audit tag; comparable-range assumption is stated.
CG-103 | No | Crossgate | Horizon | Alternate analyzer calibration with audit capture | Implementation | Released |  | A | 90% | CG-AC | 2026-05-18 | 2026-05-18 | 2026-05-18 | PM |  | 9 |  | 9 | 4200 | Yes | Lorcan Ibarra |  | 2026-05-18 | PM | Eligible | n/a | n/a | n/a |  | Excluded: released alternate occupies the same constrained Horizon slot and adds no earlier closure.
CG-104 | No | Crossgate | Horizon | Alternate telemetry and witnessed evidence verification | Implementation | Released |  | B | 85% | CG-TC, CG-AW | 2026-05-18 | 2026-05-19 | 2026-05-19 | AM | CG-103 |  | 5 | 5 | 2450 | Yes | Lorcan Ibarra | HZN-AUD-02 | 2026-05-19 | AM | Eligible | n/a | n/a | n/a |  | Excluded: paired alternate is not needed once CG-101/CG-102 close the three Crossgate tags.
MH-201 | Yes | Millhaven | Horizon | Analyzer calibration and evidence chain | Implementation | Released |  | A | 94% | MH-AC, MH-AW | 2026-05-20 | 2026-05-20 | 2026-05-20 | PM |  | 12 |  | 12 | 4800 | Yes | Lorcan Ibarra |  | 2026-05-20 | PM | Eligible | OK | n/a | OK | 2026-05-20 22:00 | Selected: released A-grade package closes Millhaven analyzer and audit tags in its held occupied-site slot.
MH-202 | Yes | Millhaven | Horizon | Telemetry continuity proving run | Implementation | Released |  | B | 88% | MH-TC | 2026-05-20 | 2026-05-21 | 2026-05-21 | AM | MH-201 | 6 |  | 6 | 2100 | Yes | Lorcan Ibarra |  | 2026-05-21 | AM | Eligible | OK | OK | OK | 2026-05-21 13:00 | Selected: released B-grade telemetry test follows MH-201 and completes Millhaven closure.
MH-203 | No | Millhaven | Horizon | Alternate analyzer and telemetry set-up | Implementation | Released |  | A | 91% | MH-AC, MH-TC | 2026-05-20 | 2026-05-20 | 2026-05-20 | PM |  | 12 |  | 12 | 4950 | Yes | Lorcan Ibarra |  | 2026-05-20 | PM | Eligible | n/a | n/a | n/a |  | Excluded: alternate uses the same 20 May occupied-site engineer and technician allocation.
MH-204 | No | Millhaven | Horizon | Alternate witnessed audit pack | Implementation | Released |  | B | 84% | MH-AW | 2026-05-20 | 2026-05-21 | 2026-05-21 | AM | MH-203 | 5 |  | 5 | 2300 | Yes | Lorcan Ibarra |  | 2026-05-21 | AM | Eligible | n/a | n/a | n/a |  | Excluded: paired alternate does not improve coverage, capacity, or completion date.
DS-301 | Yes | Docksett | Kestrel | Analyzer trim and telemetry proving run | Implementation | Released |  | A | 93% | DS-AC, DS-TC | 2026-05-26 | 2026-05-26 | 2026-05-26 | PM |  | 12 |  | 12 | 4650 | Yes | Lorcan Ibarra |  | 2026-05-26 | PM | Eligible | OK | n/a | OK | 2026-05-26 22:00 | Selected: released A-grade Kestrel package uses the held 26 May occupied-site allocation.
DS-302 | Yes | Docksett | Kestrel | Audit trail capture and witnessed evidence | Implementation | Released |  | B | 87% | DS-AW | 2026-05-26 | 2026-05-27 | 2026-05-27 | AM | DS-301 |  | 6 | 6 | 2450 | Yes | Lorcan Ibarra | KST-AUD-07 | 2026-05-27 | AM | Eligible | OK | OK | OK | 2026-05-27 13:00 | Selected: released B-grade witness package completes Docksett after DS-301; assumption is stated.
DS-303 | No | Docksett | Kestrel | Alternate analyzer calibration with audit capture | Implementation | Released |  | A | 90% | DS-AC, DS-AW | 2026-05-26 | 2026-05-26 | 2026-05-26 | PM |  | 12 |  | 12 | 5000 | Yes | Lorcan Ibarra |  | 2026-05-26 | PM | Eligible | n/a | n/a | n/a |  | Excluded: alternate occupies the same Kestrel engineer slot and offers no earlier completion.
DS-304 | No | Docksett | Kestrel | Alternate telemetry continuity verification | Implementation | Released |  | B | 85% | DS-TC | 2026-05-26 | 2026-05-27 | 2026-05-27 | AM | DS-303 | 5 |  | 5 | 2300 | Yes | Lorcan Ibarra |  | 2026-05-27 | AM | Eligible | n/a | n/a | n/a |  | Excluded: paired alternate does not improve permit closure or the grouped family sequence.
LF-401 | Yes | Larkfield | Kestrel | Integrated analyzer, telemetry and witness close-out | Implementation | Released |  | A | 95% | LF-AC, LF-TC, LF-AW | 2026-05-28 | 2026-05-28 | 2026-05-28 | PM |  | 18 |  | 18 | 5100 | Yes | Lorcan Ibarra |  | 2026-05-28 | PM | Eligible | OK | n/a | OK | 2026-05-28 22:00 | Selected: one released package closes all three Larkfield tags in the final Kestrel test slot.
LF-402 | No | Larkfield | Kestrel | Analyzer-only intervention | Implementation | Released |  | B | 89% | LF-AC | 2026-05-28 | 2026-05-28 | 2026-05-28 | PM |  | 6 |  | 6 | 1650 | Yes | Lorcan Ibarra |  | 2026-05-28 | PM | Eligible | n/a | n/a | n/a |  | Excluded: partial scope cannot close Larkfield alone; selected integrated package preserves the seven-package cap.
LF-403 | No | Larkfield | Kestrel | Telemetry-only intervention | Implementation | Released |  | B | 88% | LF-TC | 2026-05-28 | 2026-05-28 | 2026-05-28 | PM |  | 6 |  | 6 | 1580 | Yes | Lorcan Ibarra |  | 2026-05-28 | PM | Eligible | n/a | n/a | n/a |  | Excluded: partial scope cannot close Larkfield alone; no date or coverage benefit.
LF-404 | No | Larkfield | Kestrel | Witness evidence-only intervention | Implementation | Released |  | B | 83% | LF-AW | 2026-05-28 | 2026-05-28 | 2026-05-28 | PM |  | 6 |  | 6 | 1740 | Yes | Lorcan Ibarra |  | 2026-05-28 | PM | Eligible | n/a | n/a | n/a |  | Excluded: partial scope cannot close Larkfield alone; no date or coverage benefit.
LF-405 | No | Larkfield | Kestrel | Analyzer and telemetry partial intervention | Implementation | Released |  | A | 90% | LF-AC, LF-TC | 2026-05-28 | 2026-05-28 | 2026-05-28 | PM |  | 12 |  | 12 | 3120 | Yes | Lorcan Ibarra |  | 2026-05-28 | PM | Eligible | n/a | n/a | n/a |  | Excluded: still needs a separate audit package, increasing the portfolio beyond seven packages.
LF-406 | No | Larkfield | Kestrel | Trace-only witness evidence intervention | Implementation | Released |  | B | 82% | LF-AW | 2026-05-28 | 2026-05-28 | 2026-05-28 | PM |  | 6 |  | 6 | 1810 | Yes | Lorcan Ibarra |  | 2026-05-28 | PM | Eligible | n/a | n/a | n/a |  | Excluded: partial audit-only record; its blank effort has a comparable range but the scope is not required.
CG-105 | No | Crossgate | Horizon | Combined analyzer, telemetry and witness recovery | Implementation | Released |  | A | 79% | CG-AC, CG-TC, CG-AW | 2026-05-18 | 2026-05-18 | 2026-05-18 | PM |  | 10 |  | 10 | 3350 | Yes | Lorcan Ibarra |  | 2026-05-18 | PM | Ineligible | n/a | n/a | n/a |  | Excluded: confidence is 79%, one percentage point below the permit minimum despite broad coverage.
MH-205 | No | Millhaven | Horizon | Low-cost combined recovery package | Implementation | Released |  | C | 93% | MH-AC, MH-TC, MH-AW | 2026-05-20 | 2026-05-20 | 2026-05-20 | PM |  | 10 |  | 10 | 3250 | Yes | Lorcan Ibarra |  | 2026-05-20 | PM | Ineligible | n/a | n/a | n/a |  | Excluded: evidence grade C is below the accepted A/B range despite the low fixed cost.
DS-305 | No | Docksett | Kestrel | Broad close-out pack | Implementation | Released | DS-301 | A | 96% | DS-AC, DS-TC, DS-AW | 2026-05-26 | 2026-05-26 | 2026-05-26 | PM |  | 11 |  | 11 | 3850 | Yes | Lorcan Ibarra |  | 2026-05-26 | PM | Ineligible | n/a | n/a | n/a |  | Excluded: explicitly superseded by DS-301; it cannot close Docksett obligations.
LF-407 | No | Larkfield | Kestrel | Integrated close-out package | Implementation | Hold - not released |  | B | 91% | LF-AC, LF-TC, LF-AW | 2026-05-28 | 2026-05-28 | 2026-05-28 | PM |  | 16 |  | 16 | 3450 | Yes | Lorcan Ibarra |  | 2026-05-28 | PM | Ineligible | n/a | n/a | n/a |  | Excluded: technical content is complete, but release status is Hold - not released.
Formulas:
Completion timestamp = IF([Select?]="Yes",[Plan date]+IF([Plan shift]="AM",TIME(13,0,0),TIME(22,0,0)),"")

## Permit coverage
Permit coverage
Tag-level source mapping; a tag is closed only by a selected eligible implementation package
Twelve controlling permit criteria
Permit tag | Plant room | Obligation | Eligible selected packages | Status | Closing package
CG-AC | Crossgate | Analyzer calibration | 1 | COVERED | CG-101
CG-AW | Crossgate | Audit trail + witness evidence | 1 | COVERED | CG-102
CG-TC | Crossgate | Telemetry continuity | 1 | COVERED | CG-101
DS-AC | Docksett | Analyzer calibration | 1 | COVERED | DS-301
DS-AW | Docksett | Audit trail + witness evidence | 1 | COVERED | DS-302
DS-TC | Docksett | Telemetry continuity | 1 | COVERED | DS-301
LF-AC | Larkfield | Analyzer calibration | 1 | COVERED | LF-401
LF-AW | Larkfield | Audit trail + witness evidence | 1 | COVERED | LF-401
LF-TC | Larkfield | Telemetry continuity | 1 | COVERED | LF-401
MH-AC | Millhaven | Analyzer calibration | 1 | COVERED | MH-201
MH-AW | Millhaven | Audit trail + witness evidence | 1 | COVERED | MH-201
MH-TC | Millhaven | Telemetry continuity | 1 | COVERED | MH-202
Source-supported package-to-tag mapping
Package ID | Plant room | Source-supported tag | Selected? | Source eligibility | Counts toward closure | Mapping basis
CG-101 | Crossgate | CG-AC | Yes | Eligible | Yes | Work-register coverage tag
CG-101 | Crossgate | CG-TC | Yes | Eligible | Yes | Work-register coverage tag
CG-102 | Crossgate | CG-AW | Yes | Eligible | Yes | Work-register coverage tag
CG-103 | Crossgate | CG-AC | No | Eligible | No | Work-register coverage tag
CG-104 | Crossgate | CG-TC | No | Eligible | No | Work-register coverage tag
CG-104 | Crossgate | CG-AW | No | Eligible | No | Work-register coverage tag
MH-201 | Millhaven | MH-AC | Yes | Eligible | Yes | Work-register coverage tag
MH-201 | Millhaven | MH-AW | Yes | Eligible | Yes | Work-register coverage tag
MH-202 | Millhaven | MH-TC | Yes | Eligible | Yes | Work-register coverage tag
MH-203 | Millhaven | MH-AC | No | Eligible | No | Work-register coverage tag
MH-203 | Millhaven | MH-TC | No | Eligible | No | Work-register coverage tag
MH-204 | Millhaven | MH-AW | No | Eligible | No | Work-register coverage tag
DS-301 | Docksett | DS-AC | Yes | Eligible | Yes | Work-register coverage tag
DS-301 | Docksett | DS-TC | Yes | Eligible | Yes | Work-register coverage tag
DS-302 | Docksett | DS-AW | Yes | Eligible | Yes | Work-register coverage tag
DS-303 | Docksett | DS-AC | No | Eligible | No | Work-register coverage tag
DS-303 | Docksett | DS-AW | No | Eligible | No | Work-register coverage tag
DS-304 | Docksett | DS-TC | No | Eligible | No | Work-register coverage tag
LF-401 | Larkfield | LF-AC | Yes | Eligible | Yes | Work-register coverage tag
LF-401 | Larkfield | LF-TC | Yes | Eligible | Yes | Work-register coverage tag
LF-401 | Larkfield | LF-AW | Yes | Eligible | Yes | Work-register coverage tag
LF-402 | Larkfield | LF-AC | No | Eligible | No | Work-register coverage tag
LF-403 | Larkfield | LF-TC | No | Eligible | No | Work-register coverage tag
LF-404 | Larkfield | LF-AW | No | Eligible | No | Work-register coverage tag
LF-405 | Larkfield | LF-AC | No | Eligible | No | Work-register coverage tag
LF-405 | Larkfield | LF-TC | No | Eligible | No | Work-register coverage tag
LF-406 | Larkfield | LF-AW | No | Eligible | No | Work-register coverage tag
CG-105 | Crossgate | CG-AC | No | Ineligible | No | Work-register coverage tag
CG-105 | Crossgate | CG-TC | No | Ineligible | No | Work-register coverage tag
CG-105 | Crossgate | CG-AW | No | Ineligible | No | Work-register coverage tag
MH-205 | Millhaven | MH-AC | No | Ineligible | No | Work-register coverage tag
MH-205 | Millhaven | MH-TC | No | Ineligible | No | Work-register coverage tag
MH-205 | Millhaven | MH-AW | No | Ineligible | No | Work-register coverage tag
DS-305 | Docksett | DS-AC | No | Ineligible | No | Work-register coverage tag
DS-305 | Docksett | DS-TC | No | Ineligible | No | Work-register coverage tag
DS-305 | Docksett | DS-AW | No | Ineligible | No | Work-register coverage tag
LF-407 | Larkfield | LF-AC | No | Ineligible | No | Work-register coverage tag
LF-407 | Larkfield | LF-TC | No | Ineligible | No | Work-register coverage tag
LF-407 | Larkfield | LF-AW | No | Ineligible | No | Work-register coverage tag

## Shift plan
Dated shift plan
Authorised commissioning is grouped by calibration state, followed by quality review and regulator submission
Commissioning completion is shown at the end of the permitted AM/PM shift. Unselected candidates are not authorised and have no execution timestamp.
Activity ID | Activity type | Plant room | Equipment family | Planned date | Shift | Start | Completion | Technician h | Certified engineer? | Accountable owner | Authorisation status | Access / dependency | Schedule check | Blackout | Engineer slot | Cutoff / milestone check
CG-101 | Commissioning evidence | Crossgate | Horizon | 2026-05-18 | PM | 2026-05-18 14:00 | 2026-05-18 22:00 | 8 | Yes | Lorcan Ibarra | AUTHORIZED - COMMISSION | 18 May to 18 May / | OK | OK | OK | OK
CG-102 | Commissioning evidence | Crossgate | Horizon | 2026-05-19 | AM | 2026-05-19 08:00 | 2026-05-19 13:00 | 5 | Yes | Lorcan Ibarra | AUTHORIZED - COMMISSION | 19 May to 19 May / CG-101 | OK | OK | OK | OK
CG-103 | Candidate not authorised | Crossgate | Horizon |  |  |  |  | 0 |  |  | NOT AUTHORISED | 18 May to 18 May / | n/a | n/a | n/a | n/a
CG-104 | Candidate not authorised | Crossgate | Horizon |  |  |  |  | 0 |  |  | NOT AUTHORISED | 19 May to 19 May / CG-103 | n/a | n/a | n/a | n/a
MH-201 | Commissioning evidence | Millhaven | Horizon | 2026-05-20 | PM | 2026-05-20 14:00 | 2026-05-20 22:00 | 12 | Yes | Lorcan Ibarra | AUTHORIZED - COMMISSION | 20 May to 20 May / | OK | OK | OK | OK
MH-202 | Commissioning evidence | Millhaven | Horizon | 2026-05-21 | AM | 2026-05-21 08:00 | 2026-05-21 13:00 | 6 | Yes | Lorcan Ibarra | AUTHORIZED - COMMISSION | 21 May to 21 May / MH-201 | OK | OK | OK | OK
MH-203 | Candidate not authorised | Millhaven | Horizon |  |  |  |  | 0 |  |  | NOT AUTHORISED | 20 May to 20 May / | n/a | n/a | n/a | n/a
MH-204 | Candidate not authorised | Millhaven | Horizon |  |  |  |  | 0 |  |  | NOT AUTHORISED | 21 May to 21 May / MH-203 | n/a | n/a | n/a | n/a
DS-301 | Commissioning evidence | Docksett | Kestrel | 2026-05-26 | PM | 2026-05-26 14:00 | 2026-05-26 22:00 | 12 | Yes | Lorcan Ibarra | AUTHORIZED - COMMISSION | 26 May to 26 May / | OK | OK | OK | OK
DS-302 | Commissioning evidence | Docksett | Kestrel | 2026-05-27 | AM | 2026-05-27 08:00 | 2026-05-27 13:00 | 6 | Yes | Lorcan Ibarra | AUTHORIZED - COMMISSION | 27 May to 27 May / DS-301 | OK | OK | OK | OK
DS-303 | Candidate not authorised | Docksett | Kestrel |  |  |  |  | 0 |  |  | NOT AUTHORISED | 26 May to 26 May / | n/a | n/a | n/a | n/a
DS-304 | Candidate not authorised | Docksett | Kestrel |  |  |  |  | 0 |  |  | NOT AUTHORISED | 27 May to 27 May / DS-303 | n/a | n/a | n/a | n/a
LF-401 | Commissioning evidence | Larkfield | Kestrel | 2026-05-28 | PM | 2026-05-28 14:00 | 2026-05-28 22:00 | 18 | Yes | Lorcan Ibarra | AUTHORIZED - COMMISSION | 28 May to 28 May / | OK | OK | OK | OK
LF-402 | Candidate not authorised | Larkfield | Kestrel |  |  |  |  | 0 |  |  | NOT AUTHORISED | 28 May to 28 May / | n/a | n/a | n/a | n/a
LF-403 | Candidate not authorised | Larkfield | Kestrel |  |  |  |  | 0 |  |  | NOT AUTHORISED | 28 May to 28 May / | n/a | n/a | n/a | n/a
LF-404 | Candidate not authorised | Larkfield | Kestrel |  |  |  |  | 0 |  |  | NOT AUTHORISED | 28 May to 28 May / | n/a | n/a | n/a | n/a
LF-405 | Candidate not authorised | Larkfield | Kestrel |  |  |  |  | 0 |  |  | NOT AUTHORISED | 28 May to 28 May / | n/a | n/a | n/a | n/a
LF-406 | Candidate not authorised | Larkfield | Kestrel |  |  |  |  | 0 |  |  | NOT AUTHORISED | 28 May to 28 May / | n/a | n/a | n/a | n/a
CG-105 | Candidate not authorised | Crossgate | Horizon |  |  |  |  | 0 |  |  | NOT AUTHORISED | 18 May to 18 May / | n/a | n/a | n/a | n/a
MH-205 | Candidate not authorised | Millhaven | Horizon |  |  |  |  | 0 |  |  | NOT AUTHORISED | 20 May to 20 May / | n/a | n/a | n/a | n/a
DS-305 | Candidate not authorised | Docksett | Kestrel |  |  |  |  | 0 |  |  | NOT AUTHORISED | 26 May to 26 May / | n/a | n/a | n/a | n/a
LF-407 | Candidate not authorised | Larkfield | Kestrel |  |  |  |  | 0 |  |  | NOT AUTHORISED | 28 May to 28 May / | n/a | n/a | n/a | n/a
RECAL-01 | Recalibration | All plant rooms | Horizon -> Kestrel | 2026-05-22 | AM | 2026-05-22 08:00 | 2026-05-22 13:00 | 0 | Yes | Lorcan Ibarra | RESERVED - RECALIBRATION | Whole listed engineer shift; no test may share it | OK | n/a | OK | OK
MILE-QR | Quality review | Portfolio | - | 2026-05-29 | AM | 2026-05-29 09:00 | 2026-05-29 11:00 | 0 | No | Magda Villanueva | MILESTONE | Review after all commissioning evidence | OK | n/a | OK | OK
MILE-SUB | Regulator submission | Portfolio | - | 2026-05-29 | AM | 2026-05-29 13:30 | 2026-05-29 13:30 | 0 | No | Magda Villanueva | MILESTONE | Regulator-ready pack submission | OK | n/a | OK | OK
Formulas:
Start = IF([Planned date]="","",[Planned date]+IF([Shift]="AM",TIME(8,0,0),TIME(14,0,0)))
Start = IF([Planned date]="","",[Planned date]+TIME(8,0,0))
Completion = IF([Planned date]="","",[Planned date]+IF([Shift]="AM",TIME(13,0,0),TIME(22,0,0)))
Completion = IF([Planned date]="","",[Planned date]+TIME(13,0,0))

## Capacity & finance
Capacity & finance
Source rates, engineer allocation, daily field capacity, delivery cost and unit exposure
Commercial and timing inputs |  |  |  | Portfolio summary
Technician labour rate | 92 |  |  | Selected packages | 7
Engineer test-shift rate | 1180 |  |  | Selected eligible packages | 7
Recalibration charge | 6450 |  |  | Selected technician effort | 67
Delivery-cost cap | 47000 |  |  | Commissioning test shifts | 7
Exposure start | 2026-05-18 |  |  | Required recalibration shifts | 1
Testing cutoff | 2026-05-28 23:00 |  |  | Engineer shifts used | 8
Submission deadline | 2026-05-29 14:00 |  |  | Engineer shifts remaining | 0
|  |  |  | Delivery cost | 46224
|  |  |  | Cap headroom | 776
|  |  |  | Forecast exposure | 47655
|  |  |  | Combined financial impact | 93879
Daily field-technician capacity | [8 empty] | Delivery-cost detail
Date | Day | Occupied? | Capacity h | Scheduled h | Remaining h | Status | Permitted shifts |  | Package ID | Selected? | Fixed charge | Effective h | Technician labour | Test shifts | Engineer testing | Package delivery cost
2026-05-18 | Mon | No | 18 | 8 | 10 | OK | AM / PM |  | CG-101 | Yes | 3900 | 8 | 736 | 1 | 1180 | 5816
2026-05-19 | Tue | No | 18 | 5 | 13 | OK | AM / PM |  | CG-102 | Yes | 2350 | 5 | 460 | 1 | 1180 | 3990
2026-05-20 | Wed | Yes | 12 | 12 | 0 | OK | AM / PM |  | CG-103 | No | 0 | 0 | 0 | 0 | 0 | 0
2026-05-21 | Thu | No | 18 | 6 | 12 | OK | AM / PM |  | CG-104 | No | 0 | 0 | 0 | 0 | 0 | 0
2026-05-22 | Fri | No | 18 | 0 | 18 | OK | AM / PM |  | MH-201 | Yes | 4800 | 12 | 1104 | 1 | 1180 | 7084
2026-05-26 | Tue | Yes | 12 | 12 | 0 | OK | AM / PM |  | MH-202 | Yes | 2100 | 6 | 552 | 1 | 1180 | 3832
2026-05-27 | Wed | No | 18 | 6 | 12 | OK | AM / PM |  | MH-203 | No | 0 | 0 | 0 | 0 | 0 | 0
2026-05-28 | Thu | No | 18 | 18 | 0 | OK | AM / PM |  | MH-204 | No | 0 | 0 | 0 | 0 | 0 | 0
2026-05-29 | Fri | No | 18 | 0 | 18 | OK | AM only |  | DS-301 | Yes | 4650 | 12 | 1104 | 1 | 1180 | 6934
[9 empty] | DS-302 | Yes | 2450 | 6 | 552 | 1 | 1180 | 4182
[9 empty] | DS-303 | No | 0 | 0 | 0 | 0 | 0 | 0
Unit exposure forecast | [8 empty] | DS-304 | No | 0 | 0 | 0 | 0 | 0 | 0
Plant room | Daily rate | Closure completion | Cessation date | Inclusive days | Forecast exposure | Closure status |  |  | LF-401 | Yes | 5100 | 18 | 1656 | 1 | 1180 | 7936
Crossgate | 1275 | 2026-05-19 13:00 | 2026-05-19 | 2 | 2550 | CLOSED |  |  | LF-402 | No | 0 | 0 | 0 | 0 | 0 | 0
Millhaven | 1860 | 2026-05-21 13:00 | 2026-05-21 | 4 | 7440 | CLOSED |  |  | LF-403 | No | 0 | 0 | 0 | 0 | 0 | 0
Docksett | 1440 | 2026-05-27 13:00 | 2026-05-27 | 10 | 14400 | CLOSED |  |  | LF-404 | No | 0 | 0 | 0 | 0 | 0 | 0
Larkfield | 2115 | 2026-05-28 22:00 | 2026-05-28 | 11 | 23265 | CLOSED |  |  | LF-405 | No | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | LF-406 | No | 0 | 0 | 0 | 0 | 0 | 0
Total forecast exposure |  |  |  |  | 47655 |  |  |  | CG-105 | No | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | MH-205 | No | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | DS-305 | No | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | LF-407 | No | 0 | 0 | 0 | 0 | 0 | 0
[9 empty] | Selected fixed charges | [6 empty] | 25350
[9 empty] | Technician labour | [6 empty] | 6164
[9 empty] | Engineer testing | [6 empty] | 8260
[9 empty] | Recalibration | [6 empty] | 6450
[9 empty] | Total delivery cost | [6 empty] | 46224
Certified engineer shift allocation
Seq | Date | Shift | Availability | Test count | Commissioning package | Family | Previous test family | Family transition | Recalibration held | Engineer activities | Slot status | Transition control
1 | 2026-05-18 | PM | Listed | 1 | CG-101 | Horizon |  | 0 | 0 | 1 | OK
2 | 2026-05-19 | AM | Listed | 1 | CG-102 | Horizon | Horizon | 0 | 0 | 1 | OK
3 | 2026-05-20 | PM | Listed | 1 | MH-201 | Horizon | Horizon | 0 | 0 | 1 | OK
4 | 2026-05-21 | AM | Listed | 1 | MH-202 | Horizon | Horizon | 0 | 0 | 1 | OK
5 | 2026-05-22 | AM | Listed | 0 |  |  |  | 0 | 1 | 1 | OK
6 | 2026-05-26 | PM | Listed | 1 | DS-301 | Kestrel | Horizon | 1 | 0 | 1 | OK | OK
7 | 2026-05-27 | AM | Listed | 1 | DS-302 | Kestrel | Kestrel | 0 | 0 | 1 | OK
8 | 2026-05-28 | PM | Listed | 1 | LF-401 | Kestrel | Kestrel | 0 | 0 | 1 | OK
Formulas:
Occupied? = IF(COUNTIFS('Permit coverage'!$B6:B17,[Date],'Permit coverage'!$E6:E17,"COVERED")=3,MAX('Shift plan'!$H6,'Shift plan'!$H7,'Shift plan'!$H8,'Shift plan'!$H9,'Shift plan'!$H24),"")
Occupied? = IF(COUNTIFS('Permit coverage'!$B6:B17,[Date],'Permit coverage'!$E6:E17,"COVERED")=3,MAX('Shift plan'!$H18,'Shift plan'!$H19,'Shift plan'!$H20,'Shift plan'!$H21,'Shift plan'!$H22,'Shift plan'!$H23,'Shift plan'!$H27),"")
Capacity h = IF([Occupied?]="","",INT([Occupied?]))

## Assumptions
Duration assumptions
Comparable completed-work ranges retained for source records with blank technician effort
Explicit package assumptions
Package ID | Selected? | Source effort | Comparable ref | Low hrs | Typical hrs | High hrs | Chosen hrs | Basis | Accountable
CG-102 | Yes |  | HZN-AUD-02 | 4 | 5 | 6 | 5 | Typical value from HZN-AUD-02: audit / witnessed commissioning evidence (4-6h). | Magda Villanueva
CG-104 | No |  | HZN-AUD-02 | 4 | 5 | 6 | 5 | Typical value from HZN-AUD-02: audit / witnessed commissioning evidence (4-6h). | Magda Villanueva
DS-302 | Yes |  | KST-AUD-07 | 5 | 6 | 7 | 6 | Typical value from KST-AUD-07: audit / witnessed commissioning evidence (5-7h). | Magda Villanueva
Control | Recorded source effort remains the effective effort. Chosen hrs applies only where source effort is blank.

## Decision record
Decision record
Authorisation rationale for Operations, Engineering, Finance and Assurance
Decision | AUTHORISE - seven released implementation packages, grouped by equipment family, with one dedicated recalibration shift.
Selected package basis
Package | Status | Permit contribution | Planned commissioning | Accountable | Source-grounded rationale
CG-101 | Yes | CG-AC, CG-TC | 18 May PM | Lorcan Ibarra | Crossgate analyzer calibration and telemetry continuity; first Horizon commissioning slot.
CG-102 | Yes | CG-AW | 19 May AM | Lorcan Ibarra | Crossgate audit/witness evidence; 5h assumption is the comparable typical value within 4-6h range.
MH-201 | Yes | MH-AC, MH-AW | 20 May PM | Lorcan Ibarra | Millhaven analyzer calibration and audit evidence; occupies 20 May's held 12h occupied-site allocation.
MH-202 | Yes | MH-TC | 21 May AM | Lorcan Ibarra | Millhaven telemetry continuity after MH-201; preserves the Horizon grouping.
DS-301 | Yes | DS-AC, DS-TC | 26 May PM | Lorcan Ibarra | Docksett analyzer calibration and telemetry continuity; uses 26 May's held 12h occupied-site allocation.
DS-302 | Yes | DS-AW | 27 May AM | Lorcan Ibarra | Docksett audit/witness evidence after DS-301; 6h assumption is the comparable typical value within 5-7h range.
LF-401 | Yes | LF-AC, LF-TC, LF-AW | 28 May PM | Lorcan Ibarra | Integrated Larkfield close-out covers all three tags in one final Kestrel commissioning shift.
Material excluded and near-miss records
Package / group | Source condition | Why not authorised | Capacity or timing implication | Decision owner | Review note
CG-103 + CG-104 | Released alternates | Same Crossgate tags and the same 18/19 May Horizon engineer shifts as selected work. | No earlier closure; seven-package cap leaves no room for duplicate coverage. | Magda Villanueva | Retain as contingency only.
MH-203 + MH-204 | Released alternates | Same Millhaven tag set as selected work. | Would consume the same 20 May 12h occupied-site allocation and Horizon shifts. | Magda Villanueva | No coverage or deadline gain.
DS-303 + DS-304 | Released alternates | Same Docksett tag set as selected work. | Would consume the same 26/27 May Kestrel shifts and occupied-site capacity. | Magda Villanueva | No coverage or deadline gain.
LF-402 to LF-406 | Released partial scopes | No individual partial record closes all three Larkfield tags. | Two or more would be required in the single final Kestrel slot, breaching package/engineer limits. | Magda Villanueva | LF-401 is the bounded close-out.
CG-105 | Confidence 79% | One percentage point below the 80% permit confidence threshold. | Broad apparent coverage cannot override eligibility. | Magda Villanueva | High-coverage near miss.
MH-205 | Evidence grade C | Grade C is below the permit's accepted A/B evidence range. | Low fixed cost cannot override evidence acceptance. | Magda Villanueva | Low-cost near miss.
DS-305 | Superseded by DS-301 | An explicitly replaced work record cannot close a permit criterion. | Selected DS-301 remains the released active scope. | Magda Villanueva | Broad-coverage near miss.
LF-407 | Hold - not released | Technical content is not sufficient without implementation release. | No authorised execution date may be assigned. | Magda Villanueva | Release-status near miss.
Financial position | 46224 | delivery cost | 47655 | forecast exposure | 93879

## Calendar
Planning calendar
Source-derived workdays, occupied-site limits and blackout slots
Permitted workdays | [6 empty] | Blackout log
Date | Day | Workday | Permitted shifts | Tech capacity | Occupied site | Engineer available | Plant room | Date | Shift | Restriction
2026-05-18 | Mon | Yes | AM / PM | 18 | No | PM | Crossgate | 2026-05-18 | AM | resident heat-demand changeover
2026-05-19 | Tue | Yes | AM / PM | 18 | No | AM | Crossgate | 2026-05-19 | PM | boiler proving window
2026-05-20 | Wed | Yes | AM / PM | 12 | Yes | PM | Millhaven | 2026-05-20 | AM | occupied-site pump inspection
2026-05-21 | Thu | Yes | AM / PM | 18 | No | AM | Millhaven | 2026-05-21 | PM | landlord access restriction
2026-05-22 | Fri | Yes | AM / PM | 18 | No | AM | Docksett | 2026-05-26 | AM | occupied-site water treatment
2026-05-26 | Tue | Yes | AM / PM | 12 | Yes | PM | Docksett | 2026-05-27 | PM | district-load peak
2026-05-27 | Wed | Yes | AM / PM | 18 | No | AM | Larkfield | 2026-05-28 | AM | safety-system monthly check
2026-05-28 | Thu | Yes | AM / PM | 18 | No | PM
2026-05-29 | Fri | Yes | AM only | 18 | No