## Slide 1
DECISION BRIEF
Inspection capability roadmap | Lanternwood renewal
Submission due 31 March 2026 • Horizon: Year 1 (2026)–Year 3 (2028)
Stage the laser-tracker capability now; retain the approved independent signer through the qualification gate.
Demand step-up
24,000 → 66,000 bearings +175.0% in Year 2
Policy constraint
≥20% reserve (≤80% utilization) and customer-accepted certificates.
Accepted trade-off
External cost and supplier dependence now, in return for acceptance and reversibility.
Sources: Renewal Inputs—Planning brief; Demand Forecast; Issued Decision Policy

## Slide 2
01 | NEED
Demand outlook is the forcing function
Latest approved record retained per printed business key; Notes reviewed.
Year 1 (2026)
12,000
8,000
4,000
Total 24,000
Year 2 (2027)
28,000
26,000
12,000
Total 66,000
Year 3 (2028)
34,000
30,000
16,000
Total 80,000
Angular contact
Cylindrical roller
Thrust
Method disclosure: the most recent Approved revision is retained for repeated Year + family + route keys. The Year 2 Angular route note permits a 10% laser transfer after validation; it does not alter family demand.
Year 1
24,000 bearings
Year 2
66,000 bearings
Year 3
80,000 bearings
Source: Renewal Inputs—Demand Forecast

## Slide 3
02 | CAPACITY
Workload grows before the technical route can change
Hours = retained family demand × cycle time ÷ 60.
Dimensional verification
Surface / visual
Certification pack
Year 1 (2026)
1,200 h
593 h
320 h
Year 2 (2027)
3,283 h
1,620 h
877 h
Year 3 (2028)
4,017 h
1,983 h
1,070 h
Year 2 dimensional workload is 3,383 h. Laser capability is not productive until 01 January 2027; the legacy CMM cannot be a planned post-support solution.
Sources: Renewal Inputs—Demand Forecast; Inspection Workload & Resource Capacity

## Slide 4
03 | POLICY TEST
Effective capacity, not nameplate hours, determines adequacy
Policy limit: utilization ≤80% (maintain 20% reserve).
Configuration
Required
Capacity
Utilization / headroom
Year 1 | CMM dimensional
1,200 h
1,800 h
67% | +600 h
Year 1 | agency other stages
913 h
1,200 h
76% | +287 h
Year 2 | laser dimensional
3,283 h
4,500 h
73% | +1,217 h
Year 2 | agency surface/cert
2,497 h
3,200 h
78% | +703 h
Year 3 | laser dimensional
4,017 h
5,500 h
73% | +1,483 h
Year 3 | agency surface/cert
3,053 h
4,000 h
76% | +947 h
Bottleneck to manage: Year 1 agency coverage is highest at 76% utilization; the transition must protect its reservation and the laser start-up sequence.
Sources: Renewal Inputs—Inspection Workload & Resource Capacity; Issued Decision Policy

## Slide 5
04 | ALTERNATIVES
Three delivery models compared on the same basis
Capital plus annual fixed and workload-linked costs across the stated horizon.
Option
Capex
Year 1
Year 2
Year 3
3-year total
Retain independent
$0
$289,633
$601,300
$710,950
$1,601,883
In-house laser tracker
$540,000
$334,033
$684,667
$807,850
$2,366,550
Staged hybrid (recommended)
$540,000
$417,033
$512,667
$635,850
$2,105,550
Retain independent
Immediate capacity + accepted certificates; recurring cost and supplier exposure.
In-house laser tracker
Technical capacity after validation; no automatic accepted signing authority.
Staged hybrid
Bounded capital, agency signing retained, internal lead-time benefit after ramp.
Source: Renewal Inputs—Commercial Delivery Options; calculated workload allocation

## Slide 6
05 | RECOMMENDED PATH
A staged hybrid preserves accepted certificates in every year
Technical measurement and authority to issue Lanternwood-accepted certificates are kept distinct.
Year 1 (2026)
Reserve 1,200 h agency; issue staged laser PO; final CMM calibration by 31 Dec; use CMM for dimensional, agency for other stages and certificates. Owner(s): Amara / Ingrid / Emeka / Olamide
Year 2 (2027)
Laser productive 01 Jan after install, training and validation; agency signs certificates and covers other stages within the 3,200 h cap. No CMM after 30 Jun support end. Owner(s): Emeka / Olamide / Zara
Year 3 (2028)
Expand only if recognized signing authority is evidenced; otherwise keep agency certificate route within 4,000 h and do not rely on the unsupported CMM. Owner(s): Zara / Ingrid / Amara
Sources: Renewal Inputs—Planning brief; Resource Capacity; Qualification & Supplier Evidence; Commercial Options

## Slide 7
06 | GATES & CONTINGENCY
Commit now only where the fallback is executable
Gates use supported calendar triggers and named future evidence.
G1 | 31 Mar 2026
Submission deadline + reserve/certificate route evidenced.
Approve staged PO and agency reservation. Owner: Amara / Zara
G2 | 01 Jan 2027
Installation, training and validation complete.
Release laser productive hours; retain agency signer. Owner: Emeka / Olamide
G3 | 30 Sep 2027
Lanternwood feedback, 18 months from submission.
Transfer only with recognized authority; otherwise retain agency. Owner: Zara / Olamide
Late or adverse
Feedback absent/adverse at G3.
Extend agency within capacity, defer expansion; no unsupported CMM. Owner: Ingrid / Amara
Sources: Renewal Inputs—Planning brief; Issued Decision Policy; Qualification & Supplier Evidence

## Slide 8
07 | CERTIFICATE ROUTE
The certificate chain remains supported through uncertainty
Independent approval is customer-recognized; it is not transferred by buying the laser tracker.
Year 1
CMM / agency measurement as allocated → independent agency signs accepted certificate.
Year 2
Laser measures after 01 Jan → independent agency remains accepted signer pending feedback.
Year 3
Only transfer signing with documented recognized authority; otherwise agency signs.
Control
Final CMM calibration by 31 Dec 2026; no planned CMM use after support ends.
Accepted trade-off
Carry external cost and supplier dependence now to protect acceptance and reversibility.
Source: Renewal Inputs—Qualification & Supplier Evidence; Resource Capacity; Issued Decision Policy

## Slide 9
08 | RISKS & CONTROLS
The exposed items have executable controls
Risk ownership follows the planning brief responsibilities.
Capacity / reserve
Reserve agency capacity; monitor loads against 80%.
Emeka / Ingrid
Support / calibration
Final calibration by 31 Dec; retire CMM after Year 1.
Emeka / Olamide
Qualification
Keep signer; defer expansion if adverse or late.
Zara / Olamide
Staffing / schedule
Complete training and validation before productive use.
Emeka
Capital exposure
Stage investment and retain policy-compliant fallback.
Amara
Sources: Renewal Inputs—Resource Capacity; Commercial Options; Qualification & Supplier Evidence; Issued Decision Policy