Kingsferry Regional Office Move – Approved Review Packet

Issued 22 December 2025 | Authorized by Priya Demirci (Administrative Services Manager)

## Approved calendar and access

Move weekends: 7–8 February 2026, 14–15 February 2026, and 21–22 February 2026. Physical work is permitted Saturday and Sunday only. Building and loading access: 07:00–18:00. Annex access: 08:00–19:00. Both vacated floors must be fully cleared and handback-ready by 18:00 on 22 February 2026.

Loading dock: one vehicle at a time; each vehicle arrival requires a 30-minute turnover before the next vehicle. Freight elevator E1 is the only elevator: one reservation at a time, 45 minutes per trip including loading/unloading, with a 15-minute turnover between reservations. Elevator attendant is billed in 30-minute blocks, 1-block minimum.

## Swing floor and records vault

Swing Floor S is available from 07:00 on 7 February. Only one department may occupy S at a time; occupancy continues across nights and weekends until that department physically departs for its final annex destination. IT may use S only as a temporary stage and must leave S before another department can stage.

Records Vault access is escorted by Linnea Laurent only during 14 February 09:00–12:00 and 21 February 09:00–11:00. All opening, handling and closing activity must remain within an escort interval. Escort billing is $120/hour in quarter-hour increments, 1-hour minimum per continuous window.

## Rates and contract terms

Crew regular rate: $180 per crew-hour; premium rate: 1.5× regular ($270 per crew-hour) after four consecutive paid hours in a crew-day. Mobilization: $350 per crew mobilization, one per crew per day. Freight vehicle block: $900 per vehicle movement. Elevator attendant: $75 per 30-minute block. Vault escort: $120/hour. No separate charge for empty-tote return trips when included in the row note.

Premium interpretation required for the IT chain: the 1.0-hour paid staging interval on 7 February is treated here as paid time under employer control and therefore does not reset the consecutive-hours clock. This is the continuing-clock branch; premium begins after four paid hours.

## Department decisions and comment log

| ID | Comment | Disposition | Owner | Due |
| --- | --- | --- | --- | --- |
| C-01 | Leonie Sandoval must have a bookable sequence on 2 January. | Incorporated: this revised workpaper is the booking basis. | Leonie Sandoval | 2026-01-02 |
| C-02 | IT must stage on S on Weekend 1 and finish in Annex Floor 3 on Weekend 2 after network cutover. | Incorporated as IT-01A / IT-01B split with persistent S occupancy. | Maren Chakraborty | 2026-01-05 |
| C-03 | Records vault work must use the amended escorted windows. | Incorporated: REC-01 scheduled 14 Feb within 09:00–12:00 escort. | Linnea Laurent | 2026-01-16 |
| C-04 | Legal final destination is Annex Floor 3, not Floor 2. | Incorporated: LEG-01 destination changed to Annex Floor 3. | Priya Demirci | 2026-01-09 |
| C-05 | Freight capacity is 600 cu ft per vehicle block. | Incorporated: OPS-01 uses two blocks; all other loads fit one. | Leonie Sandoval | 2026-01-02 |
| C-06 | Single-elevator conflict in draft must be removed by resequencing. | Incorporated: reservations are sequential and displayed explicitly. | Leonie Sandoval | 2026-01-02 |
| C-07 | Confirm Annex Floor 3 network cutover before IT final placement. | Outstanding action: confirm cutover slot before IT-01B. | Maren Chakraborty | 2026-02-06 |
| C-08 | Client-ready summary required for Magda Carmody. | Incorporated: accompanying brief issued with this plan. | Priya Demirci | 2026-01-06 |

## Changed facts / row exceptions

FIN-01 includes the empty-tote return within its stated crew time and one vehicle block. IT-01 is explicitly split into a Weekend 1 stage and Weekend 2 final placement. OPS-01 quantity is 600 cu ft per vehicle block and requires two blocks. COM-01 may move only after OPS-01 clears the dock. All notes in the draft workbook remain authoritative where they conflict with ordinary columns.