## Schedule
Wexmoor / Foxglove implementation plan — schedule
Launch: 14 October 2025 ¦ Window: 02 Sep–10 Oct 2025 ¦ Planning basis: Wexmoor acceptance log
Activity ID | Activity | Owner(s) | Effort (staff-h) | Start | Finish | Predecessors | BPV required | Room / constraint | Status
A01 | Mobilisation and scope confirmation | Efua Seaborne | 8 | 2025-09-02 | 2025-09-02 | — | No | — | Planned
A02 | Current-state workflow mapping | Hilde Maldonado | 12 | 2025-09-03 | 2025-09-04 | A01 | No | — | Planned
A03 | Interface and configuration specification | Kenji Petrosyan | 24 | 2025-09-03 | 2025-09-05 | A01 | No | — | Planned
A04 | Booking configuration build | Kenji Petrosyan | 32 | 2025-09-08 | 2025-09-11 | A03 | No | — | Planned
A05 | Patient-booking data extract and cleanse | Meera Calloway | 18 | 2025-09-03 | 2025-09-05 | A01 | No | — | Planned
A06 | Data-load rehearsal | Meera Calloway | 12 | 2025-09-12 | 2025-09-15 | A04, A05 | No | — | Planned
A07 | Configuration validation | Kenji Petrosyan | 16 | 2025-09-16 | 2025-09-17 | A06 | Yes | — | Planned
A08 | Integration test round 1 | Kenji Petrosyan | 12 | 2025-09-18 | 2025-09-19 | A07 | Yes | — | Planned
A09 | Integration test round 2 | Kenji Petrosyan | 12 | 2025-09-25 | 2025-09-26 | A08 | Yes | — | Planned
A10 | Defect triage and retest | Kenji Petrosyan | 16 | 2025-09-29 | 2025-09-30 | A09 | Yes | — | Planned
A11 | Training materials | Olamide Elbaz | 14 | 2025-09-08 | 2025-09-09 | A02 | No | — | Planned
A12 | Trainer preparation | Olamide Elbaz | 7 | 2025-09-10 | 2025-09-10 | A11 | No | — | Planned
A13 | Staff training session 1 | Olamide Elbaz; Hilde Maldonado | 12 | 2025-09-11 | 2025-09-11 | A12 | No | Training room | Planned
A14 | Staff training session 2 | Olamide Elbaz; Hilde Maldonado | 12 | 2025-09-12 | 2025-09-12 | A12 | No | Training room | Planned
A15 | Cutover rehearsal | Kenji Petrosyan | 16 | 2025-10-01 | 2025-10-02 | A10 | Yes | — | Planned
A16 | Launch-readiness review | Efua Seaborne | 8 | 2025-10-03 | 2025-10-03 | A14, A15 | No | — | Planned

## Daily Allocations
Daily allocation detail (all scheduled entries)
One row per activity/resource/date; hours are staff-hours.
Activity ID | Activity | Resource | Date | Hours | Time slot | Notes
A01 | Mobilisation and scope confirmation | Efua Seaborne | 2025-09-02 | 8 | 08:00-16:00
A02 | Current-state workflow mapping | Hilde Maldonado | 2025-09-03 | 6 | 09:00-15:00
A02 | Current-state workflow mapping | Hilde Maldonado | 2025-09-04 | 6 | 09:00-15:00
A03 | Interface and configuration specification | Kenji Petrosyan | 2025-09-03 | 8 | 08:00-16:00
A03 | Interface and configuration specification | Kenji Petrosyan | 2025-09-04 | 8 | 08:00-16:00
A03 | Interface and configuration specification | Kenji Petrosyan | 2025-09-05 | 8 | 08:00-16:00
A04 | Booking configuration build | Kenji Petrosyan | 2025-09-08 | 8 | 08:00-16:00
A04 | Booking configuration build | Kenji Petrosyan | 2025-09-09 | 8 | 08:00-16:00
A04 | Booking configuration build | Kenji Petrosyan | 2025-09-10 | 8 | 08:00-16:00
A04 | Booking configuration build | Kenji Petrosyan | 2025-09-11 | 8 | 08:00-16:00
A05 | Patient-booking data extract and cleanse | Meera Calloway | 2025-09-03 | 6 | 09:00-15:00
A05 | Patient-booking data extract and cleanse | Meera Calloway | 2025-09-04 | 6 | 09:00-15:00
A05 | Patient-booking data extract and cleanse | Meera Calloway | 2025-09-05 | 6 | 09:00-15:00
A06 | Data-load rehearsal | Meera Calloway | 2025-09-12 | 6 | 09:00-15:00
A06 | Data-load rehearsal | Meera Calloway | 2025-09-15 | 6 | 09:00-15:00
A07 | Configuration validation | Kenji Petrosyan | 2025-09-16 | 8 | 08:00-16:00 | BPV-certified
A07 | Configuration validation | Kenji Petrosyan | 2025-09-17 | 8 | 08:00-16:00 | BPV-certified
A08 | Integration test round 1 | Kenji Petrosyan | 2025-09-18 | 8 | 08:00-16:00 | BPV-certified
A08 | Integration test round 1 | Kenji Petrosyan | 2025-09-19 | 4 | 08:00-12:00 | BPV-certified
A09 | Integration test round 2 | Kenji Petrosyan | 2025-09-25 | 8 | 08:00-16:00 | BPV-certified
A09 | Integration test round 2 | Kenji Petrosyan | 2025-09-26 | 4 | 08:00-12:00 | BPV-certified
A10 | Defect triage and retest | Kenji Petrosyan | 2025-09-29 | 8 | 08:00-16:00 | BPV-certified
A10 | Defect triage and retest | Kenji Petrosyan | 2025-09-30 | 8 | 08:00-16:00 | BPV-certified
A11 | Training materials | Olamide Elbaz | 2025-09-08 | 7 | 09:00-16:00
A11 | Training materials | Olamide Elbaz | 2025-09-09 | 7 | 09:00-16:00
A12 | Trainer preparation | Olamide Elbaz | 2025-09-10 | 7 | 09:00-16:00
A13 | Staff training session 1 | Olamide Elbaz | 2025-09-11 | 6 | 09:00-15:00 | Two-person session
A13 | Staff training session 1 | Hilde Maldonado | 2025-09-11 | 6 | 09:00-15:00 | Two-person session
A14 | Staff training session 2 | Olamide Elbaz | 2025-09-12 | 6 | 09:00-15:00 | Two-person session
A14 | Staff training session 2 | Hilde Maldonado | 2025-09-12 | 6 | 09:00-15:00 | Two-person session
A15 | Cutover rehearsal | Kenji Petrosyan | 2025-10-01 | 8 | 08:00-16:00 | BPV-certified
A15 | Cutover rehearsal | Kenji Petrosyan | 2025-10-02 | 8 | 08:00-16:00 | BPV-certified
A16 | Launch-readiness review | Efua Seaborne | 2025-10-03 | 8 | 08:00-16:00

## Budget
Budget by activity and resource
Line cost = scheduled hours × frozen charge rate.
Activity ID | Activity | Resource | Hours | Rate / hour | Line cost | Basis
A01 | Mobilisation and scope confirmation | Efua Seaborne | 8 | 125 | 1000 | Scheduled allocation
A02 | Current-state workflow mapping | Hilde Maldonado | 6 | 110 | 660 | Scheduled allocation
A02 | Current-state workflow mapping | Hilde Maldonado | 6 | 110 | 660 | Scheduled allocation
A03 | Interface and configuration specification | Kenji Petrosyan | 8 | 155 | 1240 | Scheduled allocation
A03 | Interface and configuration specification | Kenji Petrosyan | 8 | 155 | 1240 | Scheduled allocation
A03 | Interface and configuration specification | Kenji Petrosyan | 8 | 155 | 1240 | Scheduled allocation
A04 | Booking configuration build | Kenji Petrosyan | 8 | 155 | 1240 | Scheduled allocation
A04 | Booking configuration build | Kenji Petrosyan | 8 | 155 | 1240 | Scheduled allocation
A04 | Booking configuration build | Kenji Petrosyan | 8 | 155 | 1240 | Scheduled allocation
A04 | Booking configuration build | Kenji Petrosyan | 8 | 155 | 1240 | Scheduled allocation
A05 | Patient-booking data extract and cleanse | Meera Calloway | 6 | 100 | 600 | Scheduled allocation
A05 | Patient-booking data extract and cleanse | Meera Calloway | 6 | 100 | 600 | Scheduled allocation
A05 | Patient-booking data extract and cleanse | Meera Calloway | 6 | 100 | 600 | Scheduled allocation
A06 | Data-load rehearsal | Meera Calloway | 6 | 100 | 600 | Scheduled allocation
A06 | Data-load rehearsal | Meera Calloway | 6 | 100 | 600 | Scheduled allocation
A07 | Configuration validation | Kenji Petrosyan | 8 | 155 | 1240 | Scheduled allocation
A07 | Configuration validation | Kenji Petrosyan | 8 | 155 | 1240 | Scheduled allocation
A08 | Integration test round 1 | Kenji Petrosyan | 8 | 155 | 1240 | Scheduled allocation
A08 | Integration test round 1 | Kenji Petrosyan | 4 | 155 | 620 | Scheduled allocation
A09 | Integration test round 2 | Kenji Petrosyan | 8 | 155 | 1240 | Scheduled allocation
A09 | Integration test round 2 | Kenji Petrosyan | 4 | 155 | 620 | Scheduled allocation
A10 | Defect triage and retest | Kenji Petrosyan | 8 | 155 | 1240 | Scheduled allocation
A10 | Defect triage and retest | Kenji Petrosyan | 8 | 155 | 1240 | Scheduled allocation
A11 | Training materials | Olamide Elbaz | 7 | 95 | 665 | Scheduled allocation
A11 | Training materials | Olamide Elbaz | 7 | 95 | 665 | Scheduled allocation
A12 | Trainer preparation | Olamide Elbaz | 7 | 95 | 665 | Scheduled allocation
A13 | Staff training session 1 | Olamide Elbaz | 6 | 95 | 570 | Scheduled allocation
A13 | Staff training session 1 | Hilde Maldonado | 6 | 110 | 660 | Scheduled allocation
A14 | Staff training session 2 | Olamide Elbaz | 6 | 95 | 570 | Scheduled allocation
A14 | Staff training session 2 | Hilde Maldonado | 6 | 110 | 660 | Scheduled allocation
A15 | Cutover rehearsal | Kenji Petrosyan | 8 | 155 | 1240 | Scheduled allocation
A15 | Cutover rehearsal | Kenji Petrosyan | 8 | 155 | 1240 | Scheduled allocation
A16 | Launch-readiness review | Efua Seaborne | 8 | 125 | 1000 | Scheduled allocation
TOTAL |  |  |  |  | 30615

## Resource Summary
Resource capacity summary
Available hours exclude recorded unavailable dates.
Resource | Role | Daily cap (h) | Available hours in window | Scheduled hours | Remaining capacity | Rate / hour | Certification
Efua Seaborne | project management specialist | 8 | 224 | 16 | 208 | 125 | None
Kenji Petrosyan | technical implementation lead | 8 | 216 | 128 | 88 | 155 | Booking Platform Validation
Hilde Maldonado | workflow and training specialist | 6 | 162 | 24 | 138 | 110 | None
Olamide Elbaz | training lead | 7 | 175 | 33 | 142 | 95 | None
Meera Calloway | data analyst | 6 | 168 | 30 | 138 | 100 | None

## Daily Capacity
Daily capacity by person and working day
Remaining capacity = available minus scheduled.
Date | Resource | Available hours | Scheduled hours | Remaining capacity | Unavailable? | Activities scheduled | Check
2025-09-02 | Efua Seaborne | 8 | 8 | 0 | No | A01 | OK
2025-09-02 | Kenji Petrosyan | 8 | 0 | 8 | No | — | OK
2025-09-02 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-09-02 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-09-02 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-09-03 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-09-03 | Kenji Petrosyan | 8 | 8 | 0 | No | A03 | OK
2025-09-03 | Hilde Maldonado | 6 | 6 | 0 | No | A02 | OK
2025-09-03 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-09-03 | Meera Calloway | 6 | 6 | 0 | No | A05 | OK
2025-09-04 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-09-04 | Kenji Petrosyan | 8 | 8 | 0 | No | A03 | OK
2025-09-04 | Hilde Maldonado | 6 | 6 | 0 | No | A02 | OK
2025-09-04 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-09-04 | Meera Calloway | 6 | 6 | 0 | No | A05 | OK
2025-09-05 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-09-05 | Kenji Petrosyan | 8 | 8 | 0 | No | A03 | OK
2025-09-05 | Hilde Maldonado | 0 | 0 | 0 | Yes | — | OK
2025-09-05 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-09-05 | Meera Calloway | 6 | 6 | 0 | No | A05 | OK
2025-09-08 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-09-08 | Kenji Petrosyan | 8 | 8 | 0 | No | A04 | OK
2025-09-08 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-09-08 | Olamide Elbaz | 7 | 7 | 0 | No | A11 | OK
2025-09-08 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-09-09 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-09-09 | Kenji Petrosyan | 8 | 8 | 0 | No | A04 | OK
2025-09-09 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-09-09 | Olamide Elbaz | 7 | 7 | 0 | No | A11 | OK
2025-09-09 | Meera Calloway | 0 | 0 | 0 | Yes | — | OK
2025-09-10 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-09-10 | Kenji Petrosyan | 8 | 8 | 0 | No | A04 | OK
2025-09-10 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-09-10 | Olamide Elbaz | 7 | 7 | 0 | No | A12 | OK
2025-09-10 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-09-11 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-09-11 | Kenji Petrosyan | 8 | 8 | 0 | No | A04 | OK
2025-09-11 | Hilde Maldonado | 6 | 6 | 0 | No | A13 | OK
2025-09-11 | Olamide Elbaz | 7 | 6 | 1 | No | A13 | OK
2025-09-11 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-09-12 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-09-12 | Kenji Petrosyan | 8 | 0 | 8 | No | — | OK
2025-09-12 | Hilde Maldonado | 6 | 6 | 0 | No | A14 | OK
2025-09-12 | Olamide Elbaz | 7 | 6 | 1 | No | A14 | OK
2025-09-12 | Meera Calloway | 6 | 6 | 0 | No | A06 | OK
2025-09-15 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-09-15 | Kenji Petrosyan | 8 | 0 | 8 | No | — | OK
2025-09-15 | Hilde Maldonado | 0 | 0 | 0 | Yes | — | OK
2025-09-15 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-09-15 | Meera Calloway | 6 | 6 | 0 | No | A06 | OK
2025-09-16 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-09-16 | Kenji Petrosyan | 8 | 8 | 0 | No | A07 | OK
2025-09-16 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-09-16 | Olamide Elbaz | 0 | 0 | 0 | Yes | — | OK
2025-09-16 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-09-17 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-09-17 | Kenji Petrosyan | 8 | 8 | 0 | No | A07 | OK
2025-09-17 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-09-17 | Olamide Elbaz | 0 | 0 | 0 | Yes | — | OK
2025-09-17 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-09-18 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-09-18 | Kenji Petrosyan | 8 | 8 | 0 | No | A08 | OK
2025-09-18 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-09-18 | Olamide Elbaz | 0 | 0 | 0 | Yes | — | OK
2025-09-18 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-09-19 | Efua Seaborne | 0 | 0 | 0 | Yes | — | OK
2025-09-19 | Kenji Petrosyan | 8 | 4 | 4 | No | A08 | OK
2025-09-19 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-09-19 | Olamide Elbaz | 0 | 0 | 0 | Yes | — | OK
2025-09-19 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-09-22 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-09-22 | Kenji Petrosyan | 8 | 0 | 8 | No | — | OK
2025-09-22 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-09-22 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-09-22 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-09-23 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-09-23 | Kenji Petrosyan | 0 | 0 | 0 | Yes | — | OK
2025-09-23 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-09-23 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-09-23 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-09-24 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-09-24 | Kenji Petrosyan | 0 | 0 | 0 | Yes | — | OK
2025-09-24 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-09-24 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-09-24 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-09-25 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-09-25 | Kenji Petrosyan | 8 | 8 | 0 | No | A09 | OK
2025-09-25 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-09-25 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-09-25 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-09-26 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-09-26 | Kenji Petrosyan | 8 | 4 | 4 | No | A09 | OK
2025-09-26 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-09-26 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-09-26 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-09-29 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-09-29 | Kenji Petrosyan | 8 | 8 | 0 | No | A10 | OK
2025-09-29 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-09-29 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-09-29 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-09-30 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-09-30 | Kenji Petrosyan | 8 | 8 | 0 | No | A10 | OK
2025-09-30 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-09-30 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-09-30 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-10-01 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-10-01 | Kenji Petrosyan | 8 | 8 | 0 | No | A15 | OK
2025-10-01 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-10-01 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-10-01 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-10-02 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-10-02 | Kenji Petrosyan | 8 | 8 | 0 | No | A15 | OK
2025-10-02 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-10-02 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-10-02 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-10-03 | Efua Seaborne | 8 | 8 | 0 | No | A16 | OK
2025-10-03 | Kenji Petrosyan | 8 | 0 | 8 | No | — | OK
2025-10-03 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-10-03 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-10-03 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-10-06 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-10-06 | Kenji Petrosyan | 8 | 0 | 8 | No | — | OK
2025-10-06 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-10-06 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-10-06 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-10-07 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-10-07 | Kenji Petrosyan | 8 | 0 | 8 | No | — | OK
2025-10-07 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-10-07 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-10-07 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-10-08 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-10-08 | Kenji Petrosyan | 8 | 0 | 8 | No | — | OK
2025-10-08 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-10-08 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-10-08 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-10-09 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-10-09 | Kenji Petrosyan | 8 | 0 | 8 | No | — | OK
2025-10-09 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-10-09 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-10-09 | Meera Calloway | 6 | 0 | 6 | No | — | OK
2025-10-10 | Efua Seaborne | 8 | 0 | 8 | No | — | OK
2025-10-10 | Kenji Petrosyan | 8 | 0 | 8 | No | — | OK
2025-10-10 | Hilde Maldonado | 6 | 0 | 6 | No | — | OK
2025-10-10 | Olamide Elbaz | 7 | 0 | 7 | No | — | OK
2025-10-10 | Meera Calloway | 6 | 0 | 6 | No | — | OK

## Exceptions & Evidence
Exceptions and evidence register
Facts, planning values and unresolved status are shown separately.
Exception ID | Topic | Evidence references | Source facts | Planning value used | Variance / impact | Status | Affected activities
EX-01 | Integration testing effort | EV-TEST-WEX-2025-08-18; EV-TEST-FOX-2025-08-20 | Wexmoor: 24 staff-h (12+12). Foxglove: 32 staff-h (16+16). | 24 staff-h (12 per round), per governance precedence | 8 staff-h alternate estimate; £1,240 at Kenji rate | Unresolved factual exception | A08, A09
EX-02 | Training staffing | EV-TRAIN-WEX-2025-08-19; EV-TRAIN-FOX-2025-08-21 | Two named trainers confirmed: Olamide + Hilde. Foxglove requests three; no third named resource. | Schedule uses only two confirmed named trainers (6h each/session) | Additional requested trainer not represented; capacity implication remains unresolved | Unresolved factual exception | A13, A14
EX-03 | Calendar / governance basis | governance_and_calendar.pdf | Window, blackout, certification, separation and deadline rules frozen. | Applied to all allocations | Readiness completes 03-Oct-2025 within 10-Oct deadline | Settled planning convention | All

## Calendar
Calendar view — every scheduled entry exposed
No hidden rows; one row per allocation.
Date | Time slot | Activity ID | Activity | Resource | Hours
2025-09-02 | 08:00-16:00 | A01 | Mobilisation and scope confirmation | Efua Seaborne | 8
2025-09-03 | 08:00-16:00 | A03 | Interface and configuration specification | Kenji Petrosyan | 8
2025-09-03 | 09:00-15:00 | A02 | Current-state workflow mapping | Hilde Maldonado | 6
2025-09-03 | 09:00-15:00 | A05 | Patient-booking data extract and cleanse | Meera Calloway | 6
2025-09-04 | 08:00-16:00 | A03 | Interface and configuration specification | Kenji Petrosyan | 8
2025-09-04 | 09:00-15:00 | A02 | Current-state workflow mapping | Hilde Maldonado | 6
2025-09-04 | 09:00-15:00 | A05 | Patient-booking data extract and cleanse | Meera Calloway | 6
2025-09-05 | 08:00-16:00 | A03 | Interface and configuration specification | Kenji Petrosyan | 8
2025-09-05 | 09:00-15:00 | A05 | Patient-booking data extract and cleanse | Meera Calloway | 6
2025-09-08 | 08:00-16:00 | A04 | Booking configuration build | Kenji Petrosyan | 8
2025-09-08 | 09:00-16:00 | A11 | Training materials | Olamide Elbaz | 7
2025-09-09 | 08:00-16:00 | A04 | Booking configuration build | Kenji Petrosyan | 8
2025-09-09 | 09:00-16:00 | A11 | Training materials | Olamide Elbaz | 7
2025-09-10 | 08:00-16:00 | A04 | Booking configuration build | Kenji Petrosyan | 8
2025-09-10 | 09:00-16:00 | A12 | Trainer preparation | Olamide Elbaz | 7
2025-09-11 | 08:00-16:00 | A04 | Booking configuration build | Kenji Petrosyan | 8
2025-09-11 | 09:00-15:00 | A13 | Staff training session 1 | Hilde Maldonado | 6
2025-09-11 | 09:00-15:00 | A13 | Staff training session 1 | Olamide Elbaz | 6
2025-09-12 | 09:00-15:00 | A06 | Data-load rehearsal | Meera Calloway | 6
2025-09-12 | 09:00-15:00 | A14 | Staff training session 2 | Hilde Maldonado | 6
2025-09-12 | 09:00-15:00 | A14 | Staff training session 2 | Olamide Elbaz | 6
2025-09-15 | 09:00-15:00 | A06 | Data-load rehearsal | Meera Calloway | 6
2025-09-16 | 08:00-16:00 | A07 | Configuration validation | Kenji Petrosyan | 8
2025-09-17 | 08:00-16:00 | A07 | Configuration validation | Kenji Petrosyan | 8
2025-09-18 | 08:00-16:00 | A08 | Integration test round 1 | Kenji Petrosyan | 8
2025-09-19 | 08:00-12:00 | A08 | Integration test round 1 | Kenji Petrosyan | 4
2025-09-25 | 08:00-16:00 | A09 | Integration test round 2 | Kenji Petrosyan | 8
2025-09-26 | 08:00-12:00 | A09 | Integration test round 2 | Kenji Petrosyan | 4
2025-09-29 | 08:00-16:00 | A10 | Defect triage and retest | Kenji Petrosyan | 8
2025-09-30 | 08:00-16:00 | A10 | Defect triage and retest | Kenji Petrosyan | 8
2025-10-01 | 08:00-16:00 | A15 | Cutover rehearsal | Kenji Petrosyan | 8
2025-10-02 | 08:00-16:00 | A15 | Cutover rehearsal | Kenji Petrosyan | 8
2025-10-03 | 08:00-16:00 | A16 | Launch-readiness review | Efua Seaborne | 8