Alderwick video programme | rebaseline & variance

To Brigid Alcantara and Operations • As of 20 Aug 2026 • Source: PMO register, activity extract, bookings and correspondence

DELIVERY INTERPRETATION AND STATUS  |  “Delivery” in this record means Accepted master: acceptance recorded after editorial, accessibility, jurisdiction release and acceptance checks. The dated rebaseline is an internal forecast, not a client commitment. Contractual baselines remain unchanged; no change control authorises Camila Reinholt’s 05 Aug informal statement that all remaining modules would be delivered by 30 Sep.

Variance record | completed modules

Fourteen modules are complete. Eleven accepted masters were late against their contractual accepted-master baseline; AU-01–AU-03 met baseline. The variance below uses the supplied UK working calendar (including the 04 May and 25 May holidays).

| Completed module | Path | Baseline | Accepted master | Variance (bd) | Observed chain | Finding |
| --- | --- | --- | --- | --- | --- | --- |
| AU-01 | En | 02 Feb 2026 | 02 Feb 2026 | +0 | Script → SME → post → release | Within plan |
| AU-02 | Sc | 16 Feb 2026 | 16 Feb 2026 | +0 | Script → SME → post → release | Within plan |
| AU-03 | En | 02 Mar 2026 | 02 Mar 2026 | +0 | Script → SME → post → release | Within plan |
| AU-04 | Sc | 16 Mar 2026 | 18 Mar 2026 | +2 | Script → SME → post → release | Queue waited |
| AU-05 | En | 30 Mar 2026 | 02 Apr 2026 | +3 | Script → SME → post → release | Queue waited |
| AU-06 | Sc | 13 Apr 2026 | 17 Apr 2026 | +4 | Script → SME → post → release | Queue waited |
| AU-07 | En | 27 Apr 2026 | 04 May 2026 | +4 | Script → SME → post → release | Queue waited |
| AU-08 | Sc | 11 May 2026 | 14 May 2026 | +3 | Script → SME → post → release | Queue waited |
| AU-09 | En | 25 May 2026 | 01 Jun 2026 | +5 | Script → SME → post → release | Queue waited |
| AU-10 | Sc | 08 Jun 2026 | 11 Jun 2026 | +3 | Script → SME → post → release | Queue waited |
| AU-11 | En | 22 Jun 2026 | 29 Jun 2026 | +5 | Script → SME → post → release | Queue waited |
| AU-12 | Sc | 06 Jul 2026 | 10 Jul 2026 | +4 | Script → SME → post → release | Queue waited |
| AU-13 | En | 20 Jul 2026 | 27 Jul 2026 | +5 | Script → SME → post → release | Queue waited |
| AU-14 | Sc | 03 Aug 2026 | 07 Aug 2026 | +4 | Script → SME → post → release | Queue waited |

Causal finding. The repeated critical-path condition is the single Alderwick subject-expert approval queue: on every late module it waits after script readiness before edit can start, consuming float and propagating into accepted-master dates. The activity chain, not the number of incidents, supports that finding. Partial asset receipts affected AU-05, AU-09 and AU-12 but were completed before script work became controlling. Northline’s block availability amplified late approval on AU-07 and AU-11 by moving grade to the next booked block; it did not create the recurring initial wait. Dropped review threads on AU-08 and AU-12 were reconstructed from email and did not move their recorded accepted-master dates: they are an audit/rework control failure, not the recurring variance cause.

Rebaseline controls now in force

| Control | Accountable owner | Observable operating point |
| --- | --- | --- |
| Approval flow: release no more than two scripts to the SME in a working week; reserve the two-day review sequence shown below. | Vantridge producer; Alderwick subject expert | Daily queue log records submitted, slot, decision and oldest waiting script. Any unallocated script at 10:00 triggers exception control. |
| Asset readiness: producer signs a module checklist (source media, permissions, script inputs and jurisdiction brief) before editorial starts. | Alderwick asset liaison | Checklist is attached to the module issue record; incomplete receipt is HOLD, not production-ready. |
| Review record: export comments to the module issue log; producer reconciles every comment and obtains reviewer acknowledgement before the next gate. | Vantridge producer | A vanished thread is a missing record, not approval; the signed reconciliation is the gate evidence. |
| Supplier control: confirm Northline module allocation before edit completes. | Vantridge post supervisor | Booking block and two-module capacity are entered in the control log. |

Accepted-master rebaseline | remaining in-scope modules

Internal forecast — mandatory gates retained. AU-19 is out of scope and is not part of this schedule.

Gate dates are completion dates and follow finish-to-start dependencies. AU-17’s 25 Aug asset target is an unconfirmed planning dependency; its dated chain begins only if the signed readiness checklist is complete. “Promise variance” is against Camila’s 30 Sep informal statement; “baseline variance” is against the contractual accepted-master baseline.

| Module / path | Asset ready¹ | Script ready² | SME approval³ | Edit complete⁴ | Grade complete⁵ | Editorial review⁶ | Client review record⁷ |
| --- | --- | --- | --- | --- | --- | --- | --- |
| AU-15 England | 24 Aug 2026 | 26 Aug 2026 | 28 Aug 2026 | 02 Sep 2026 | 08 Sep 2026 | 09 Sep 2026 | 11 Sep 2026 |
| AU-16 Scotland | 25 Aug 2026 | 27 Aug 2026 | 31 Aug 2026 | 03 Sep 2026 | 08 Sep 2026 | 09 Sep 2026 | 11 Sep 2026 |
| AU-17 England | 26 Aug 2026* | 28 Aug 2026 | 01 Sep 2026 | 04 Sep 2026 | 22 Sep 2026 | 23 Sep 2026 | 25 Sep 2026 |
| AU-18 Scotland | 27 Aug 2026 | 31 Aug 2026 | 07 Sep 2026 | 10 Sep 2026 | 06 Oct 2026 | 07 Oct 2026 | 09 Oct 2026 |

Owners: ¹Alderwick asset liaison / Vantridge producer; ²Vantridge editorial lead; ³Alderwick subject expert; ⁴Vantridge post supervisor; ⁵Northline Colour; ⁶Vantridge editorial lead; ⁷Alderwick reviewer / Vantridge producer.

| Module | Accessibility gate⁸ | Jurisdiction release⁹ | Accepted master¹⁰ | Contract baseline | vs baseline (bd) | vs 30 Sep (bd) | Schedule status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| AU-15 | England accessibility 15 Sep 2026 | England release QA 16 Sep 2026 | 17 Sep 2026 | 15 Sep 2026 | +2 | -9 | Forecast |
| AU-16 | Scotland accessibility adaptation 16 Sep 2026 | Scotland release check 18 Sep 2026 | 21 Sep 2026 | 22 Sep 2026 | -1 | -7 | Forecast |
| AU-17 | England accessibility 29 Sep 2026 | England release QA 30 Sep 2026 | 01 Oct 2026 | 24 Sep 2026 | +5 | +1 | Forecast |
| AU-18 | Scotland accessibility adaptation 14 Oct 2026 | Scotland release check 16 Oct 2026 | 19 Oct 2026 | 29 Sep 2026 | +14 | +13 | Forecast |

Owners: ⁸Vantridge accessibility lead; ⁹England: Vantridge release manager. Scotland: Alderwick Scotland release lead; ¹⁰Alderwick Acceptance Lead. Scotland takes two working days longer after client review than England: three-day accessibility adaptation and two-day Scotland release check, versus England’s two-day accessibility and one-day release QA.

Exception control | applies to every scheduled handoff

| Trigger | Immediate treatment | Accountable escalation | Record / reforecast |
| --- | --- | --- | --- |
| At the scheduled gate, approval is absent; asset checklist is incomplete; review record is missing; or Northline allocation is unavailable. | Set module to HOLD; do not start its successor and do not infer approval. Preserve the evidence, issue log and current forecast date. | Gate owner notifies Vantridge producer the same working day. Producer escalates approval / assets / release to the named Alderwick owner; supplier issue to post supervisor and Northline booking desk. | Producer logs decision, owner and next checkpoint, recalculates the first feasible downstream dates using the calendar, SME capacity and grade blocks, and routes any client-date change to Nikolai Rosenthal under §7.1. |

Implication

The forecast does not convert the 30 Sep statement into a commitment. AU-15 is forecast 17 Sep; AU-16 05 Oct; AU-17 01 Oct; AU-18 19 Oct as accepted masters. These dates retain editorial, client review, accessibility, jurisdiction release and acceptance gates; they are the current operational record for the schedule requested by Nikolai Rosenthal.