## Inputs
CRAGSIDE INVITATIONAL — HIGHLIGHTS EDIT INPUTS
Operations handoff ¦ supplied planning tables ¦ export 2026-08-24
Residual helper
Package ID | Day | Client | Release / Event | Package title | Edit min | Finish min | Finish required | Caption required | Priority | Uplink required | Baseline uplink | Baseline delivery | Scope | Notes
D1-A01 | Day 1 | Ashgrove Cooperative | 2026-09-07 10:30 | Morning recap | 60 | 30 | Yes | Yes | High | Yes | Slot A | 2026-09-07 20:30 | In scope
D1-A02 | Day 1 | Tanneryside Provisions | 2026-09-07 09:00 | Field package | 75 | 0 | No | No | Medium | No |  | 2026-09-07 10:30 | In scope
D1-A03 | Day 1 | Ashgrove Cooperative | 2026-09-07 11:30 | Feature cut | 60 | 30 | Yes | Yes | High | No |  | 2026-09-07 20:10 | In scope | Caption window held at 20:10
D1-A04 | Day 1 | Tanneryside Provisions | 2026-09-07 14:00 | Interview cut | 90 | 30 | Yes | No | Medium | No |  | 2026-09-07 17:00 | In scope
D1-FINAL | Day 1 | Ashgrove Cooperative | 2026-09-07 18:00 | Evening final | 120 | 40 | Yes | Yes | Critical | Yes | Slot A | 2026-09-07 20:50 | In scope | Late-final scenario: release 19:00; move to Slot B
D2-B01 | Day 2 | Tanneryside Provisions | 2026-09-08 10:30 | Morning recap | 60 | 30 | Yes | Yes | High | Yes | Slot A | 2026-09-08 20:30 | In scope
D2-B02 | Day 2 | Ashgrove Cooperative | 2026-09-08 10:00 | Field package | 75 | 0 | No | No | Medium | No |  | 2026-09-08 11:30 | In scope
D2-B03 | Day 2 | Tanneryside Provisions | 2026-09-08 12:00 | Feature cut | 60 | 30 | Yes | Yes | High | No |  | 2026-09-08 20:10 | In scope | Caption window held at 20:10
D2-B04 | Day 2 | Ashgrove Cooperative | 2026-09-08 15:00 | Interview cut | 90 | 30 | Yes | No | Medium | No |  | 2026-09-08 18:00 | In scope
D2-FINAL | Day 2 | Tanneryside Provisions | 2026-09-08 18:00 | Evening final | 120 | 40 | Yes | Yes | Critical | Yes | Slot A | 2026-09-08 20:50 | In scope | Late-final scenario: release 19:00; move to Slot B
D2-X99 | Day 2 | Ashgrove Cooperative | 2026-09-08 13:00 | Duplicate hold | 45 | 0 | No | No | Low | No |  | 2026-09-08 15:00 | In scope | Exclude: duplicate of D2-B03; do not schedule
D3-C01 | Day 3 | Ashgrove Cooperative | 2026-09-09 10:30 | Morning recap | 60 | 30 | Yes | Yes | High | Yes | Slot A | 2026-09-09 20:30 | In scope
D3-C02 | Day 3 | Tanneryside Provisions | 2026-09-09 10:00 | Field package | 75 | 0 | No | No | Medium | No |  | 2026-09-09 11:30 | In scope
D3-C03 | Day 3 | Ashgrove Cooperative | 2026-09-09 12:00 | Feature cut | 60 | 30 | Yes | Yes | High | No |  | 2026-09-09 20:10 | In scope | Caption window held at 20:10
D3-C04 | Day 3 | Tanneryside Provisions | 2026-09-09 15:00 | Interview cut | 90 | 30 | Yes | No | Medium | No |  | 2026-09-09 18:00 | In scope
D3-FINAL | Day 3 | Ashgrove Cooperative | 2026-09-09 18:00 | Evening final | 120 | 40 | Yes | Yes | Critical | Yes | Slot A | 2026-09-09 20:50 | In scope | Late-final scenario: release 19:00; move to Slot B
EDITOR AVAILABILITY
Editor ID | Editor name | Day | Available from | Available to
E01 | Amina Okafor | Day 1 | 2026-09-07 07:00 | 2026-09-07 23:00
E02 | Mateo Ruiz | Day 1 | 2026-09-07 07:00 | 2026-09-07 23:00
E03 | Priya Nair | Day 1 | 2026-09-07 07:00 | 2026-09-07 23:00
E04 | Jon Bell | Day 1 | 2026-09-07 07:00 | 2026-09-07 23:00
E05 | Sofia Lind | Day 1 | 2026-09-07 07:00 | 2026-09-07 23:00
E06 | Caleb Wong | Day 1 | 2026-09-07 07:00 | 2026-09-07 23:00
E07 | Nia Brooks | Day 1 | 2026-09-07 07:00 | 2026-09-07 23:00
E08 | Luka Petrov | Day 1 | 2026-09-07 07:00 | 2026-09-07 23:00
E09 | Mara Chen | Day 1 | 2026-09-07 07:00 | 2026-09-07 23:00
E10 | Theo Grant | Day 1 | 2026-09-07 07:00 | 2026-09-07 23:00
E11 | Ivy Mensah | Day 1 | 2026-09-07 07:00 | 2026-09-07 23:00
E12 | Owen Hart | Day 1 | 2026-09-07 07:00 | 2026-09-07 23:00
E01 | Amina Okafor | Day 2 | 2026-09-08 07:00 | 2026-09-08 23:00
E02 | Mateo Ruiz | Day 2 | 2026-09-08 07:00 | 2026-09-08 23:00
E03 | Priya Nair | Day 2 | 2026-09-08 07:00 | 2026-09-08 23:00
E04 | Jon Bell | Day 2 | 2026-09-08 07:00 | 2026-09-08 23:00
E05 | Sofia Lind | Day 2 | 2026-09-08 07:00 | 2026-09-08 23:00
E06 | Caleb Wong | Day 2 | 2026-09-08 07:00 | 2026-09-08 23:00
E07 | Nia Brooks | Day 2 | 2026-09-08 07:00 | 2026-09-08 23:00
E08 | Luka Petrov | Day 2 | 2026-09-08 07:00 | 2026-09-08 23:00
E09 | Mara Chen | Day 2 | 2026-09-08 07:00 | 2026-09-08 23:00
E10 | Theo Grant | Day 2 | 2026-09-08 07:00 | 2026-09-08 23:00
E11 | Ivy Mensah | Day 2 | 2026-09-08 07:00 | 2026-09-08 23:00
E12 | Owen Hart | Day 2 | 2026-09-08 07:00 | 2026-09-08 23:00
E01 | Amina Okafor | Day 3 | 2026-09-09 07:00 | 2026-09-09 23:00
E02 | Mateo Ruiz | Day 3 | 2026-09-09 07:00 | 2026-09-09 23:00
E03 | Priya Nair | Day 3 | 2026-09-09 07:00 | 2026-09-09 23:00
E04 | Jon Bell | Day 3 | 2026-09-09 07:00 | 2026-09-09 23:00
E05 | Sofia Lind | Day 3 | 2026-09-09 07:00 | 2026-09-09 23:00
E06 | Caleb Wong | Day 3 | 2026-09-09 07:00 | 2026-09-09 23:00
E07 | Nia Brooks | Day 3 | 2026-09-09 07:00 | 2026-09-09 23:00
E08 | Luka Petrov | Day 3 | 2026-09-09 07:00 | 2026-09-09 23:00
E09 | Mara Chen | Day 3 | 2026-09-09 07:00 | 2026-09-09 23:00
E10 | Theo Grant | Day 3 | 2026-09-09 07:00 | 2026-09-09 23:00
E11 | Ivy Mensah | Day 3 | 2026-09-09 07:00 | 2026-09-09 23:00
E12 | Owen Hart | Day 3 | 2026-09-09 07:00 | 2026-09-09 23:00
FINISHING BAYS
Bay | Available from | Available to
Bay 1 | 2026-09-07 08:00 | 2026-09-07 23:30
Bay 2 | 2026-09-07 08:00 | 2026-09-07 23:30
Bay 3 | 2026-09-07 08:00 | 2026-09-07 23:30
Bay 4 | 2026-09-07 08:00 | 2026-09-07 23:30
Bay 1 | 2026-09-08 08:00 | 2026-09-08 23:30
Bay 2 | 2026-09-08 08:00 | 2026-09-08 23:30
Bay 3 | 2026-09-08 08:00 | 2026-09-08 23:30
Bay 4 | 2026-09-08 08:00 | 2026-09-08 23:30
Bay 1 | 2026-09-09 08:00 | 2026-09-09 23:30
Bay 2 | 2026-09-09 08:00 | 2026-09-09 23:30
Bay 3 | 2026-09-09 08:00 | 2026-09-09 23:30
Bay 4 | 2026-09-09 08:00 | 2026-09-09 23:30
CAPTION ENCODER WINDOWS
Day | Encoder | Window start | Window end | Staffing
Day 1 | Encoder 1 | 2026-09-07 20:00 | 2026-09-07 21:00 | Vendor staffed
Day 2 | Encoder 1 | 2026-09-08 20:00 | 2026-09-08 21:00 | Vendor staffed
Day 3 | Encoder 1 | 2026-09-09 20:00 | 2026-09-09 21:00 | Vendor staffed
Day 1 | Encoder 1 | 2026-09-07 22:00 | 2026-09-07 23:00 | Vendor staffed
Day 2 | Encoder 1 | 2026-09-08 22:00 | 2026-09-08 23:00 | Vendor staffed
Day 3 | Encoder 1 | 2026-09-09 22:00 | 2026-09-09 23:00 | Vendor staffed
CREW AGREEMENT / TIMING RULES
Rule | Value
Turnaround hours | 10
Meal threshold hours | 6
Meal break minutes | 30
Meal must fall within hours of shift start | 6
Late-final release shift minutes | 60
Late-final uplink movement | Slot A to Slot B
UPLINK SLOTS
Day | Slot | Slot start | Slot end | Capacity
Day 1 | Slot A | 2026-09-07 20:00 | 2026-09-07 21:00 | 2
Day 2 | Slot A | 2026-09-08 20:00 | 2026-09-08 21:00 | 2
Day 3 | Slot A | 2026-09-09 20:00 | 2026-09-09 21:00 | 2
Day 1 | Slot B | 2026-09-07 23:00 | 2026-09-07 23:59 | 2
Day 2 | Slot B | 2026-09-08 23:00 | 2026-09-08 23:59 | 2
Day 3 | Slot B | 2026-09-09 23:00 | 2026-09-09 23:59 | 2