## Cycle Facts
Client | Saltmarsh Press
Valuation anchor | 31 December 2025
Election window assumption | 30 calendar days from election-letter release
Payroll cutoff | 12 June 2026
Form 5500 extension deadline | 30 June 2026
Plan-audit sample window | 22–26 June 2026
Distribution payroll cutoff | 31 July 2026
Distribution release cutoff | 14 August 2026
Trustee availability | Q2 meeting: 14 April 2026
June decision | Payroll cutoff work first; Form 5500 extension work second; plan-audit sample work third; release letters after collision clears

## Milestones
Week or date | Milestone | Owner | Waiting on | Dependency or gate | Planned date
Week 1 ¦ 05 Jan 2026 | Confirm 31 December valuation anchor | Eamon Rasmussen | Saltmarsh Press records | Valuation date fixed: 31 Dec 2025 | 2026-01-05
Week 14 ¦ 30 Mar 2026 | Appraiser valuation draft prepared | Valuation appraiser | Eamon Rasmussen | Uses 31 Dec 2025 valuation anchor | 2026-03-30
Week 15 ¦ 06 Apr 2026 | Appraiser draft review | Javier Rivenburgh | Valuation appraiser | Appraiser draft received | 2026-04-06
Week 16 ¦ 14 Apr 2026 | Trustee approval gate | ESOP trustee | Javier Rivenburgh | Review complete; Q2 trustee meeting available | 2026-04-14
Week 17 ¦ 20 Apr 2026 | Allocation preparation | Eamon Rasmussen | ESOP trustee | Trustee approval required | 2026-04-20
Week 18 ¦ 27 Apr 2026 | Allocation reconciliation | Eamon Rasmussen | Payroll team | Allocation preparation complete | 2026-04-27
Week 19 ¦ 04 May 2026 | Diversification and election-letter preparation | Benefits operations | Eamon Rasmussen | Reconciled allocation inputs | 2026-05-04
Week 20 ¦ 08 Jun 2026 | Payroll cutoff work | Payroll team | Eamon Rasmussen | Cutoff: 12 Jun 2026; protect payroll feed | 2026-06-08
Week 21 ¦ 15 Jun 2026 | Form 5500 extension work | Plan administrator | Eamon Rasmussen | Extension filing due 30 Jun 2026 | 2026-06-15
Week 22 ¦ 22 Jun 2026 | Plan-audit sample work | Plan auditor | Eamon Rasmussen | Sample window: 22–26 Jun 2026 | 2026-06-22
Week 23 ¦ 29 Jun 2026 | Release election letters | Benefits operations | Eamon Rasmussen | Allocation reconciled; June collision cleared | 2026-06-29
Weeks 24–27 ¦ 30 Jun–29 Jul 2026 | Statutory election window (30 calendar days) | Eamon Rasmussen | Eligible participants | Starts on election-letter release | 2026-06-30
Week 28 ¦ 30 Jul 2026 | Retiree distribution preparation | Benefits operations | Eamon Rasmussen | Election window outcome; payroll cutoff 31 Jul 2026 | 2026-07-30
Week 30 ¦ 14 Aug 2026 | Retiree distribution release | Payroll team | Eamon Rasmussen | Distribution files approved; cutoff 14 Aug 2026 | 2026-08-14

## Lists
Status | Handoff confirmed
Not started | Yes
Waiting | No
In progress
Complete
At risk