## Activity Register
Frozen implementation register | Wexmoor Regional Office / Foxglove Services
Activity ID | Activity description | Effort (staff-hours) | Assigned staffing | Predecessors | BPV required | Milestone
A01 | Mobilisation and scope confirmation | 8 | Efua Seaborne | — | No | No
A02 | Current-state workflow mapping | 12 | Hilde Maldonado | A01 | No | No
A03 | Interface and configuration specification | 24 | Kenji Petrosyan | A01 | No | No
A04 | Booking configuration build | 32 | Kenji Petrosyan | A03 | No | No
A05 | Patient-booking data extract and cleanse | 18 | Meera Calloway | A01 | No | No
A06 | Data-load rehearsal | 12 | Meera Calloway | A04, A05 | No | No
A07 | Configuration validation | 16 | Kenji Petrosyan | A06 | Yes | No
A08 | Integration test round 1 | 12 | Kenji Petrosyan | A07 | Yes | No
A09 | Integration test round 2 | 12 | Kenji Petrosyan | A08 | Yes | No
A10 | Defect triage and retest | 16 | Kenji Petrosyan | A09 | Yes | No
A11 | Training materials | 14 | Olamide Elbaz | A02 | No | No
A12 | Trainer preparation | 7 | Olamide Elbaz | A11 | No | No
A13 | Staff training session 1 | 12 | Olamide Elbaz; Hilde Maldonado | A12 | No | No
A14 | Staff training session 2 | 12 | Olamide Elbaz; Hilde Maldonado | A12 | No | No
A15 | Cutover rehearsal | 16 | Kenji Petrosyan | A10 | Yes | No
A16 | Launch-readiness review | 8 | Efua Seaborne | A14, A15 | No | Yes
Competing testing records | Wexmoor acceptance log: 24 staff-hours (12 per round); Foxglove frozen estimate: 32 staff-hours (16 per round).