## Resource Record
Frozen resource capacity and rates | As supplied
Resource | Role | Daily capacity (hours) | Charge rate (per hour) | Certifications | Unavailable dates | Training availability
Efua Seaborne | project management specialist | 8 | 125 | None | 2025-09-19 | Available per record
Kenji Petrosyan | technical implementation lead | 8 | 155 | Booking Platform Validation | 2025-09-23, 2025-09-24 | Available per record
Hilde Maldonado | workflow and training specialist | 6 | 110 | None | 2025-09-05, 2025-09-15 | Confirmed named resource
Olamide Elbaz | training lead | 7 | 95 | None | 2025-09-16, 2025-09-17, 2025-09-18, 2025-09-19 | Confirmed named resource
Meera Calloway | data analyst | 6 | 100 | None | 2025-09-09 | Available per record
Training evidence note | Confirmed capacity is Olamide Elbaz + Hilde Maldonado; Foxglove requests three trainers, no third named resource supplied.