## Control & Phases
Vesper Hollow Ranch — Recorded Governing Document Inventory
Authorization and control file before Marlowe Chambers evaluates the planned setback enforcement. No recorder research has been performed; all property-record fields remain unverified until sourced.
Decision gate & operating rules
Purpose | Authorize, direct and reconcile recorded-document research for six separately controlled annexed phases across two recorder jurisdictions.
Initial release | Authorize the Base forecast for index research, retrieval and first-pass review. Release High-cost escalation only at the gap gate on the Roadmap sheet.
Completion gate | A phase may be Completed only when declaration lineage, phase-adding instrument, applicable map/plat, cross-references and search coverage are reconciled and no core gap remains open.
Evidence rule | Located = index hit; Obtained = image/copy received; Reviewed = readable and assessed; Verified = recorder metadata/image reconciled. These do not by themselves establish legal effect.
Counsel boundary | Records staff preserve competing sources and ask questions; binding effect, priority, enforceability and interpretation are reserved to counsel.
Phase evidence register — a blank is not completion
Phase ID | Build window (planning cue) | County / recorder coverage | Aliases / tract / parcel / map cues | Declaration lineage status | Phase-adding instrument status | Applicable map / plat status | Parent / annexation link claimed; verify | Research status | Completion gate
VHR-P01 | 1974 | County A / County B — determine applicable recorder | Enter recorded tract, lot, parcel, plat name and historical phase aliases | Unsearched | Unsearched | Unsearched | Record instrument ID(s), express linkage, and source; chronology alone is insufficient | Unsearched | BLOCKED — core evidence
VHR-P02 | 1978 | County A / County B — determine applicable recorder | Enter recorded tract, lot, parcel, plat name and historical phase aliases | Unsearched | Unsearched | Unsearched | Record instrument ID(s), express linkage, and source; chronology alone is insufficient | Unsearched | BLOCKED — core evidence
VHR-P03 | 1982 | County A / County B — determine applicable recorder | Enter recorded tract, lot, parcel, plat name and historical phase aliases | Unsearched | Unsearched | Unsearched | Record instrument ID(s), express linkage, and source; chronology alone is insufficient | Unsearched | BLOCKED — core evidence
VHR-P04 | 1987 | County A / County B — determine applicable recorder | Enter recorded tract, lot, parcel, plat name and historical phase aliases | Unsearched | Unsearched | Unsearched | Record instrument ID(s), express linkage, and source; chronology alone is insufficient | Unsearched | BLOCKED — core evidence
VHR-P05 | 1992 | County A / County B — determine applicable recorder | Enter recorded tract, lot, parcel, plat name and historical phase aliases | Unsearched | Unsearched | Unsearched | Record instrument ID(s), express linkage, and source; chronology alone is insufficient | Unsearched | BLOCKED — core evidence
VHR-P06 | 1998 | County A / County B — determine applicable recorder | Enter recorded tract, lot, parcel, plat name and historical phase aliases | Unsearched | Unsearched | Unsearched | Record instrument ID(s), express linkage, and source; chronology alone is insufficient | Unsearched | BLOCKED — core evidence
Status & provenance prompts
Record facts only from the cited source: Recorder-index metadata ¦ Document-image text ¦ Staff observation ¦ Counsel determination. Research assumptions and workload estimates belong in their named planning fields, not in verified-record fields.
Inherited photocopied declaration: intake item only; unverified and not proof of phase coverage. Unrecorded association policies/resolutions stay outside recorded-coverage counts. Refer potentially relevant deeds/easements to counsel issues.

## Instrument Register
Instrument Register & Phase Links
One stable record per potential or verified instrument. Do not create an instrument record from an assumption; use a search event until a record is found.
Recorded governing-instrument inventory (blank until a source supports entry)
Instrument ID | Evidence level | Type | Recorder jurisdiction | Instrument / reception no. | Book / page fallback | Recording date | Execution / adoption / effective date | Recorded title / description | Grantor / indexed side A | Grantee / indexed side B | Legal-description / tract / map cue | Source locator + accessed / obtained date
VHR-I0001 | Unverified / not yet located | Select type | [9 empty] | Enter index URL/path, request ID or result citation; date accessed separately
VHR-I0002 | Unverified / not yet located | Select type | [9 empty] | Enter index URL/path, request ID or result citation; date accessed separately
VHR-I0003 | Unverified / not yet located | Select type | [9 empty] | Enter index URL/path, request ID or result citation; date accessed separately
VHR-I0004 | Unverified / not yet located | Select type | [9 empty] | Enter index URL/path, request ID or result citation; date accessed separately
VHR-I0005 | Unverified / not yet located | Select type | [9 empty] | Enter index URL/path, request ID or result citation; date accessed separately
VHR-I0006 | Unverified / not yet located | Select type | [9 empty] | Enter index URL/path, request ID or result citation; date accessed separately
Relationships, copy controls & duplicate rule
Link ID | Instrument ID | Phase ID | Relationship to phase | Related instrument ID | Relationship type | Cited reference as recorded | Retrieved? | Copy status | Certification status | Quality exception | Reviewer | Review date
VHR-L0001 |  |  | Select relation |  |  |  | Not applicable | Not requested | Not required | Not assessed
VHR-L0002 |  |  | Select relation |  |  |  | Not applicable | Not requested | Not required | Not assessed
VHR-L0003 |  |  | Select relation |  |  |  | Not applicable | Not requested | Not required | Not assessed
VHR-L0004 |  |  | Select relation |  |  |  | Not applicable | Not requested | Not required | Not assessed
VHR-L0005 |  |  | Select relation |  |  |  | Not applicable | Not requested | Not required | Not assessed
Duplicate control: match Recorder jurisdiction + Instrument/reception no.; if absent, use Recorder jurisdiction + Book/page. Never deduplicate by title. Earlier, superseded or replaced records remain in this register and are linked rather than deleted.

## Searches & Issues
Search Log, Name Universe & Counsel Issues
Research plan records affirmative no-results, not just hits. Exact historical spellings belong in the Name Universe when received or discovered.
Known / discovered search-name universe
Name ID | Exact search term | Name role | Source / how discovered | Status | Use in both index sides? | County A | County B | Added by | Date added
VHR-N001 | Known developer entity 1 — exact spelling pending intake | Developer identity |  | Planned | Yes
VHR-N002 | Known developer entity 2 — exact spelling pending intake | Developer identity |  | Planned | Yes
VHR-N003 | Known developer entity 3 — exact spelling pending intake | Developer identity |  | Planned | Yes
VHR-N004 | Association / abbreviation / historical form — add when found | Association variant |  | Planned | Yes
Search event log
Search ID | Jurisdiction / system | Search date | Searcher | Exact query / index term | Index side / method | Date range searched | Result disposition | Result / source locator | Follow-up / linked ID
VHR-S0001 | County A / County B recorder; identify actual system |  |  |  | Select method |  | Not run
VHR-S0002 | County A / County B recorder; identify actual system |  |  |  | Select method |  | Not run
VHR-S0003 | County A / County B recorder; identify actual system |  |  |  | Select method |  | Not run
VHR-S0004 | County A / County B recorder; identify actual system |  |  |  | Select method |  | Not run
VHR-S0005 | County A / County B recorder; identify actual system |  |  |  | Select method |  | Not run
VHR-S0006 | County A / County B recorder; identify actual system |  |  |  | Select method |  | Not run
Conflict / counsel-question queue
Issue ID | Issue type | Phase ID(s) | Source A: instrument ID + page / section / image | Source B: instrument ID + page / section / image | Competing provisions observed | Counsel question | Owner | Disposition status | Counsel determination / date
VHR-Q0001 | Setback inconsistency / ambiguity | [6 empty] | Open
VHR-Q0002 | Setback inconsistency / ambiguity | [6 empty] | Open
VHR-Q0003 | Setback inconsistency / ambiguity | [6 empty] | Open
VHR-Q0004 | Setback inconsistency / ambiguity | [6 empty] | Open
VHR-Q0005 | Setback inconsistency / ambiguity | [6 empty] | Open
When a gap remains after electronic/name searching, log an affirmative no-result, then escalate through property cues, map books, manual index review, recorder staff/on-site retrieval or title-specialist support. Preserve competing provisions; staff do not select a controlling rule.

## Roadmap & Handoff
Research Roadmap, Gaps & Migration Handoff
Planning dates are relative to authorization. Search wider than a phase year: include earlier foundations and later amendments/replacements.
Sequenced work plan
Step ID | Work package | Owner | Planned timing | Dependency | Completion evidence | Base / escalation | Shared-drive action | Matter-system handoff
VHR-W01 | Authorize base scope / open controls | Stonebridge manager | Day 0 | Approval | Authorized amount + owner | Base | Create controlled folder; save source copies | Create matter + map stable IDs
VHR-W02 | Index searches: all names, both sides, property cues | Records coordinator | Days 1–5 | W01 | Search events incl. no-results | Base | Log links/requests by stable ID | Import Search IDs + locators
VHR-W03 | Map/plat and cross-reference searches; retrieve copies | Records coordinator | Days 3–8 | W02 | Copy status and source locator | Base | Store images by Instrument ID | Import Instrument IDs + links
VHR-W04 | Quality review and phase reconciliation | Records coordinator + title reviewer | Days 6–10 | W03 | Reviewed records; gaps logged | Base | Update phase/gap tables | Import status, reviewer, dates
VHR-W05 | Gap gate: second pass / specialist support | Stonebridge manager | Day 10 | Open core gap | Decision documented before release | Escalation | Record approval/change | Import decision + budget change
VHR-W06 | Counsel handoff: coverage and open issues | Ivo Khouri | After W04 / W05 | Reconciled record set | Issue queue + inventory export | Base | Export locked review copy | Attach export; retain IDs
Open-gap action register
Gap ID | Phase / core evidence | Blocking reason / dependency | Next action | Owner | Target date | Status | Escalation required? | Migration ID
VHR-G0001 | [5 empty] | Open
VHR-G0002 | [5 empty] | Open
VHR-G0003 | [5 empty] | Open
VHR-G0004 | [5 empty] | Open
VHR-G0005 | [5 empty] | Open
Change control & transition checks
Change ID | Change date | Changed by | What changed | Affected stable ID(s) | Shared-drive location | Matter-system import status | Validation / reconciliation | Notes
VHR-C0001 | [5 empty] | Not yet migrated
VHR-C0002 | [5 empty] | Not yet migrated
VHR-C0003 | [5 empty] | Not yet migrated
VHR-C0004 | [5 empty] | Not yet migrated
VHR-C0005 | [5 empty] | Not yet migrated
Transition control: during shared-drive use, keep one controlled workbook and source files named by stable ID. At handoff, export structured tables; reconcile row counts, stable IDs, source locators, open gaps and issues before the matter-system tracker becomes controlling.

## Budget & Authorization
Budget Forecast & Authorization Gate
Planning assumptions only; same six-phase / two-recorder-jurisdiction scope in both scenarios. Amounts are formula-driven and exclude legal advice.
Scenario budget — quantities × rates or clearly labeled fixed allowances
Cost ID | Cost driver / scope | Unit | Base qty | Base rate | Base total | High qty | High rate | High total
VHR-B01 | Records research labor — all phases / both counties | hours | 28 | 95 | 2660 | 48 | 95 | 4560
VHR-B02 | Recorder / index access fees — two jurisdictions | fixed allowance | 1 | 120 | 120 | 1 | 300 | 300
VHR-B03 | Document image / copy requests | copies | 18 | 8 | 144 | 42 | 12 | 504
VHR-B04 | Certified copies if counsel requests | copies | 2 | 35 | 70 | 8 | 55 | 440
VHR-B05 | Map / plat retrieval and manual-index access | fixed allowance | 1 | 180 | 180 | 1 | 500 | 500
VHR-B06 | Title-records specialist escalation | hours | 0 | 175 | 0 | 12 | 175 | 2100
Scenario totals & operational allocation
Measure | Base forecast | High-cost forecast | Base formula / allocation | High formula / allocation
Direct costs | 3174 | 8404
Contingency — retrieval uncertainty | 317.4 | 1260.6 | 10% of direct costs | 15% of direct costs
Forecast total | 3491.4 | 9664.6
County A work package | 1920.27 | 5315.53 | 55% allocation | 55% allocation
County B work package | 1571.13 | 4349.07 | balance to total | balance to total
Allocation check | 0 | 0 | must equal $0 | must equal $0
Authorization decision
Request now | Base forecast total | 3491.4 | Authorize W01–W04: initial index research, retrieval and first-pass review.
High-cost release gate | Increment above base | 6173.2 | Manager decision at W05 only if core gaps remain after base work; include documented change log entry.
Scope note | Both scenarios |  | Six phases, two jurisdictions, all known/developed name variants, map/plat, cross-reference and issue controls.
Rates, quantities, contingency and timing are planning assumptions—not recorder facts. Contingency is separately stated for uncertainty in access, retrieval and gap follow-up; it is not embedded in ordinary unit rates.