Delegated Signature-Authority Schedule

Saltmarsh Design Partnership  |  Audience: Project Managers and Finance Partner  |  Adoption-ready operating schedule

SOURCE PRECEDENCE. This delegation applies only to an active client engagement governed by the relevant current MSA. It does not amend, waive, or override that MSA. The legacy template in the authority pack is superseded and must not be used.

1  Read “approval” correctly before acting

| Term | Operational meaning |
| --- | --- |
| Internal approval | Saltmarsh’s delegated decision that the named role may approve or sign within this schedule. It is not the client’s consent. |
| Client authorization | The written client authorization or signed client change instrument required by the applicable MSA before changed work is authorized or proceeds. |
| Contractual notice | A separate written notice required to protect a potential time or cost claim. It has its own trigger, deadline, and evidence. |

DO NOT ASSUME. Internal approval within a dollar ceiling does not constitute contractual notice, does not cure late notice, and does not automatically preserve a claim.

2  Live variation decision: follow this sequence

| Step | Required check and action |
| --- | --- |
| 1. Identify | Confirm the client and the active governing MSA; describe the underlying scope or decision, value, and date. |
| 2. Aggregate | Treat related requests as one Variation when they arise from the same underlying scope or decision. Splitting requests, documents, or invoices creates no additional authority. |
| 3. Test authority | Use the client row below. The operative amount is the lesser of the PM per-Variation ceiling and the remaining applicable MSA not-to-exceed amount. |
| 4. Separate obligations | Meet the applicable notice deadline and obtain the required client authorization before work is treated as authorized or proceeds. |
| 5. Record / escalate | Record the decision and evidence. Escalate to the Finance Partner if outside authority, above the aggregated PM ceiling, outside MSA scope, or ambiguous. |

3  Client-specific authority and contractual gates

| Client / current source | PM internal approval ceiling | MSA limit and authorization gate | Notice / escalation |
| --- | --- | --- | --- |
| Wexmoor Group Current MSA §§4.2, 4.4, 7.1 | Up to $20,000 per Variation, only if remaining MSA headroom is sufficient. | NTE: $150,000. Written client authorization is required before changed work is treated as authorized. Delegation cannot enlarge the NTE. | Written potential-claim notice: within 5 business days after PM first becomes aware of the event. Above PM limit: Finance Partner approval and required client change instrument. |
| Tidewater Logistics Current MSA §§3.3, 3.5, 6.2 | Up to $12,000 per Variation, only if remaining MSA headroom is sufficient. | NTE: $90,000. Written change order signed by the designated client representative is required for a scope or price change before work proceeds. Delegation cannot enlarge the NTE. | Potential-claim notice: within 3 business days after the event or direction giving rise to it. Above PM limit: Finance Partner approval and signed change order. |

4  Escalation, uncertain value, and record

Escalate to the Finance Partner before binding Saltmarsh where the aggregated Variation exceeds the Project Manager ceiling, remaining NTE headroom is inadequate, the change is outside scope, the MSA is not confirmed as active, the client authorization or notice requirement is unclear, or any exception is requested.

If the value is not fully known, do not convert uncertainty into approval. Document the supported estimate and its basis; escalate to the Finance Partner when the aggregate could exceed the applicable ceiling or remaining NTE amount.

| Minimum contemporaneous record | What to retain |
| --- | --- |
| Variation description and underlying scope/decision; client; value (or supported estimate); date; applicable current MSA and section; remaining NTE headroom; approver. | Client written authorization or signed change order, notice evidence and timing, the authority-decision basis, and every escalation or exception outcome. |

5  Short worked distinction

WEXMOOR ILLUSTRATION. A $20,000 Variation may be within the PM internal ceiling only if at least that amount remains under the $150,000 NTE. It still needs written client authorization under §4.4. If it also involves a potential time or cost claim, written notice remains due within 5 business days after awareness under §7.1; internal approval does not change that clock.