## Roster
CRAGSIDE INVITATIONAL — SAME-NIGHT EDIT ROSTER
Baseline plan with late-final contingency shown per package ¦ owner: Oyin Adebowale
Package ID | Day | Client | Package / next step | Priority | Editor | Edit start | Edit finish | Bay | Finish start | Finish finish | Caption status | Caption start | Caption finish | Baseline uplink | Baseline delivery | Late scenario uplink | Late scenario delivery | Late edit start | Late edit finish | Late finish start | Late finish finish | Late caption start | Late caption finish | Meal break start | Meal break finish | Owner action | Source Notes
D1-A01 | Day 1 | Ashgrove Cooperative | Morning recap | High | E01 | 2026-09-07 10:30 | 2026-09-07 11:30 | Bay 1 | 2026-09-07 11:30 | 2026-09-07 12:00 | Captioned | 2026-09-07 20:00 | 2026-09-07 20:10 | Slot A | 2026-09-07 20:30 | Slot A | 2026-09-07 20:30 | 2026-09-07 10:30 | 2026-09-07 11:30 | 2026-09-07 11:30 | 2026-09-07 12:00 | 2026-09-07 20:00 | 2026-09-07 20:10 | 2026-09-07 13:00 | 2026-09-07 13:30 | Ready for uplink
D1-A02 | Day 1 | Tanneryside Provisions | Field package | Medium | E02 | 2026-09-07 09:00 | 2026-09-07 10:15 |  |  |  | Not required |  |  | Not required | 2026-09-07 10:30 | Not required | 2026-09-07 10:30 | 2026-09-07 09:00 | 2026-09-07 10:15 | [6 empty] | Publish to internal queue
D1-A03 | Day 1 | Ashgrove Cooperative | Feature cut | High | E03 | 2026-09-07 11:30 | 2026-09-07 12:30 | Bay 2 | 2026-09-07 12:30 | 2026-09-07 13:00 | Captioned | 2026-09-07 20:10 | 2026-09-07 20:20 | Not required | 2026-09-07 20:20 | Not required | 2026-09-07 20:20 | 2026-09-07 11:30 | 2026-09-07 12:30 | 2026-09-07 12:30 | 2026-09-07 13:00 | 2026-09-07 20:10 | 2026-09-07 20:20 |  |  | Publish to internal queue | Caption window held at 20:10
D1-A04 | Day 1 | Tanneryside Provisions | Interview cut | Medium | E04 | 2026-09-07 14:00 | 2026-09-07 15:30 | Bay 3 | 2026-09-07 15:30 | 2026-09-07 16:00 | Not required |  |  | Not required | 2026-09-07 17:00 | Not required | 2026-09-07 17:00 | 2026-09-07 14:00 | 2026-09-07 15:30 | 2026-09-07 15:30 | 2026-09-07 16:00 |  |  |  |  | Publish to internal queue
D1-FINAL | Day 1 | Ashgrove Cooperative | Evening final | Critical | E01 | 2026-09-07 18:00 | 2026-09-07 20:00 | Bay 4 | 2026-09-07 20:00 | 2026-09-07 20:40 | Captioned | 2026-09-07 20:40 | 2026-09-07 20:50 | Slot A | 2026-09-07 20:50 | Slot B | 2026-09-07 23:20 | 2026-09-07 19:00 | 2026-09-07 21:00 | 2026-09-07 21:00 | 2026-09-07 21:40 | 2026-09-07 22:00 | 2026-09-07 22:10 | 2026-09-07 13:00 | 2026-09-07 13:30 | Ready for uplink | Late-final scenario: release 19:00; move to Slot B
D2-B01 | Day 2 | Tanneryside Provisions | Morning recap | High | E05 | 2026-09-08 10:30 | 2026-09-08 11:30 | Bay 1 | 2026-09-08 11:30 | 2026-09-08 12:00 | Captioned | 2026-09-08 20:00 | 2026-09-08 20:10 | Slot A | 2026-09-08 20:30 | Slot A | 2026-09-08 20:30 | 2026-09-08 10:30 | 2026-09-08 11:30 | 2026-09-08 11:30 | 2026-09-08 12:00 | 2026-09-08 20:00 | 2026-09-08 20:10 | 2026-09-08 13:00 | 2026-09-08 13:30 | Ready for uplink
D2-B02 | Day 2 | Ashgrove Cooperative | Field package | Medium | E06 | 2026-09-08 10:00 | 2026-09-08 11:15 |  |  |  | Not required |  |  | Not required | 2026-09-08 11:30 | Not required | 2026-09-08 11:30 | 2026-09-08 10:00 | 2026-09-08 11:15 | [6 empty] | Publish to internal queue
D2-B03 | Day 2 | Tanneryside Provisions | Feature cut | High | E07 | 2026-09-08 12:00 | 2026-09-08 13:00 | Bay 2 | 2026-09-08 13:00 | 2026-09-08 13:30 | Captioned | 2026-09-08 20:10 | 2026-09-08 20:20 | Not required | 2026-09-08 20:20 | Not required | 2026-09-08 20:20 | 2026-09-08 12:00 | 2026-09-08 13:00 | 2026-09-08 13:00 | 2026-09-08 13:30 | 2026-09-08 20:10 | 2026-09-08 20:20 |  |  | Publish to internal queue | Caption window held at 20:10
D2-B04 | Day 2 | Ashgrove Cooperative | Interview cut | Medium | E08 | 2026-09-08 15:00 | 2026-09-08 16:30 | Bay 3 | 2026-09-08 16:30 | 2026-09-08 17:00 | Not required |  |  | Not required | 2026-09-08 18:00 | Not required | 2026-09-08 18:00 | 2026-09-08 15:00 | 2026-09-08 16:30 | 2026-09-08 16:30 | 2026-09-08 17:00 |  |  |  |  | Publish to internal queue
D2-FINAL | Day 2 | Tanneryside Provisions | Evening final | Critical | E05 | 2026-09-08 18:00 | 2026-09-08 20:00 | Bay 4 | 2026-09-08 20:00 | 2026-09-08 20:40 | Captioned | 2026-09-08 20:40 | 2026-09-08 20:50 | Slot A | 2026-09-08 20:50 | Slot B | 2026-09-08 23:20 | 2026-09-08 19:00 | 2026-09-08 21:00 | 2026-09-08 21:00 | 2026-09-08 21:40 | 2026-09-08 22:00 | 2026-09-08 22:10 | 2026-09-08 13:00 | 2026-09-08 13:30 | Ready for uplink | Late-final scenario: release 19:00; move to Slot B
D3-C01 | Day 3 | Ashgrove Cooperative | Morning recap | High | E09 | 2026-09-09 10:30 | 2026-09-09 11:30 | Bay 1 | 2026-09-09 11:30 | 2026-09-09 12:00 | Captioned | 2026-09-09 20:00 | 2026-09-09 20:10 | Slot A | 2026-09-09 20:30 | Slot A | 2026-09-09 20:30 | 2026-09-09 10:30 | 2026-09-09 11:30 | 2026-09-09 11:30 | 2026-09-09 12:00 | 2026-09-09 20:00 | 2026-09-09 20:10 | 2026-09-09 13:00 | 2026-09-09 13:30 | Ready for uplink
D3-C02 | Day 3 | Tanneryside Provisions | Field package | Medium | E10 | 2026-09-09 10:00 | 2026-09-09 11:15 |  |  |  | Not required |  |  | Not required | 2026-09-09 11:30 | Not required | 2026-09-09 11:30 | 2026-09-09 10:00 | 2026-09-09 11:15 | [6 empty] | Publish to internal queue
D3-C03 | Day 3 | Ashgrove Cooperative | Feature cut | High | E11 | 2026-09-09 12:00 | 2026-09-09 13:00 | Bay 2 | 2026-09-09 13:00 | 2026-09-09 13:30 | Captioned | 2026-09-09 20:10 | 2026-09-09 20:20 | Not required | 2026-09-09 20:20 | Not required | 2026-09-09 20:20 | 2026-09-09 12:00 | 2026-09-09 13:00 | 2026-09-09 13:00 | 2026-09-09 13:30 | 2026-09-09 20:10 | 2026-09-09 20:20 |  |  | Publish to internal queue | Caption window held at 20:10
D3-C04 | Day 3 | Tanneryside Provisions | Interview cut | Medium | E12 | 2026-09-09 15:00 | 2026-09-09 16:30 | Bay 3 | 2026-09-09 16:30 | 2026-09-09 17:00 | Not required |  |  | Not required | 2026-09-09 18:00 | Not required | 2026-09-09 18:00 | 2026-09-09 15:00 | 2026-09-09 16:30 | 2026-09-09 16:30 | 2026-09-09 17:00 |  |  |  |  | Publish to internal queue
D3-FINAL | Day 3 | Ashgrove Cooperative | Evening final | Critical | E09 | 2026-09-09 18:00 | 2026-09-09 20:00 | Bay 4 | 2026-09-09 20:00 | 2026-09-09 20:40 | Captioned | 2026-09-09 20:40 | 2026-09-09 20:50 | Slot A | 2026-09-09 20:50 | Slot B | 2026-09-09 23:20 | 2026-09-09 19:00 | 2026-09-09 21:00 | 2026-09-09 21:00 | 2026-09-09 21:40 | 2026-09-09 22:00 | 2026-09-09 22:10 | 2026-09-09 13:00 | 2026-09-09 13:30 | Ready for uplink | Late-final scenario: release 19:00; move to Slot B

## Bay Plan
FINISHING-BAY PLAN — OCCUPANCY AND IDLE WINDOWS
All four bays available 08:00–23:30 each event day; gaps are idle capacity.
Day | Bay | Package ID | Finish start | Finish finish | Duration min | Status | Idle before / after | Plan version
Day 1 | Bay 1 | D1-A01 | 2026-09-07 11:30 | 2026-09-07 12:00 | 30 | Reserved | 08:00–11:30 idle; 12:00–23:30 idle | Baseline
Day 1 | Bay 2 | D1-A03 | 2026-09-07 12:30 | 2026-09-07 13:00 | 30 | Reserved | 08:00–12:30 idle; 13:00–23:30 idle | Baseline
Day 1 | Bay 3 | D1-A04 | 2026-09-07 15:30 | 2026-09-07 16:00 | 30 | Reserved | 08:00–15:30 idle; 16:00–23:30 idle | Baseline
Day 1 | Bay 4 | D1-FINAL | 2026-09-07 20:00 | 2026-09-07 20:40 | 40 | Reserved | 08:00–20:00 idle; 20:40–23:30 idle | Baseline
Day 2 | Bay 1 | D2-B01 | 2026-09-08 11:30 | 2026-09-08 12:00 | 30 | Reserved | 08:00–11:30 idle; 12:00–23:30 idle | Baseline
Day 2 | Bay 2 | D2-B03 | 2026-09-08 13:00 | 2026-09-08 13:30 | 30 | Reserved | 08:00–13:00 idle; 13:30–23:30 idle | Baseline
Day 2 | Bay 3 | D2-B04 | 2026-09-08 16:30 | 2026-09-08 17:00 | 30 | Reserved | 08:00–16:30 idle; 17:00–23:30 idle | Baseline
Day 2 | Bay 4 | D2-FINAL | 2026-09-08 20:00 | 2026-09-08 20:40 | 40 | Reserved | 08:00–20:00 idle; 20:40–23:30 idle | Baseline
Day 3 | Bay 1 | D3-C01 | 2026-09-09 11:30 | 2026-09-09 12:00 | 30 | Reserved | 08:00–11:30 idle; 12:00–23:30 idle | Baseline
Day 3 | Bay 2 | D3-C03 | 2026-09-09 13:00 | 2026-09-09 13:30 | 30 | Reserved | 08:00–13:00 idle; 13:30–23:30 idle | Baseline
Day 3 | Bay 3 | D3-C04 | 2026-09-09 16:30 | 2026-09-09 17:00 | 30 | Reserved | 08:00–16:30 idle; 17:00–23:30 idle | Baseline
Day 3 | Bay 4 | D3-FINAL | 2026-09-09 20:00 | 2026-09-09 20:40 | 40 | Reserved | 08:00–20:00 idle; 20:40–23:30 idle | Baseline
Day 1 | Bay 4 | D1-FINAL | 2026-09-07 21:00 | 2026-09-07 21:40 | 40 | Reserved | 08:00–21:00 idle; 21:40–23:30 idle | Late-final scenario
Day 2 | Bay 4 | D2-FINAL | 2026-09-08 21:00 | 2026-09-08 21:40 | 40 | Reserved | 08:00–21:00 idle; 21:40–23:30 idle | Late-final scenario
Day 3 | Bay 4 | D3-FINAL | 2026-09-09 21:00 | 2026-09-09 21:40 | 40 | Reserved | 08:00–21:00 idle; 21:40–23:30 idle | Late-final scenario

## Method
METHOD / CHECKS
Located authoritative package headers at Inputs!D6:R22 beneath the banner and gutter; resource tables are Inputs!D27:H63 (editors), D69:F80 (bays), D84:H89 (encoder), D93:E99 (rules), and D103:H108 (uplinks). Notes take precedence over ordinary columns: finals use a 19:00 late release and move Slot A to Slot B; D2-X99 is excluded as a duplicate; caption-window notes are retained. The residual formula error was ignored and not copied. Edit starts respect release times and exact source durations; finishing follows edit completion. Caption reservations are 10-minute blocks inside vendor windows. Delivery is after the chain and within ten hours of effective release; late-final delivery is 23:20. Meal rule is a 30-minute break when an editor span exceeds six hours, shown on affected rows. I checked editor overlap/availability, bay overlap/availability, single-encoder overlap/window, meal placement, turnaround, dependency order, and uplink capacity/slot timing for baseline and late-final scenario.

## Change Log
CHANGE LOG — AUTHORIZED PLANNER ACTIONS
Package / scope | Change type | Source value | Roster value | Reason / evidence | Scenario effect
D1-A01 | Assignment | Unassigned in source | E01 / Bay 1 | Resource plan fits supplied availability | No change
D1-A02 | Assignment | Unassigned in source | E02 / None | Resource plan fits supplied availability | No change
D1-A03 | Assignment | Unassigned in source | E03 / Bay 2 | Resource plan fits supplied availability | No change
D1-A03 | Caption timing | Window not fixed | Captioned | Notes override | No movement
D1-A04 | Assignment | Unassigned in source | E04 / Bay 3 | Resource plan fits supplied availability | No change
D1-FINAL | Assignment | Unassigned in source | E01 / Bay 4 | Resource plan fits supplied availability | No change
D1-FINAL | Timing + uplink | Release 18:00; Slot A | Scenario release 19:00; Slot B at 23:20 | Supplied late-final assumption | Final moves; other packages remain
D2-B01 | Assignment | Unassigned in source | E05 / Bay 1 | Resource plan fits supplied availability | No change
D2-B02 | Assignment | Unassigned in source | E06 / None | Resource plan fits supplied availability | No change
D2-B03 | Assignment | Unassigned in source | E07 / Bay 2 | Resource plan fits supplied availability | No change
D2-B03 | Caption timing | Window not fixed | Captioned | Notes override | No movement
D2-B04 | Assignment | Unassigned in source | E08 / Bay 3 | Resource plan fits supplied availability | No change
D2-FINAL | Assignment | Unassigned in source | E05 / Bay 4 | Resource plan fits supplied availability | No change
D2-FINAL | Timing + uplink | Release 18:00; Slot A | Scenario release 19:00; Slot B at 23:20 | Supplied late-final assumption | Final moves; other packages remain
D3-C01 | Assignment | Unassigned in source | E09 / Bay 1 | Resource plan fits supplied availability | No change
D3-C02 | Assignment | Unassigned in source | E10 / None | Resource plan fits supplied availability | No change
D3-C03 | Assignment | Unassigned in source | E11 / Bay 2 | Resource plan fits supplied availability | No change
D3-C03 | Caption timing | Window not fixed | Captioned | Notes override | No movement
D3-C04 | Assignment | Unassigned in source | E12 / Bay 3 | Resource plan fits supplied availability | No change
D3-FINAL | Assignment | Unassigned in source | E09 / Bay 4 | Resource plan fits supplied availability | No change
D3-FINAL | Timing + uplink | Release 18:00; Slot A | Scenario release 19:00; Slot B at 23:20 | Supplied late-final assumption | Final moves; other packages remain
D2-X99 | Exclusion | Scope: In scope | Excluded | Notes: duplicate of D2-B03 | Not scheduled