## Transition_Overview
Crownridge Associates — Receiving Handover Packet
Saltmarsh Housing Trust ¦ Building Components Facility ¦ compiled 01 Sep 2026
Planning date | 2026-09-01
Senior receiver final working date | 2026-11-03
Crownridge account review | 2026-10-22
Target assignment effective date | 2026-10-20
Operating note | Recent measures are observations, not root-cause determinations.
Control note | Blank source evidence remains unknown; it is not No, zero, current, available, or complete.
Prepared for | Shipping, receiving, inventory, and Crownridge account oversight
Legacy routing note: | The old night roster field is no longer populated in this extract.

## Personnel_Evidence
Personnel readiness evidence
Current extract; blank fields are intentionally not affirmative.
Person_ID | Person | Role | ESD_Cert_Through | Forklift_Authorized | Night_Available | Cycle_Training | ESD_Practical_Passed | Independent_Audit_Signoff | Evidence_Note
P-101 | Chidi Moravec | Senior Receiver / outgoing | 2026-11-03
P-103 | Paloma Ilechukwu | Lead clerk / decision maker
P-102 | Esperanza Mortensen | Receiver | 2027-08-31 | Yes | Yes | Yes | Yes | Yes | All-family evidence current
P-117 | Ragnhild Garrido | Receiver | 2027-05-31 | Yes | Yes | Yes |  | Yes | ESD observed assessment not supplied
P-124 | Valeria Nightingale | Inventory receiver | 2026-12-31 | Yes |  | Yes | Yes |  | Night availability and audit sign-off not supplied

## Duty_Register
Duty register
In-scope duties retain their account identifiers.
Duty_ID | Duty_Family | Duty_Name | In_Scope
ESD-01 | Crownridge ESD handling | Certified ESD material staging | Yes
ESD-02 | Crownridge ESD handling | Crownridge ESD receipt release | Yes
NFR-01 | Night forklift receiving | Night-shift forklift receiving | Yes
NFR-02 | Night forklift receiving | Night dock receipt reconciliation | Yes
CCA-01 | Cycle-count audit | Cycle-count audit lead | Yes
CCA-02 | Cycle-count audit | Cycle-count variance approval | Yes

## Controls
Applicable controls
Read alongside duty register and evidence.
Duty_Family | Control_Description | Mandatory_Evidence | Control_Purpose
Crownridge ESD handling | Active ESD certification through effective date; practical/observed ESD qualification | Certification current; ESD practical assessment affirmative | Crownridge account control
Night forklift receiving | Active forklift authorization; affirmative night-shift availability | Forklift authorization current; Night availability = Yes | Safe material handling
Cycle-count audit | Cycle-count training; independent audit sign-off | Training affirmative; independent sign-off affirmative | Audit independence

## Operating_Measures
Comparable operating measures
Period measures supplied by operations reporting.
Metric_ID | Duty_Family | Metric | Unit | Prior_Label | Recent_Label | Prior_Value | Recent_Value | Materiality_Basis | Materiality_Threshold | Context_Note
MET-01 | Crownridge ESD handling | ESD receipts processed | pallets | Apr-Jun 2026 | Jul-Sep 2026 | 420 | 505 | Pct | 0.15 | Higher volume increases documented ESD handover workload.
MET-02 | Crownridge ESD handling | ESD handling exceptions | exceptions | Apr-Jun 2026 | Jul-Sep 2026 | 4 | 7 | Abs | 2 | Increase warrants continuity and observed coverage.
MET-03 | Night forklift receiving | Night receipts | loads | Apr-Jun 2026 | Jul-Sep 2026 | 188 | 242 | Pct | 0.2 | Higher night volume increases safe-coverage demand.
MET-04 | Night forklift receiving | Dock damage events | events | Apr-Jun 2026 | Jul-Sep 2026 | 2 | 2 | Abs | 1 | No material change observed.
MET-05 | Cycle-count audit | Cycle-count lines reviewed | lines | Apr-Jun 2026 | Jul-Sep 2026 | 620 | 710 | Pct | 0.1 | Higher audit workload needs independent ownership.
MET-06 | Cycle-count audit | Unresolved count variances | variances | Apr-Jun 2026 | Jul-Sep 2026 | 11 | 19 | Abs | 5 | Deterioration raises audit exposure; not a stated causal finding.

## Known_Gaps
Known information gaps
Record a disposition in the completed plan; do not silently infer blanks.
Gap_ID | Subject | Missing_Field | Source_Value | Potential_Effect | Handling_Note
G-01 | Valeria Nightingale | Night-shift availability | Not supplied | Eligibility / scheduling | Do not treat blank as affirmative availability.
G-02 | Ragnhild Garrido | ESD practical assessment | Not supplied | ESD readiness | May be resolved by observed assessment before effective date.
G-03 | Valeria Nightingale | Independent cycle-count sign-off | Not supplied | Audit readiness | May be resolved by independent sign-off before audit milestone.

## Decision_Criteria
Decision criteria
Rate 1–5; higher is preferred. Weight is percent of aggregate.
Criterion | Weight_Pct | Rating_Guide
Control and safety compliance | 35 | Higher is preferred; 5 = all controls current and evidenced
Crownridge audit continuity | 25 | Higher is preferred; 5 = continuity with documented coverage
Workload feasibility | 15 | Higher is preferred; 5 = capacity aligned to recent demand
Concentration resilience | 15 | Higher is preferred; 5 = distributed primaries and coverage
Employee development | 10 | Higher is preferred; 5 = controlled development opportunity

## Output_Spec
Completed workbook and Crownridge import specification
This worksheet is the controlled implementation specification for the transition tool.
Specification | Required implementation
Required worksheet order | README ¦ Source_Snapshot ¦ Decision_Summary ¦ Duty_Plan ¦ Readiness ¦ Period_Analysis ¦ Assumptions ¦ System_Export ¦ Lists
Duty_Plan table / fields | Duty_Plan: Duty_ID, Duty_Family, Duty_Name, Primary_Owner, Backup_Owner, Effective_Date, Readiness_Status, Required_Action, Rationale
Readiness table / fields | Readiness: Person, Duty_ID, Current_Status, Evidence, Gap, Required_Action, Action_Owner, Due_Date, Action_Status
Period table / fields | Period_Analysis: Metric_ID, Duty_Family, Metric, Unit, Prior_Period, Recent_Period, Variance, Variance_Pct, Material_Flag, Interpretation
Assumptions table / fields | Assumptions: Gap_ID, Subject, Missing_Field, Disposition, Basis, Decision_Impact, Owner, Resolution_Date
Export table / fields | Crownridge_Export: Record_Type, Duty_ID, Duty_Name, Primary_Person_ID, Backup_Person_ID, Effective_Date, Readiness_Status, Assignment_Key
Assignment candidates | Esperanza Mortensen ¦ Ragnhild Garrido ¦ Valeria Nightingale (only)
Status lists | Readiness: Ready, Conditional, Not Ready; Action: Not Started, In Progress, Complete; Disposition: Assume, Exclude, Escalate
Readiness aggregation | Not Ready if either assignment is Not Ready; Conditional if neither is Not Ready and at least one is Conditional; otherwise Ready.
Formula fields | Duty_Plan.Readiness_Status; Period_Analysis.Variance, Variance_Pct, Material_Flag; Decision option results; System_Export.Assignment_Key
Crownridge parsed area | Worksheet System_Export; defined name CROWNRIDGE_HANDOVER_IMPORT; exact table fields only; header plus populated data, no title/totals/blanks/merges.
Key format | Assignment_Key = Duty_ID ¦ Primary_Person_ID; vertical-bar delimiter; source identifiers unchanged.
Export field types | Record_Type text literal HANDOVER; Duty_ID/text IDs text; dates true date values displayed yyyy-mm-dd; status accepted readiness literal.
Style legend | Ready = green fill; Conditional = amber fill; Not Ready = red fill.
Protection | Formula cells locked; planned user-input cells unlocked; protected sheets permit selecting unlocked cells and validated entry.
Print requirements | Audit-facing: Duty_Plan, Readiness, Period_Analysis, Assumptions, System_Export. Letter, landscape, fit one page wide, print area through data, repeat rows 1:4.
Blank convention | Intentional blanks remain unknown and cannot be treated as No, zero, current, available, or complete without explicit disposition.