## Planning
ELDERGROVE SOLUTIONS ¦ POST-DELIVERY CONTROL PLAN
Owner: Jacinta Jaramillo ¦ Review partner: Cormac Duarte ¦ Calendar: Mon-Fri excluding 2026-02-04 public holiday
Contractual delivery | 2026-03-20
Holiday excluded | 2026-02-04
Task_ID | Episode | Task | Owner | Start_Date | End_Date | Duration_Working_Days | Predecessor_Task_ID | Status | Critical_Flag | Float_Working_Days
ST-E1 | E1 | Picture-lock / source ready | Post Producer | 2026-01-05 | 2026-01-05 | 1 |  | Complete | N | 53
ST-E2 | E2 | Picture-lock / source ready | Post Producer | 2026-01-05 | 2026-01-05 | 1 |  | Complete | N | 53
ST-E4 | E4 | Composer stems received | Composer | 2026-01-05 | 2026-01-05 | 1 |  | Complete | Y | 53
C-E1 | E1 | Online conform | Online Editor | 2026-01-06 | 2026-01-08 | 3 | ST-E1 | Complete | N | 5
C-E4 | E4 | Online conform | Online Editor | 2026-01-06 | 2026-01-08 | 3 | ST-E4 | Complete | Y | 2
C-E2 | E2 | Online conform | Online Editor | 2026-01-08 | 2026-01-12 | 3 | ST-E2 | Complete | N | 15
G-E4 | E4 | Colour grade ¦ suite block W2 | Colourist / shared suite | 2026-01-12 | 2026-01-14 | 3 | C-E4 | Planned | Y | 1
G-E1 | E1 | Colour grade ¦ suite block W2 | Colourist / shared suite | 2026-01-15 | 2026-01-19 | 3 | C-E1 | Planned | N | 1
M-E4 | E4 | Final mix | Mix Engineer | 2026-01-15 | 2026-01-19 | 3 | G-E4 | Planned | Y | 25
M-E1 | E1 | Final mix | Mix Engineer | 2026-01-20 | 2026-01-22 | 3 | G-E1 | Planned | N | 22
G-E2 | E2 | Colour grade ¦ suite block W5 (holiday excluded) | Colourist / shared suite | 2026-02-02 | 2026-02-05 | 3 | C-E2 | Planned | N | 2
M-E2 | E2 | Final mix | Mix Engineer | 2026-02-09 | 2026-02-11 | 3 | G-E2 | Planned | N | 9
ST-E3 | E3 | Composer E3 stems received | Composer | 2026-02-09 | 2026-02-09 | 1 |  | Waiting until W6 | Y | 29
C-E3 | E3 | Online conform (stems-dependent) | Online Editor | 2026-02-09 | 2026-02-11 | 3 | ST-E3 | Planned | Y | 3
G-E3 | E3 | Colour grade ¦ suite block W7 | Colourist / shared suite | 2026-02-16 | 2026-02-18 | 3 | C-E3 | Planned | Y | 1
M-E3 | E3 | Final mix | Mix Engineer | 2026-02-19 | 2026-02-23 | 3 | G-E3 | Planned | Y | 1
CAP-ALL | All | Captions vendor window (5 working days) | Captions vendor | 2026-02-24 | 2026-03-02 | 5 | M-E1,M-E2,M-E3,M-E4 | Planned | Y | 1
QC-ALL | All | Distributor QC pass | Distributor QC | 2026-03-03 | 2026-03-05 | 3 | CAP-ALL | Planned | Y | 11
DEL-ALL | All | Contractual delivery milestone | Coordinating Producer | 2026-03-20 | 2026-03-20 | 1 | QC-ALL | Planned | Y | 0
Suite allocation summary
Available constrained blocks | 3
Scheduled episode grade assignments | 4
Recovery room after distributor QC (working days) | 11
Interpretation | Readiness/resource-block reading: use early suite access for ready E1/E4, place E2 in W5, and reserve W7 for late E3 stems.
Rejected alternative | Strict episode sequence would strand the early blocks while E3 waits, leaving less recovery room after the shared suite.
Working-day rule | NETWORKDAYS Mon-Fri, excluding 2026-02-04; suite W5 is bookable only on Mon/Tue/Thu/Fri.
Formulas:
Duration_Working_Days = NETWORKDAYS.INTL([Start_Date],[End_Date],1,B4)
Float_Working_Days = MAX(0,NETWORKDAYS.INTL([End_Date],B3,1,B4)-1)
Float_Working_Days = MAX(0,NETWORKDAYS.INTL([End_Date],E14,1,B4)-1)

## Export
Task_ID | Episode | Task | Owner | Start_Date | End_Date | Duration_Working_Days | Predecessor_Task_ID | Status | Critical_Flag
ST-E1 | E1 | Picture-lock / source ready | Post Producer | 2026-01-05 | 2026-01-05 | 1 |  | Complete | N
ST-E2 | E2 | Picture-lock / source ready | Post Producer | 2026-01-05 | 2026-01-05 | 1 |  | Complete | N
ST-E4 | E4 | Composer stems received | Composer | 2026-01-05 | 2026-01-05 | 1 |  | Complete | Y
C-E1 | E1 | Online conform | Online Editor | 2026-01-06 | 2026-01-08 | 3 | ST-E1 | Complete | N
C-E4 | E4 | Online conform | Online Editor | 2026-01-06 | 2026-01-08 | 3 | ST-E4 | Complete | Y
C-E2 | E2 | Online conform | Online Editor | 2026-01-08 | 2026-01-12 | 3 | ST-E2 | Complete | N
G-E4 | E4 | Colour grade ¦ suite block W2 | Colourist / shared suite | 2026-01-12 | 2026-01-14 | 3 | C-E4 | Planned | Y
G-E1 | E1 | Colour grade ¦ suite block W2 | Colourist / shared suite | 2026-01-15 | 2026-01-19 | 3 | C-E1 | Planned | N
M-E4 | E4 | Final mix | Mix Engineer | 2026-01-15 | 2026-01-19 | 3 | G-E4 | Planned | Y
M-E1 | E1 | Final mix | Mix Engineer | 2026-01-20 | 2026-01-22 | 3 | G-E1 | Planned | N
G-E2 | E2 | Colour grade ¦ suite block W5 (holiday excluded) | Colourist / shared suite | 2026-02-02 | 2026-02-05 | 3 | C-E2 | Planned | N
M-E2 | E2 | Final mix | Mix Engineer | 2026-02-09 | 2026-02-11 | 3 | G-E2 | Planned | N
ST-E3 | E3 | Composer E3 stems received | Composer | 2026-02-09 | 2026-02-09 | 1 |  | Waiting until W6 | Y
C-E3 | E3 | Online conform (stems-dependent) | Online Editor | 2026-02-09 | 2026-02-11 | 3 | ST-E3 | Planned | Y
G-E3 | E3 | Colour grade ¦ suite block W7 | Colourist / shared suite | 2026-02-16 | 2026-02-18 | 3 | C-E3 | Planned | Y
M-E3 | E3 | Final mix | Mix Engineer | 2026-02-19 | 2026-02-23 | 3 | G-E3 | Planned | Y
CAP-ALL | All | Captions vendor window (5 working days) | Captions vendor | 2026-02-24 | 2026-03-02 | 5 | M-E1,M-E2,M-E3,M-E4 | Planned | Y
QC-ALL | All | Distributor QC pass | Distributor QC | 2026-03-03 | 2026-03-05 | 3 | CAP-ALL | Planned | Y
DEL-ALL | All | Contractual delivery milestone | Coordinating Producer | 2026-03-20 | 2026-03-20 | 1 | QC-ALL | Planned | Y

## Decision_Key
DECISION CHECK ¦ KEYED REVIEW
Question | Answer | Rationale | Evidence / trigger
1. Which constraint reading is selected? | Readiness/resource-block reading. | Early blocks are used by ready E1/E4; W7 is deliberately held for later E3 stems, preserving recovery room. | Suite blocks W1-2, W5, W7-8; E3 stems 2026-02-09.
2. What does a 2-day slip to E3 stems threaten first? | E3 conform and its W7 grade booking. | C-E3 starts on stem arrival; a slip consumes the only planned late suite window and pushes mix/captions/QC. | ST-E3 -> C-E3 -> G-E3 chain.
3. How is scarce suite access used? | Four episode grade assignments across three shared blocks. | E1/E4 share W2, E2 uses W5 (holiday excluded), E3 uses W7; no continuous reservation is assumed. | G-E1, G-E4, G-E2, G-E3.
4. Which work has recoverable float? | E1 conform has 5 working days of deadline float. | Its successors finish well before the shared captions gate; a slip up to 5 working days does not move delivery. | Planning K column / E1 chain.
5. What must clear before captions and QC? | All four mixes, then the 5-day captions vendor window before QC. | Captions is a real vendor block, and QC is a distinct pass; both sit after grade/mix gates. | CAP-ALL 2026-02-24..2026-03-02; QC-ALL 2026-03-03..05.