## Slide 1
CAVENDISH LOGISTICS / DECISION PACK
Crew scheduling pilot protocol
A controlled, concurrent test for 11 Emberline Clinic field crews in England & Scotland
OWNER Mikkel Fairbairn
SPONSOR Eamon Rasmussen
For Eamon • Astrid Yamamoto • Camila Okonkwo • Jasmin Ellingsen
Decision gate: approve design, funding and contract protections before any pilot access

## Slide 2
01 / QUESTION & SCOPE
What the pilot is allowed to answer
Cavendish Logistics • Emberline Clinic • planning assumption set • 20 Aug 2026
02
Decision question
For eligible crews, does access to and use of the scheduling tool reduce overtime per productive workload unit versus concurrent crews without access during the same 12-week season?
Vendor’s “20%” is a claim to test—not an expected result or pass mark.
In scope
All 11 Cavendish field crews serving Emberline Clinic work in England and Scotland. Assignment unit = whole crew; workers, dispatch and schedules can spill over.
Pilot access to 5–6 crews; retain 5–6 concurrent comparison crews.
Design guardrails frozen before outcome review
• No raw before→after claim as primary evidence; demand and season move together.
• Concurrent windows and a crew-and-time model are mandatory.
• Volunteer willingness ≠ allocation: opt-in to training/notice, then balanced draw.
• Record region, capacity/headcount, job mix, travel burden, baseline overtime and disruptions.
• No post-result exclusions, replacements or subgroup shopping.
• Primary population remains crews as assigned (intention-to-treat).

## Slide 3
02 / ELIGIBILITY, ALLOCATION & TIMING
Freeze the comparison before launch
Cavendish Logistics • Emberline Clinic • planning assumption set • 20 Aug 2026
03
Eligibility (assessed at T−6 weeks)
• Active Emberline work; ≥10 of prior 12 weeks with payroll + job records.
• Stable crew roster and manager able to attend one 90-min training.
• No known shutdown, mobilisation or planned long absence during observation.
• Exclude only for pre-specified safety, data or continuity failure—record reason/date.
Constrained draw
1 Freeze candidate list
2 Block by region (E/Scotland), size/capacity and baseline OT quartile; balance job mix/travel where data allow.
3 Randomly assign within blocks using seed logged by Mikkel + finance witness.
If imbalance >20% on any pre-set factor: re-draw once before access; otherwise pause for sponsor decision.
Measurement calendar
• Baseline: 12 complete weeks immediately before launch (same weekdays).
• Observation: 12 complete weeks; synchronized Monday–Sunday windows for all groups.
• Activation delayed >7 days: crew remains assigned; exposure window flagged and ITT retained.
• Holiday/partial week: keep in panel, mark event; do not silently drop.
VOLUNTARY PARTICIPATION
Astrid may invite all eligible crews; crews may decline training or access without penalty. Decliners stay in the allocated group for analysis. Allocation is never based on enthusiasm, manager preference or expected savings.

## Slide 4
03 / METRIC, DATA & FIDELITY
Measure one primary outcome—and the ways savings can mislead
Cavendish Logistics • Emberline Clinic • planning assumption set • 20 Aug 2026
04
Primary outcome (weekly, crew level)
OT rate = approved overtime hours ÷ productive paid hours × 100; productive hours = paid hours on Emberline jobs, excluding leave/training.
Aggregate as crew-weighted 12-week mean; report hours and rate. Same payroll coding rules in England/Scotland.
Balancing / guardrails (secondary)
On-time job completion; missed/late jobs; safety incidents; absence; agency hours/cost; travel hours; rework/callbacks; schedule changes <24h; worker pulse (monthly).
Any material service, safety or cost-shift harm overrides an OT saving.
Required capture map
Payroll/timekeeping
OT + paid/productive hours; weekly freeze
Jasmin / payroll lead
Dispatch/job ledger
job volume, mix, urgent work, completion, travel
Astrid / ops
Tool audit log
login, eligible jobs scheduled, overrides, active weeks
Vendor admin + Mikkel
People/exception log
absence, transfers, cross-crew work, disruptions, approver
Crew managers; Mikkel
Data quality gate: completeness ≥95%, no duplicate crew-week keys, period alignment checked, and OT reconciles to payroll total within 1%. Late/unreliable fields escalate to Mikkel; missingness ≥10% in any group → pause analysis and label inconclusive.

## Slide 5
04 / ANALYSIS & DECISION RULES
Pre-declare what “success” means
Cavendish Logistics • Emberline Clinic • planning assumption set • 20 Aug 2026
05
Primary analysis
Intention-to-treat difference-in-differences on weekly crew panel: (post−baseline OT rate) treatment minus comparison, adjusted for region, capacity, job mix, travel and logged disruptions.
Estimate = percentage-point and relative change; cluster-robust or randomization-based interval at crew level. With 11 crews, precision is limited; no invented power claim.
Evidence standard
Baseline data readiness triggers a simple simulation/precision check before launch. Report 95% interval (or exact randomization interval) and all 11 assignments.
Regional/crew subgroups are exploratory only; no post-hoc “winner” claim.
Decision matrix (all conditions must be visible in the signed readout)
FAVORABLE
≥10% relative OT-rate reduction AND interval’s upper bound <0% (or exact p<0.10) AND no guardrail breach; supports scoped rollout case, not automatic purchase.
HARMFUL / UNFAVOURABLE
OT rate worsens ≥10% OR any material safety/service harm or cost shift; stop/rollback and investigate.
INCONCLUSIVE
Interval spans meaningful benefit and null/harm, fidelity <80% of eligible jobs, or missingness ≥10%; do not claim proof either way.
The vendor’s 20% is a contextual benchmark only. A raw before/after fall—without the concurrent comparison—is prohibited as the primary success claim.

## Slide 6
05 / FIDELITY, WITHDRAWAL & GATES
Exceptions are decided before outcomes are visible
Cavendish Logistics • Emberline Clinic • planning assumption set • 20 Aug 2026
06
Fidelity & contamination controls
• Pilot package identical: 90-min training, standard configuration, launch week, helpdesk and weekly check-in.
• Access is role-based; comparison crews blocked from pilot tenant. Log shared dispatchers, worker transfers, cross-crew jobs and support contacts.
• Fidelity flag: <80% eligible jobs scheduled in tool for 2 consecutive weeks → Amber review.
Prospective exception rule
• Crew may withdraw/ be diverted only for safety, client emergency, legal/privacy issue or documented continuity risk.
• Astrid requests; Mikkel records event, timing, crew, reason, approver and analytical treatment. Camila approves legal/privacy; Eamon approves continuity spend.
• After launch, a replacement may cover work operationally but never replaces the original crew in primary ITT. Replacement is tagged exploratory only.
PAUSE / STOP GATES
Immediate stop: safety incident, privacy/security breach, material service harm, or unauthorized access (Astrid + Camila; Eamon notified). Pause: data completeness <95%, contamination, fidelity <80%, or major co-intervention; Mikkel documents disposition within 2 business days. Resume only with written gate log.

## Slide 7
06 / TIMELINE, OWNERS & RECORDS
Run the pilot to a dated checklist
Cavendish Logistics • Emberline Clinic • planning assumption set • 20 Aug 2026
07
W−8 to −6
Design + eligibility freeze
Mikkel / Astrid
Signed protocol; eligible list; privacy notice
W−6 to −4
Baseline extract + quality gate
Jasmin + data owner
12-week panel; reconciliation report
W−4
Blocked random draw + balance check
Mikkel + finance witness
Seed, block table, imbalance decision
W−3 to −1
Contract, DPIA/monitoring review, access build, training
Camila + vendor admin
Executed terms; RBAC list; attendance
W0–12
Synchronized launch, weekly monitoring
Astrid + crew managers
Tool logs; exception/co-intervention log
W13–15
Freeze, clean, model, readout
Mikkel + Jasmin
Locked dataset; analysis memo; interval
W16
Final decision / records archive
Eamon (sponsor)
Decision minute; rollout/stop/inconclusive action
Record pack: frozen protocol/version, allocation seed and inputs, signed access/notice logs, weekly extracts, exceptions, gate decisions, analysis dataset hash, budget ledger and final decision minute.

## Slide 8
07 / ENGLAND–SCOTLAND & CONTRACTING
Common controls; local facts still need confirmation
Cavendish Logistics • Emberline Clinic • planning assumption set • 20 Aug 2026
08
COMMON UK / GB BASELINE
• UK GDPR / Data Protection Act principles: minimisation, purpose, access, retention, breach route. • Written pilot scope, security, support, export/deletion and non-production status. • Payroll/timekeeping definitions, H&S escalation, equality and worker transparency checks. • No individual performance monitoring beyond scheduling purpose without review.
CONFIRM SEPARATELY
England: local bank-holiday / client-access calendar, workforce consultation route, site rules and records owner. Scotland: Scottish bank-holiday / travel calendar, local workforce arrangements, site/client rules and records owner. These are planning checks—not legal conclusions.
CAMILA’S PRE-ACCESS CHECKLIST
Term + crew scope; price basis; exit/no auto-renewal or rollout; pilot acceptance as non-production; data ownership/processor roles; RBAC; sub-processors; incident SLA; support; export/deletion; IP and confidentiality; worker notice; no commitment created by moving beyond pilot.
Camila confirms unresolved jurisdiction, employment, client-contract and privacy questions in writing before access. Astrid owns local calendar/operations confirmation; Jasmin owns payroll record provenance.

## Slide 9
08 / LOW–BASE–HIGH GBP ESTIMATE
Planning budget: visible assumptions, not a quote
Cavendish Logistics • Emberline Clinic • planning assumption set • 20 Aug 2026
09
Assumption: 11 crews, 12-week observation; vendor pricing unknown, so license is an allowance. Internal rates are loaded planning rates.
Line item (qty × rate)
LOW
BASE
HIGH
Internal PM + finance + ops (160/220/300 h × £55)
£8,800
£12,100
£16,500
Vendor license allowance (11 crews × £80/£120/£180 × 3 mo)
£2,640
£3,960
£5,940
Implementation / integration (40/70/110 h × £85)
£3,400
£5,950
£9,350
Training + support (11 × £180/£260/£360)
£1,980
£2,860
£3,960
Data engineering + analysis (60/100/150 h × £75)
£4,500
£7,500
£11,250
Privacy / contracting review (20/35/55 h × £150)
£3,000
£5,250
£8,250
Travel / materials allowance
£800
£1,500
£2,500
Contingency (10% of above)
£2,512
£3,912
£5,775
£27,632
£43,032
£63,525
TOTAL (sum of visible lines)
Pause at W4: estimated committed £18k/£27k/£39k (license + setup + review + work done); avoidable remainder requires written stop decision. Excludes VAT, production rollout, payroll policy changes, hardware and client compensation.

## Slide 10
09 / DECISION REQUEST
Authorize only when the record is complete
Cavendish Logistics • Emberline Clinic • planning assumption set • 20 Aug 2026
10
Eamon’s approval today
☐ Fund scenario: Low £27,632 / Base £43,032 / High £63,525 ☐ Select 12-week window and confirm 5–6 treatment crews ☐ Name final data owner and finance witness ☐ Require Camila’s written pre-access confirmation ☐ Accept that “inconclusive” is a valid result
Before any login is issued
1 Eligibility + baseline quality gate passed 2 Allocation seed, block table and balance check archived 3 Contract, privacy/monitoring and local England/Scotland checks signed 4 RBAC, training, notice and support package ready 5 Stop/pause contacts tested; record pack location shared
Final decision at W16: FAVORABLE / HARMFUL–UNFAVOURABLE / INCONCLUSIVE → documented rollout, rollback, redesign or no-go. Never substitute an unadjusted before–after fall for the comparative readout.