## Instructions
Saltmarsh Press ¦ Annual ESOP Cycle Tracker
Purpose | Blank execution instrument for Eamon Rasmussen and benefits/payroll coverage.
How to use | Work top to bottom. Enter actual completion date, choose a status, confirm handoff, then capture comments or exceptions.
Status choices | Not started = no work begun; Waiting = external input or gate outstanding; In progress = actively being worked; Complete = finished and handed off; At risk = cutoff or dependency may be missed.
Derived variance | Actual completion date minus planned date. Blank until an actual date is entered; negative is early and positive is late.
Waiting state | Use Waiting when the named “Waiting on” party or dependency has not supplied the required input. Record what is missing in Owner comments or Exception.
June sequence | Payroll cutoff work → Form 5500 extension work → plan-audit sample work. Release election letters after the collision and allocation reconciliation are cleared.
Related files | saltmarsh_esop_cycle_plan.pptx and saltmarsh_esop_handoff_brief.docx

## Cycle Tracker
Week or date | Milestone | Owner | Waiting on | Dependency or gate | Planned date | Actual completion date | Status | Derived variance | Handoff confirmed | Owner comments | Exception
Week 1 ¦ 05 Jan 2026 | Confirm 31 December valuation anchor | Eamon Rasmussen | Saltmarsh Press records | Valuation date fixed: 31 Dec 2025 | 2026-01-05
Week 14 ¦ 30 Mar 2026 | Appraiser valuation draft prepared | Valuation appraiser | Eamon Rasmussen | Uses 31 Dec 2025 valuation anchor | 2026-03-30
Week 15 ¦ 06 Apr 2026 | Appraiser draft review | Javier Rivenburgh | Valuation appraiser | Appraiser draft received | 2026-04-06
Week 16 ¦ 14 Apr 2026 | Trustee approval gate | ESOP trustee | Javier Rivenburgh | Review complete; Q2 trustee meeting available | 2026-04-14
Week 17 ¦ 20 Apr 2026 | Allocation preparation | Eamon Rasmussen | ESOP trustee | Trustee approval required | 2026-04-20
Week 18 ¦ 27 Apr 2026 | Allocation reconciliation | Eamon Rasmussen | Payroll team | Allocation preparation complete | 2026-04-27
Week 19 ¦ 04 May 2026 | Diversification and election-letter preparation | Benefits operations | Eamon Rasmussen | Reconciled allocation inputs | 2026-05-04
Week 20 ¦ 08 Jun 2026 | Payroll cutoff work | Payroll team | Eamon Rasmussen | Cutoff: 12 Jun 2026; protect payroll feed | 2026-06-08
Week 21 ¦ 15 Jun 2026 | Form 5500 extension work | Plan administrator | Eamon Rasmussen | Extension filing due 30 Jun 2026 | 2026-06-15
Week 22 ¦ 22 Jun 2026 | Plan-audit sample work | Plan auditor | Eamon Rasmussen | Sample window: 22–26 Jun 2026 | 2026-06-22
Week 23 ¦ 29 Jun 2026 | Release election letters | Benefits operations | Eamon Rasmussen | Allocation reconciled; June collision cleared | 2026-06-29
Weeks 24–27 ¦ 30 Jun–29 Jul 2026 | Statutory election window (30 calendar days) | Eamon Rasmussen | Eligible participants | Starts on election-letter release | 2026-06-30
Week 28 ¦ 30 Jul 2026 | Retiree distribution preparation | Benefits operations | Eamon Rasmussen | Election window outcome; payroll cutoff 31 Jul 2026 | 2026-07-30
Week 30 ¦ 14 Aug 2026 | Retiree distribution release | Payroll team | Eamon Rasmussen | Distribution files approved; cutoff 14 Aug 2026 | 2026-08-14

## Lists
Status | Handoff confirmed
Not started | Yes
Waiting | No
In progress
Complete
At risk