## Slide 1
SALTMARSH PRESS • 2026 OPERATING CYCLE
From valuation anchor to retiree distribution
A dated handoff plan for Eamon Rasmussen and the frontline benefits / payroll desk.
Use the weekly roadmap, gate logic, and blank capture areas to make the next handoff explicit.
CYCLE ANCHOR
31 December 2025 Approval → allocation → letters → 30-day election window → distributions
Prepared by Javier Rivenburgh • source: saltmarsh_esop_cycle_source.xlsx
Saltmarsh Press | Annual ESOP cycle | 01

## Slide 2
OPERATING PLAN
Source assumptions and annual date spine
FIXED FACTS
Valuation anchor 31 Dec 2025 Trustee availability Q2 meeting • 14 Apr 2026 Election window 30 calendar days from letter release
CUT-OFFS
Payroll cutoff 12 Jun 2026 Form 5500 extension 30 Jun 2026 Plan-audit sample 22–26 Jun 2026
DISTRIBUTION
Distribution payroll cutoff 31 Jul 2026 Release cutoff 14 Aug 2026 Sequence clears June before letters.
Saltmarsh Press | Annual ESOP cycle | 02

## Slide 3
OPERATING PLAN
Weekly roadmap | make the next handoff visible
05 Jan
Anchor
30 Mar
Draft
06 Apr
Review
14 Apr
Approve
20 Apr
Allocate
27 Apr
Reconcile
04 May
Letters prep
08 Jun
Payroll
15 Jun
5500
22 Jun
Audit
29 Jun
Release
30 Jun
Window
30 Jul
Dist. prep
14 Aug
Release
Saltmarsh Press | Annual ESOP cycle | 03

## Slide 4
OPERATING PLAN
Gate 1 | draft → review → trustee approval
No approval, no allocation preparation.
1 APPRAISER DRAFT
30 Mar Appraiser hands draft to Javier / Eamon
2 REVIEW
06 Apr Javier checks draft and records open points
3 TRUSTEE GATE
14 Apr Q2 trustee meeting returns approval outcome
WAITING SIGNAL
Status = Waiting when the draft, review response, or approval outcome has not arrived; name the party and missing item in the tracker.
Saltmarsh Press | Annual ESOP cycle | 04

## Slide 5
OPERATING PLAN
Gate 2 | allocation → reconciliation → letters
ALLOCATE
20 Apr Eamon prepares approved allocation inputs
RECONCILE
27 Apr Payroll team validates totals and feed
LETTER PREP
04 May Benefits operations prepares diversification and election letters
Release gate: letters cannot go out until trustee approval, allocation preparation, and reconciliation are complete.
HANDOFF CHECK
Use Handoff confirmed = Yes only when the named recipient acknowledges the input. Otherwise leave blank and use Waiting.
Saltmarsh Press | Annual ESOP cycle | 05

## Slide 6
OPERATING PLAN
June collision | choose the order, protect the hard dates
Selected order: ① payroll cutoff work → ② Form 5500 extension work → ③ plan-audit sample work → letters release.
01 PAYROLL CUTOFF
08–12 Jun Clear the 12 Jun payroll cutoff first; it feeds downstream payroll timing.
02 FORM 5500 EXTENSION
15–19 Jun Use the next week before the 30 Jun deadline.
03 PLAN-AUDIT SAMPLE
22–26 Jun Reserve the audit sample window.
Rationale: protect the earliest hard cutoff, retain each activity, and release letters only after the collision and reconciliation clear on 29 Jun.
Saltmarsh Press | Annual ESOP cycle | 06

## Slide 7
OPERATING PLAN
Election window → distribution execution
RELEASE LETTERS
29 Jun 2026 Benefits operations releases approved letters after June work clears.
30-DAY WINDOW
30 Jun–29 Jul 2026 Source assumption: 30 calendar days.
DISTRIBUTE
30 Jul prep → 14 Aug release Outcome feeds distribution files; 31 Jul payroll cutoff applies.
Gate: do not prepare or release distributions until the election window outcome is known and the applicable cutoff is protected.
Saltmarsh Press | Annual ESOP cycle | 07

## Slide 8
OPERATING PLAN
Handoff and escalation map
Appraiser
→
Javier / Eamon
Valuation draft
Javier
→
ESOP trustee
Reviewed draft / open points
ESOP trustee
→
Eamon
Approval outcome
Payroll team
→
Eamon
Reconciled allocation input
Benefits operations
→
Eamon / participants
Election letters
Eamon
→
Payroll team
Approved distribution file
ESCALATE
If a handoff is late or incomplete: set Status = At risk, name the missing item and party, record the cutoff threatened, and notify Eamon / the owner shown.
Saltmarsh Press | Annual ESOP cycle | 08

## Slide 9
OPERATING PLAN
Blank action & exception capture | use during the cycle
Next action / owner / gate
Exception / escalation notes
Leave blank until the cycle is live. Pair every exception with a status, waiting party, threatened cutoff, and next follow-up.
Saltmarsh Press | Annual ESOP cycle | 09