## Register
Glassmere alternate approval — opening register
Exported 06/02/2026 ¦ starting state for review replay
Record key | Category | Opening status | Owner | Evidence reference | Decision relevance | Opening value | Notes
TECH-01 | Finding | Open | Mateo Ainsworth | REG-TECH-01 | Corrosion witness at rail seat |  | Initial review required
TECH-02 | Finding | Open | Lucia Jelinek | REG-TECH-02 | Clamp-load retention |  | Initial review required
EVID-01 | Evidence | Pending | Mateo Ainsworth | REG-EVID-01 | Fatigue evidence acceptance |  | Accelerated test boundary applies
TRIAL-01 | Control | Draft | Lucia Jelinek | REG-TRIAL-01 | Staged trial readiness |  | Control plan not yet approved
COMM-01 | Commercial | Pending | Lachlan Mikkelsen | REG-COMM-01 | Unit rate confirmation | 18.4700000003 USD/clip | Quoted supply rate
TECH-EDGE-01 | Finding | Closed | Mateo Ainsworth | REG-EDGE-01 | Verification sample acceptance |  | Apparent closure at opening