DUNCASTLE WHOLESALE

Employee Interview Travel Sequence Plan

Operational plan for HR staffing and external-audit file handover | Window: 01-11 December 2026 | Handover: close of business, 11 December

Orientation and control notes

| Control | Meaning |
| --- | --- |
| Purpose | 31 authorized employee-interview appointments across six branches and two depots. Prepared by investigator Solomon Ngata for HR partner Freya Lindholm and site coordinators. This is an operational booking plan only: no findings, attendance, evidence, or interview completion is asserted. |
| Status / confirmation | BOOKED = calendar slot arranged; PLANNED = intended slot with local confirmation open; RESERVED = travel time, not an interview. No row is marked completed. The audit commitment is to show every appointment arranged before handover, including planned appointments; it does not guarantee attendance or evidence. |
| Staffing | Solomon is required for every interview. Freya is the sole HR partner and is scheduled only once at any time. Where F1 appears, the labeled fallback is Solomon plus the named site coordinator as local witness; the coordinator confirms room, attendee and witness record before the slot. Limitation: this is not the ideal Freya-attended arrangement. |
| Dependency gates | D1-01 follows B1-01 (Northgate goods-in supervisor); D1-02 follows B2-01 (Riverway goods-in supervisor); D2-01 follows B3-01 (Meadow Park goods-in supervisor). “Gate” means do not start the depot session unless its prerequisite interview has been conducted; retain the booking as pending if it has not. |
| Sequence / travel | Branch information may circulate within one day. The plan therefore batches each branch in a single morning, then moves to the next site; this is a neutral scheduling limitation, not a conclusion about staff. Meadow Park Branch trades Thursday-Sunday only. Meadow Park and West Distribution Depot are approximately four hours apart; T-01 reserves the driving leg and 30-minute contingency. |

Location allocation

| Location | Type / availability | Authorized interviews |
| --- | --- | --- |
| Northgate Branch | Branch | 4 |
| Riverway Branch | Branch | 4 |
| Meadow Park Branch | Branch - Thursday-Sunday trading only | 4 |
| Harbour Branch | Branch | 4 |
| Eastfield Branch | Branch | 4 |
| Hilltop Branch | Branch | 4 |
| Central Distribution Depot | Depot | 4 |
| West Distribution Depot | Depot | 3 |
| Total authorized interviews |  | 31 |

Booking owner convention: each “Open” confirmation is owned by the specified site coordinator. Travel estimates and room availability remain planning assumptions until locally confirmed.

Dated operational schedule | 01-03 December

| Seq / ID | Date / time (local) | Site | Interviewee role | Required staffing | Status / confirmation | Dependency or timing note |
| --- | --- | --- | --- | --- | --- | --- |
| 01 / B1-01 | 01 Dec Tue 08:30-09:15 | Northgate Branch (Branch) | Goods-in supervisor | Solomon + Freya | BOOKED - | B1-01 prerequisite for D1-01 |
| 02 / B1-02 | 01 Dec Tue 09:30-10:15 | Northgate Branch (Branch) | Branch manager | Solomon + Freya | BOOKED - | same-site buffer 15m |
| 03 / B1-03 | 01 Dec Tue 10:30-11:15 | Northgate Branch (Branch) | Sales-floor colleague | Solomon + Freya | BOOKED - | same-site buffer 15m |
| 04 / B1-04 | 01 Dec Tue 11:30-12:15 | Northgate Branch (Branch) | Cash-office colleague | Solomon + Freya | PLANNED Open: Northgate site coordinator | local confirmation due before slot |
| 05 / B2-01 | 02 Dec Wed 08:30-09:15 | Riverway Branch (Branch) | Goods-in supervisor | Solomon + Freya | BOOKED - | B2-01 prerequisite for D1-02 |
| 06 / B2-02 | 02 Dec Wed 09:30-10:15 | Riverway Branch (Branch) | Branch manager | Solomon + Freya | BOOKED - | same-site buffer 15m |
| 07 / B2-03 | 02 Dec Wed 10:30-11:15 | Riverway Branch (Branch) | Stock-control colleague | Solomon + Freya | PLANNED Open: Riverway site coordinator | local confirmation due before slot |
| 08 / B2-04 | 02 Dec Wed 11:30-12:15 | Riverway Branch (Branch) | Checkout colleague | Solomon + Freya | BOOKED - | same-site buffer 15m |
| 09 / B3-01 | 03 Dec Thu 08:30-09:15 | Meadow Park Branch (Branch) | Goods-in supervisor | Solomon + Freya | BOOKED - | B3-01 prerequisite for D2-01 |
| 10 / B3-02 | 03 Dec Thu 09:30-10:15 | Meadow Park Branch (Branch) | Branch manager | Solomon + Freya | BOOKED - | restricted branch: Thu-Sun |
| 11 / B3-03 | 03 Dec Thu 10:30-11:15 | Meadow Park Branch (Branch) | Stockroom colleague | Solomon + Freya | PLANNED Open: Meadow Park site coordinator | restricted branch: Thu-Sun |

Timing convention: all times are local site time. Each 45-minute appointment is separated by a 15-minute same-site buffer. No interview is a completed interview until attendance and record closure are separately logged.

Dated operational schedule | 03-06 December

| Seq / ID | Date / time (local) | Site | Interviewee role | Required staffing | Status / confirmation | Dependency or timing note |
| --- | --- | --- | --- | --- | --- | --- |
| T-01 | 04 Dec Fri 08:00-12:00 | TRAVEL Meadow Park -> West Depot | Not an interview | Solomon + Freya | RESERVED | 4h driving estimate + 30m contingency; next session 13:00 |
| 12 / B3-04 | 03 Dec Thu 11:30-12:15 | Meadow Park Branch (Branch) | Sales-floor colleague | Solomon + Freya | BOOKED - | restricted branch: Thu-Sun |
| 13 / D2-01 | 04 Dec Fri 13:00-13:45 | West Distribution Depot (Depot) | Depot goods-in records colleague | Solomon + Freya | BOOKED Gate: B3-01 conducted first | after T-01; do not start if gate unmet |
| 14 / D2-02 | 04 Dec Fri 14:00-14:45 | West Distribution Depot (Depot) | Depot shift colleague | Solomon + local site coordinator | PLANNED Open: West Depot site coordinator | FALLBACK F1; local witness record |
| 15 / D2-03 | 04 Dec Fri 15:00-15:45 | West Distribution Depot (Depot) | Depot dispatch colleague | Solomon + local site coordinator | PLANNED Open: West Depot site coordinator | FALLBACK F1; local witness record |
| 16 / D1-01 | 05 Dec Sat 08:30-09:15 | Central Distribution Depot (Depot) | Depot goods-in records colleague | Solomon + Freya | BOOKED Gate: B1-01 conducted first | dependent depot appointment |
| 17 / D1-02 | 05 Dec Sat 09:30-10:15 | Central Distribution Depot (Depot) | Depot receiving colleague | Solomon + Freya | BOOKED Gate: B2-01 conducted first | dependent depot appointment |
| 18 / D1-03 | 05 Dec Sat 10:30-11:15 | Central Distribution Depot (Depot) | Depot inventory colleague | Solomon + local site coordinator | PLANNED Open: Central Depot site coordinator | FALLBACK F1; local witness record |
| 19 / D1-04 | 05 Dec Sat 11:30-12:15 | Central Distribution Depot (Depot) | Depot administration colleague | Solomon + local site coordinator | PLANNED Open: Central Depot site coordinator | FALLBACK F1; local witness record |
| 20 / B4-01 | 06 Dec Sun 08:30-09:15 | Harbour Branch (Branch) | Goods-in colleague | Solomon + Freya | BOOKED - | same-site buffer 15m |
| 21 / B4-02 | 06 Dec Sun 09:30-10:15 | Harbour Branch (Branch) | Branch manager | Solomon + Freya | BOOKED - | same-site buffer 15m |

Timing convention: all times are local site time. Each 45-minute appointment is separated by a 15-minute same-site buffer. No interview is a completed interview until attendance and record closure are separately logged.

Dated operational schedule | 06-08 December and handover

| Seq / ID | Date / time (local) | Site | Interviewee role | Required staffing | Status / confirmation | Dependency or timing note |
| --- | --- | --- | --- | --- | --- | --- |
| 22 / B4-03 | 06 Dec Sun 10:30-11:15 | Harbour Branch (Branch) | Customer-service colleague | Solomon + local site coordinator | PLANNED Open: Harbour site coordinator | FALLBACK F1; local witness record |
| 23 / B4-04 | 06 Dec Sun 11:30-12:15 | Harbour Branch (Branch) | Cash-office colleague | Solomon + local site coordinator | PLANNED Open: Harbour site coordinator | FALLBACK F1; local witness record |
| 24 / B5-01 | 07 Dec Mon 08:30-09:15 | Eastfield Branch (Branch) | Goods-in colleague | Solomon + Freya | BOOKED - | same-site buffer 15m |
| 25 / B5-02 | 07 Dec Mon 09:30-10:15 | Eastfield Branch (Branch) | Branch manager | Solomon + Freya | BOOKED - | same-site buffer 15m |
| 26 / B5-03 | 07 Dec Mon 10:30-11:15 | Eastfield Branch (Branch) | Stock-control colleague | Solomon + Freya | PLANNED Open: Eastfield site coordinator | local confirmation due before slot |
| 27 / B5-04 | 07 Dec Mon 11:30-12:15 | Eastfield Branch (Branch) | Sales-floor colleague | Solomon + Freya | BOOKED - | same-site buffer 15m |
| 28 / B6-01 | 08 Dec Tue 08:30-09:15 | Hilltop Branch (Branch) | Goods-in colleague | Solomon + Freya | BOOKED - | same-site buffer 15m |
| 29 / B6-02 | 08 Dec Tue 09:30-10:15 | Hilltop Branch (Branch) | Branch manager | Solomon + Freya | BOOKED - | same-site buffer 15m |
| 30 / B6-03 | 08 Dec Tue 10:30-11:15 | Hilltop Branch (Branch) | Stockroom colleague | Solomon + local site coordinator | PLANNED Open: Hilltop site coordinator | FALLBACK F1; local witness record |
| 31 / B6-04 | 08 Dec Tue 11:30-12:15 | Hilltop Branch (Branch) | Checkout colleague | Solomon + Freya | PLANNED Open: Hilltop site coordinator | final scheduled interview; before 11 Dec handover |

Timing convention: all times are local site time. Each 45-minute appointment is separated by a 15-minute same-site buffer. No interview is a completed interview until attendance and record closure are separately logged.

Handover boundary

Final scheduled interview: B6-04, 08 Dec 2026, 11:30-12:15, Hilltop Branch, status PLANNED (local confirmation open). The operational deadline is external-audit file handover at close of business on 11 Dec 2026. That handover is separate from interview attendance or record completion.