## Deliverables
Fenwick Marsh Environmental — Q3 2026 permitting workload
Operational records effective 15 May 2026 ¦ Reporting week starts Monday
Deliverable ID | Deliverable | Client | Class | Earliest Week | Latest Week | Required Effort (h) | Major Submission? | Owner milestone | Control note
D1 | Saltcombe wetlands permit variation | Saltcombe Provisions | Major | W02 | W08 | 100 | Yes | Client submission | Approved water/wetlands signatory + independent review + supervised submission
D2 | Westmere air permit variation | Westmere Logistics | Major | W03 | W11 | 98 | Yes | Client submission | Approved air signatory + independent review
D3 | Saltcombe ecology screening | Saltcombe Provisions | Standard | W01 | W06 | 30 | No | Screening memo | Technical record
D4 | Westmere waste controls | Westmere Logistics | Standard | W06 | W08 | 42 | No | Client control review | Client-facing review
D5 | Westmere noise assessment | Westmere Logistics | Standard | W02 | W04 | 36 | No | Noise memo | Technical record
D6 | Saltcombe drainage note | Saltcombe Provisions | Standard | W01 | W03 | 40 | No | Water discipline review | Technical review
D7 | Westmere solvent inventory | Westmere Logistics | Standard | W02 | W03 | 24 | No | Risk note | Operational control
D8 | Saltcombe trade-effluent pre-application | Saltcombe Provisions | Standard | W09 | W10 | 26 | No | Client pre-application | Approved water signatory
D9 | Quarterly permit register | Both | Standard | W09 | W10 | 32 | No | Register QA | Portfolio control

## Activities
Activity-level source records
Effort is stipulated hours; dependencies require prior-week completion.
Activity ID | Deliverable ID | Activity | Competence tags | Earliest Week | Latest Week | Required Effort (h) | Splittable | Predecessor | Required role
D1-A | D1 | Scope and requirements | water;wetlands | W02 | W02 | 12 | No |  | Owner
D1-B | D1 | Site evidence and walkover | water;wetlands | W03 | W03 | 18 | No | D1-A | Owner
D1-C | D1 | Technical assessment | water;wetlands | W04 | W04 | 20 | No | D1-B | Owner
D1-D | D1 | Draft variation pack | water;drafting | W05 | W05 | 18 | No | D1-C | Owner
D1-E | D1 | Independent assurance | independent review | W06 | W06 | 10 | No | D1-D | Reviewer
D1-F | D1 | Client submission | water;submission | W08 | W08 | 6 | No | D1-E | Submission; supervised
D2-A | D2 | Scope and requirements | air | W03 | W03 | 10 | No |  | Owner
D2-B | D2 | Site test | air | W04 | W04 | 16 | No | D2-A | Owner
D2-C | D2 | Air model and inventory | air modelling | W05 | W05 | 24 | No | D2-B | Owner
D2-D | D2 | Draft variation pack | air;drafting | W06 | W06 | 18 | No | D2-C | Owner
D2-E | D2 | Independent assurance | independent review | W08 | W08 | 10 | No | D2-D | Reviewer
D2-F | D2 | Client submission | air;submission | W11 | W11 | 6 | No | D2-E | Submission
D3-A | D3 | Ecology scope | ecology | W01 | W01 | 8 | No |  | Owner
D3-B | D3 | Ecology walkover | ecology | W05 | W05 | 12 | No | D3-A | Owner
D3-C | D3 | Screening memo | ecology | W06 | W06 | 10 | No | D3-B | Owner
D4-A | D4 | Waste audit | waste;site audit | W06 | W06 | 14 | No |  | Owner
D4-B | D4 | Control design | waste;controls | W07 | W07 | 16 | No | D4-A | Owner
D4-C | D4 | Client control review | waste review | W08 | W08 | 6 | No | D4-B | Reviewer
D5-A | D5 | Noise survey | noise | W02 | W02 | 12 | No |  | Owner
D5-B | D5 | Noise assessment | noise;quantitative | W03 | W03 | 16 | No | D5-A | Owner
D5-C | D5 | Noise memo | noise | W04 | W04 | 8 | No | D5-B | Owner
D6-A | D6 | Drainage desktop review | drainage | W01 | W01 | 10 | No |  | Owner
D6-B | D6 | Drainage design note | drainage | W02 | W02 | 18 | No | D6-A | Owner
D6-C | D6 | Water discipline review | water review | W03 | W03 | 6 | No | D6-B | Reviewer
D7-A | D7 | Solvent inventory | waste;inventory | W02 | W02 | 12 | No |  | Owner
D7-B | D7 | Risk note | controls | W03 | W03 | 12 | No | D7-A | Owner
D8-A | D8 | Trade-effluent pre-app draft | water;drafting | W09 | W09 | 14 | No |  | Owner
D8-B | D8 | Client pre-application | water;submission | W10 | W10 | 6 | No | D8-A | Signatory
D9-A | D9 | Register compilation | permit register | W09 | W09 | 16 | No |  | Owner
D9-B | D9 | Register QA | independent QA | W10 | W10 | 8 | No | D9-A | Reviewer

## Consultants
Consultant roster and weekly net capacity
Listed capacity is time remaining after other committed work.
Consultant | Net weekly capacity (h) | Exceptions | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | Competence profile | Client continuity | Approval record
Marisol Reinholt | 32 | W05= 0h, W09= 24h | 32 | 32 | 32 | 32 | 0 | 32 | 32 | 32 | 24 | 32 | 32 | 32 | 32 | Water; Wetlands; Integrated permits | Saltcombe | Approved signatory: water, wetlands, integrated
Ravi Moravec | 30 | W08= 0h, W12= 20h | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 30 | 30 | 30 | 20 | 30 | Air; Waste; Logistics depot | Westmere | Approved signatory: air, waste, logistics
Chidi Jankowski | 34 | W04= 20h | 34 | 34 | 34 | 20 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | Ecology; Drainage; Water evidence; Independent review | Both | Not an approved signatory
Arjun Redmayne | 32 | W07= 24h | 32 | 32 | 32 | 32 | 32 | 32 | 24 | 32 | 32 | 32 | 32 | 32 | 32 | Air modelling; Emissions; Noise; Quantitative analysis | Westmere | Not an approved signatory
Lorcan Dimitrov | 34 | W10= 18h | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 18 | 34 | 34 | 34 | Waste operations; Site audits; Permit registers; Controls | Westmere | Not an approved signatory
Casimir Oyelowo | 30 | W06= 24h | 30 | 30 | 30 | 30 | 30 | 24 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | Water; Wetlands; Drafting; Client preparation | Saltcombe | Not yet approved; supervised submission required by W08

## Controls
England permitting controls and reporting terms
Topic | Rule
Effective date | 15 May 2026
Client-facing sign-off | Only Marisol Reinholt (water/wetlands/integrated) and Ravi Moravec (air/waste/logistics) may sign.
Major permit control | Each major submission needs discipline-appropriate approved signatory and independent reviewer distinct from drafter.
Supervised submission | Casimir Oyelowo must own and complete one qualifying water/wetlands major submission by end W08 under Marisol Reinholt.
Mutual exclusion | D1 site evidence vs D3 ecology walkover; D2 site test vs D4 waste audit must be in different workweeks.
Reporting terms | Accountable owner owns deliverable and ownership milestones. Support allocation is scheduled hours by another consultant. Utilisation = planned / net available. Remaining capacity = available - planned.