## Duty Schedule
Ballantyne Market Co-op ¦ interim meat & seafood duty schedule
Coverage: 06 Jul 2026 - 11 Oct 2026 (14 operational weeks) | [6 empty] | Prepared for 24 Jun board meeting
Operational Week | Duty ID | Duty | Workflow | Owner | Start | Finish | Hours | Predecessor | Handoff Evidence | Backup or Escalation | Compliance Status
2026-07-06 | ORD_FORECAST | Demand forecast | Ordering | Marisol Reyes | 2026-07-06 08:00 | 2026-07-06 10:00 | 2 |  | Forecast workbook | Amara Draganov | COMPLIANT
2026-07-06 | ORD_DRAFT | Purchase-order draft | Ordering | Marisol Reyes | 2026-07-06 10:00 | 2026-07-06 13:00 | 3 | ORD_FORECAST | Draft PO | Amara Draganov | COMPLIANT
2026-07-06 | ORD_HACCP | HACCP order review | Ordering | Emeric Novak | 2026-07-06 13:00 | 2026-07-06 14:00 | 1 | ORD_DRAFT | HACCP initials | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-06 | ORD_RELEASE | Vendor order release | Ordering | Marisol Reyes | 2026-07-06 14:00 | 2026-07-06 15:00 | 1 | ORD_HACCP | Vendor release confirmation | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-06 | RCV_VERIFY | Delivery verification | Receiving | Yusuf Gasparyan | 2026-07-09 06:00 | 2026-07-09 08:00 | 2 |  | Receiving log | Emeric Novak | COMPLIANT
2026-07-06 | RCV_DISPOSITION | HACCP disposition | Receiving | Emeric Novak | 2026-07-09 08:00 | 2026-07-09 09:00 | 1 | RCV_VERIFY | Disposition entry | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-06 | RCV_TRACE | Lot traceability closeout | Receiving | Emeric Novak | 2026-07-09 09:00 | 2026-07-09 10:00 | 1 | RCV_DISPOSITION | Lot traceability closeout | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-06 | PROD_PLAN | Production cut plan | Production training | Amara Draganov | 2026-07-07 07:00 | 2026-07-07 10:00 | 3 |  | Cut plan | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-06 | PROD_DEMO | Closing-crew demonstration | Production training | Amara Draganov | 2026-07-07 10:00 | 2026-07-07 11:00 | 1 | PROD_PLAN | Crew demonstration acknowledgment | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-06 | PROD_RECORD | Competency record | Production training | Amara Draganov | 2026-07-07 11:00 | 2026-07-07 12:00 | 1 | PROD_DEMO | Competency record | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-06 | INV_COUNT | Cycle count | Inventory | Yusuf Gasparyan | 2026-07-08 07:00 | 2026-07-08 10:00 | 3 |  | Count sheet | Marisol Reyes | COMPLIANT
2026-07-06 | INV_VARIANCE | Variance review | Inventory | Yusuf Gasparyan | 2026-07-08 10:00 | 2026-07-08 12:00 | 2 | INV_COUNT | Variance log | Marisol Reyes | COMPLIANT
2026-07-06 | INV_SHRINK | Shrink brief | Inventory | Yusuf Gasparyan | 2026-07-08 12:00 | 2026-07-08 13:00 | 1 | INV_VARIANCE | Shrink brief acknowledgment | Marisol Reyes | COMPLIANT
2026-07-06 | SAN_VERIFY | Sanitation verification | Sanitation | Emeric Novak | 2026-07-10 15:00 | 2026-07-10 17:00 | 2 |  | Sanitation verification log | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-13 | ORD_FORECAST | Demand forecast | Ordering | Marisol Reyes | 2026-07-13 08:00 | 2026-07-13 10:00 | 2 |  | Forecast workbook | Amara Draganov | COMPLIANT
2026-07-13 | ORD_DRAFT | Purchase-order draft | Ordering | Marisol Reyes | 2026-07-13 10:00 | 2026-07-13 13:00 | 3 | ORD_FORECAST | Draft PO | Amara Draganov | COMPLIANT
2026-07-13 | ORD_HACCP | HACCP order review | Ordering | Emeric Novak | 2026-07-13 13:00 | 2026-07-13 14:00 | 1 | ORD_DRAFT | HACCP initials | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-13 | ORD_RELEASE | Vendor order release | Ordering | Marisol Reyes | 2026-07-13 14:00 | 2026-07-13 15:00 | 1 | ORD_HACCP | Vendor release confirmation | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-13 | RCV_VERIFY | Delivery verification | Receiving | Yusuf Gasparyan | 2026-07-16 06:00 | 2026-07-16 08:00 | 2 |  | Receiving log | Emeric Novak | COMPLIANT
2026-07-13 | RCV_DISPOSITION | HACCP disposition | Receiving | Emeric Novak | 2026-07-16 08:00 | 2026-07-16 09:00 | 1 | RCV_VERIFY | Disposition entry | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-13 | RCV_TRACE | Lot traceability closeout | Receiving | Emeric Novak | 2026-07-16 09:00 | 2026-07-16 10:00 | 1 | RCV_DISPOSITION | Lot traceability closeout | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-13 | PROD_PLAN | Production cut plan | Production training | Amara Draganov | 2026-07-14 07:00 | 2026-07-14 10:00 | 3 |  | Cut plan | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-13 | PROD_DEMO | Closing-crew demonstration | Production training | Amara Draganov | 2026-07-14 10:00 | 2026-07-14 11:00 | 1 | PROD_PLAN | Crew demonstration acknowledgment | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-13 | PROD_RECORD | Competency record | Production training | Amara Draganov | 2026-07-14 11:00 | 2026-07-14 12:00 | 1 | PROD_DEMO | Competency record | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-13 | INV_COUNT | Cycle count | Inventory | Yusuf Gasparyan | 2026-07-15 07:00 | 2026-07-15 10:00 | 3 |  | Count sheet | Marisol Reyes | COMPLIANT
2026-07-13 | INV_VARIANCE | Variance review | Inventory | Yusuf Gasparyan | 2026-07-15 10:00 | 2026-07-15 12:00 | 2 | INV_COUNT | Variance log | Marisol Reyes | COMPLIANT
2026-07-13 | INV_SHRINK | Shrink brief | Inventory | Yusuf Gasparyan | 2026-07-15 12:00 | 2026-07-15 13:00 | 1 | INV_VARIANCE | Shrink brief acknowledgment | Marisol Reyes | COMPLIANT
2026-07-13 | SAN_VERIFY | Sanitation verification | Sanitation | Emeric Novak | 2026-07-17 15:00 | 2026-07-17 17:00 | 2 |  | Sanitation verification log | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-20 | ORD_FORECAST | Demand forecast | Ordering | Marisol Reyes | 2026-07-20 08:00 | 2026-07-20 10:00 | 2 |  | Forecast workbook | Amara Draganov | COMPLIANT
2026-07-20 | ORD_DRAFT | Purchase-order draft | Ordering | Marisol Reyes | 2026-07-20 10:00 | 2026-07-20 13:00 | 3 | ORD_FORECAST | Draft PO | Amara Draganov | COMPLIANT
2026-07-20 | ORD_HACCP | HACCP order review | Ordering | Emeric Novak | 2026-07-20 13:00 | 2026-07-20 14:00 | 1 | ORD_DRAFT | HACCP initials | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-20 | ORD_RELEASE | Vendor order release | Ordering | Marisol Reyes | 2026-07-20 14:00 | 2026-07-20 15:00 | 1 | ORD_HACCP | Vendor release confirmation | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-20 | RCV_VERIFY | Delivery verification | Receiving | Yusuf Gasparyan | 2026-07-23 06:00 | 2026-07-23 08:00 | 2 |  | Receiving log | Emeric Novak | COMPLIANT
2026-07-20 | RCV_DISPOSITION | HACCP disposition | Receiving | Emeric Novak | 2026-07-23 08:00 | 2026-07-23 09:00 | 1 | RCV_VERIFY | Disposition entry | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-20 | RCV_TRACE | Lot traceability closeout | Receiving | Emeric Novak | 2026-07-23 09:00 | 2026-07-23 10:00 | 1 | RCV_DISPOSITION | Lot traceability closeout | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-20 | PROD_PLAN | Production cut plan | Production training | Amara Draganov | 2026-07-21 07:00 | 2026-07-21 10:00 | 3 |  | Cut plan | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-20 | PROD_DEMO | Closing-crew demonstration | Production training | Amara Draganov | 2026-07-21 10:00 | 2026-07-21 11:00 | 1 | PROD_PLAN | Crew demonstration acknowledgment | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-20 | PROD_RECORD | Competency record | Production training | Amara Draganov | 2026-07-21 11:00 | 2026-07-21 12:00 | 1 | PROD_DEMO | Competency record | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-20 | INV_COUNT | Cycle count | Inventory | Yusuf Gasparyan | 2026-07-22 07:00 | 2026-07-22 10:00 | 3 |  | Count sheet | Marisol Reyes | COMPLIANT
2026-07-20 | INV_VARIANCE | Variance review | Inventory | Yusuf Gasparyan | 2026-07-22 10:00 | 2026-07-22 12:00 | 2 | INV_COUNT | Variance log | Marisol Reyes | COMPLIANT
2026-07-20 | INV_SHRINK | Shrink brief | Inventory | Yusuf Gasparyan | 2026-07-22 12:00 | 2026-07-22 13:00 | 1 | INV_VARIANCE | Shrink brief acknowledgment | Marisol Reyes | COMPLIANT
2026-07-20 | SAN_VERIFY | Sanitation verification | Sanitation | Emeric Novak | 2026-07-24 15:00 | 2026-07-24 17:00 | 2 |  | Sanitation verification log | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-27 | ORD_FORECAST | Demand forecast | Ordering | Marisol Reyes | 2026-07-27 08:00 | 2026-07-27 10:00 | 2 |  | Forecast workbook | Amara Draganov | COMPLIANT
2026-07-27 | ORD_DRAFT | Purchase-order draft | Ordering | Marisol Reyes | 2026-07-27 10:00 | 2026-07-27 13:00 | 3 | ORD_FORECAST | Draft PO | Amara Draganov | COMPLIANT
2026-07-27 | ORD_HACCP | HACCP order review | Ordering | Emeric Novak | 2026-07-27 13:00 | 2026-07-27 14:00 | 1 | ORD_DRAFT | HACCP initials | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-27 | ORD_RELEASE | Vendor order release | Ordering | Marisol Reyes | 2026-07-27 14:00 | 2026-07-27 15:00 | 1 | ORD_HACCP | Vendor release confirmation | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-27 | RCV_VERIFY | Delivery verification | Receiving | Yusuf Gasparyan | 2026-07-30 06:00 | 2026-07-30 08:00 | 2 |  | Receiving log | Emeric Novak | COMPLIANT
2026-07-27 | RCV_DISPOSITION | HACCP disposition | Receiving | Emeric Novak | 2026-07-30 08:00 | 2026-07-30 09:00 | 1 | RCV_VERIFY | Disposition entry | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-27 | RCV_TRACE | Lot traceability closeout | Receiving | Emeric Novak | 2026-07-30 09:00 | 2026-07-30 10:00 | 1 | RCV_DISPOSITION | Lot traceability closeout | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-27 | PROD_PLAN | Production cut plan | Production training | Amara Draganov | 2026-07-28 07:00 | 2026-07-28 10:00 | 3 |  | Cut plan | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-27 | PROD_DEMO | Closing-crew demonstration | Production training | Amara Draganov | 2026-07-28 10:00 | 2026-07-28 11:00 | 1 | PROD_PLAN | Crew demonstration acknowledgment | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-27 | PROD_RECORD | Competency record | Production training | Amara Draganov | 2026-07-28 11:00 | 2026-07-28 12:00 | 1 | PROD_DEMO | Competency record | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-07-27 | INV_COUNT | Cycle count | Inventory | Yusuf Gasparyan | 2026-07-29 07:00 | 2026-07-29 10:00 | 3 |  | Count sheet | Marisol Reyes | COMPLIANT
2026-07-27 | INV_VARIANCE | Variance review | Inventory | Yusuf Gasparyan | 2026-07-29 10:00 | 2026-07-29 12:00 | 2 | INV_COUNT | Variance log | Marisol Reyes | COMPLIANT
2026-07-27 | INV_SHRINK | Shrink brief | Inventory | Yusuf Gasparyan | 2026-07-29 12:00 | 2026-07-29 13:00 | 1 | INV_VARIANCE | Shrink brief acknowledgment | Marisol Reyes | COMPLIANT
2026-07-27 | SAN_VERIFY | Sanitation verification | Sanitation | Emeric Novak | 2026-07-31 15:00 | 2026-07-31 17:00 | 2 |  | Sanitation verification log | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-03 | ORD_FORECAST | Demand forecast | Ordering | Marisol Reyes | 2026-08-03 08:00 | 2026-08-03 10:00 | 2 |  | Forecast workbook | Amara Draganov | COMPLIANT
2026-08-03 | ORD_DRAFT | Purchase-order draft | Ordering | Marisol Reyes | 2026-08-03 10:00 | 2026-08-03 13:00 | 3 | ORD_FORECAST | Draft PO | Amara Draganov | COMPLIANT
2026-08-03 | ORD_HACCP | HACCP order review | Ordering | Emeric Novak | 2026-08-03 13:00 | 2026-08-03 14:00 | 1 | ORD_DRAFT | HACCP initials | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-03 | ORD_RELEASE | Vendor order release | Ordering | Marisol Reyes | 2026-08-03 14:00 | 2026-08-03 15:00 | 1 | ORD_HACCP | Vendor release confirmation | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-03 | RCV_VERIFY | Delivery verification | Receiving | Yusuf Gasparyan | 2026-08-06 06:00 | 2026-08-06 08:00 | 2 |  | Receiving log | Emeric Novak | COMPLIANT
2026-08-03 | RCV_DISPOSITION | HACCP disposition | Receiving | Emeric Novak | 2026-08-06 08:00 | 2026-08-06 09:00 | 1 | RCV_VERIFY | Disposition entry | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-03 | RCV_TRACE | Lot traceability closeout | Receiving | Emeric Novak | 2026-08-06 09:00 | 2026-08-06 10:00 | 1 | RCV_DISPOSITION | Lot traceability closeout | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-03 | PROD_PLAN | Production cut plan | Production training | Amara Draganov | 2026-08-04 07:00 | 2026-08-04 10:00 | 3 |  | Cut plan | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-03 | PROD_DEMO | Closing-crew demonstration | Production training | Amara Draganov | 2026-08-04 10:00 | 2026-08-04 11:00 | 1 | PROD_PLAN | Crew demonstration acknowledgment | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-03 | PROD_RECORD | Competency record | Production training | Amara Draganov | 2026-08-04 11:00 | 2026-08-04 12:00 | 1 | PROD_DEMO | Competency record | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-03 | INV_COUNT | Cycle count | Inventory | Yusuf Gasparyan | 2026-08-05 07:00 | 2026-08-05 10:00 | 3 |  | Count sheet | Marisol Reyes | COMPLIANT
2026-08-03 | INV_VARIANCE | Variance review | Inventory | Yusuf Gasparyan | 2026-08-05 10:00 | 2026-08-05 12:00 | 2 | INV_COUNT | Variance log | Marisol Reyes | COMPLIANT
2026-08-03 | INV_SHRINK | Shrink brief | Inventory | Yusuf Gasparyan | 2026-08-05 12:00 | 2026-08-05 13:00 | 1 | INV_VARIANCE | Shrink brief acknowledgment | Marisol Reyes | COMPLIANT
2026-08-03 | SAN_VERIFY | Sanitation verification | Sanitation | Emeric Novak | 2026-08-07 15:00 | 2026-08-07 17:00 | 2 |  | Sanitation verification log | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-10 | ORD_FORECAST | Demand forecast | Ordering | Marisol Reyes | 2026-08-10 08:00 | 2026-08-10 10:00 | 2 |  | Forecast workbook | Amara Draganov | COMPLIANT
2026-08-10 | ORD_DRAFT | Purchase-order draft | Ordering | Marisol Reyes | 2026-08-10 10:00 | 2026-08-10 13:00 | 3 | ORD_FORECAST | Draft PO | Amara Draganov | COMPLIANT
2026-08-10 | ORD_HACCP | HACCP order review | Ordering | Emeric Novak | 2026-08-10 13:00 | 2026-08-10 14:00 | 1 | ORD_DRAFT | HACCP initials | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-10 | ORD_RELEASE | Vendor order release | Ordering | Marisol Reyes | 2026-08-10 14:00 | 2026-08-10 15:00 | 1 | ORD_HACCP | Vendor release confirmation | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-10 | RCV_VERIFY | Delivery verification | Receiving | Yusuf Gasparyan | 2026-08-13 06:00 | 2026-08-13 08:00 | 2 |  | Receiving log | Emeric Novak | COMPLIANT
2026-08-10 | RCV_DISPOSITION | HACCP disposition | Receiving | Emeric Novak | 2026-08-13 08:00 | 2026-08-13 09:00 | 1 | RCV_VERIFY | Disposition entry | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-10 | RCV_TRACE | Lot traceability closeout | Receiving | Emeric Novak | 2026-08-13 09:00 | 2026-08-13 10:00 | 1 | RCV_DISPOSITION | Lot traceability closeout | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-10 | PROD_PLAN | Production cut plan | Production training | Amara Draganov | 2026-08-11 07:00 | 2026-08-11 10:00 | 3 |  | Cut plan | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-10 | PROD_DEMO | Closing-crew demonstration | Production training | Amara Draganov | 2026-08-11 10:00 | 2026-08-11 11:00 | 1 | PROD_PLAN | Crew demonstration acknowledgment | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-10 | PROD_RECORD | Competency record | Production training | Amara Draganov | 2026-08-11 11:00 | 2026-08-11 12:00 | 1 | PROD_DEMO | Competency record | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-10 | INV_COUNT | Cycle count | Inventory | Yusuf Gasparyan | 2026-08-12 07:00 | 2026-08-12 10:00 | 3 |  | Count sheet | Marisol Reyes | COMPLIANT
2026-08-10 | INV_VARIANCE | Variance review | Inventory | Yusuf Gasparyan | 2026-08-12 10:00 | 2026-08-12 12:00 | 2 | INV_COUNT | Variance log | Marisol Reyes | COMPLIANT
2026-08-10 | INV_SHRINK | Shrink brief | Inventory | Yusuf Gasparyan | 2026-08-12 12:00 | 2026-08-12 13:00 | 1 | INV_VARIANCE | Shrink brief acknowledgment | Marisol Reyes | COMPLIANT
2026-08-10 | SAN_VERIFY | Sanitation verification | Sanitation | Emeric Novak | 2026-08-14 15:00 | 2026-08-14 17:00 | 2 |  | Sanitation verification log | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-17 | ORD_FORECAST | Demand forecast | Ordering | Marisol Reyes | 2026-08-17 08:00 | 2026-08-17 10:00 | 2 |  | Forecast workbook | Amara Draganov | COMPLIANT
2026-08-17 | ORD_DRAFT | Purchase-order draft | Ordering | Marisol Reyes | 2026-08-17 10:00 | 2026-08-17 13:00 | 3 | ORD_FORECAST | Draft PO | Amara Draganov | COMPLIANT
2026-08-17 | ORD_HACCP | HACCP order review | Ordering | Emeric Novak | 2026-08-17 13:00 | 2026-08-17 14:00 | 1 | ORD_DRAFT | HACCP initials | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-17 | ORD_RELEASE | Vendor order release | Ordering | Marisol Reyes | 2026-08-17 14:00 | 2026-08-17 15:00 | 1 | ORD_HACCP | Vendor release confirmation | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-17 | RCV_VERIFY | Delivery verification | Receiving | Yusuf Gasparyan | 2026-08-20 06:00 | 2026-08-20 08:00 | 2 |  | Receiving log | Emeric Novak | COMPLIANT
2026-08-17 | RCV_DISPOSITION | HACCP disposition | Receiving | Emeric Novak | 2026-08-20 08:00 | 2026-08-20 09:00 | 1 | RCV_VERIFY | Disposition entry | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-17 | RCV_TRACE | Lot traceability closeout | Receiving | Emeric Novak | 2026-08-20 09:00 | 2026-08-20 10:00 | 1 | RCV_DISPOSITION | Lot traceability closeout | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-17 | PROD_PLAN | Production cut plan | Production training | Amara Draganov | 2026-08-18 07:00 | 2026-08-18 10:00 | 3 |  | Cut plan | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-17 | PROD_DEMO | Closing-crew demonstration | Production training | Amara Draganov | 2026-08-18 10:00 | 2026-08-18 11:00 | 1 | PROD_PLAN | Crew demonstration acknowledgment | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-17 | PROD_RECORD | Competency record | Production training | Amara Draganov | 2026-08-18 11:00 | 2026-08-18 12:00 | 1 | PROD_DEMO | Competency record | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-17 | INV_COUNT | Cycle count | Inventory | Yusuf Gasparyan | 2026-08-19 07:00 | 2026-08-19 10:00 | 3 |  | Count sheet | Marisol Reyes | COMPLIANT
2026-08-17 | INV_VARIANCE | Variance review | Inventory | Yusuf Gasparyan | 2026-08-19 10:00 | 2026-08-19 12:00 | 2 | INV_COUNT | Variance log | Marisol Reyes | COMPLIANT
2026-08-17 | INV_SHRINK | Shrink brief | Inventory | Yusuf Gasparyan | 2026-08-19 12:00 | 2026-08-19 13:00 | 1 | INV_VARIANCE | Shrink brief acknowledgment | Marisol Reyes | COMPLIANT
2026-08-17 | SAN_VERIFY | Sanitation verification | Sanitation | Emeric Novak | 2026-08-21 15:00 | 2026-08-21 17:00 | 2 |  | Sanitation verification log | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-24 | ORD_FORECAST | Demand forecast | Ordering | Marisol Reyes | 2026-08-24 08:00 | 2026-08-24 10:00 | 2 |  | Forecast workbook | Amara Draganov | COMPLIANT
2026-08-24 | ORD_DRAFT | Purchase-order draft | Ordering | Marisol Reyes | 2026-08-24 10:00 | 2026-08-24 13:00 | 3 | ORD_FORECAST | Draft PO | Amara Draganov | COMPLIANT
2026-08-24 | ORD_HACCP | HACCP order review | Ordering | Emeric Novak | 2026-08-24 13:00 | 2026-08-24 14:00 | 1 | ORD_DRAFT | HACCP initials | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-24 | ORD_RELEASE | Vendor order release | Ordering | Marisol Reyes | 2026-08-24 14:00 | 2026-08-24 15:00 | 1 | ORD_HACCP | Vendor release confirmation | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-24 | RCV_VERIFY | Delivery verification | Receiving | Yusuf Gasparyan | 2026-08-27 06:00 | 2026-08-27 08:00 | 2 |  | Receiving log | Emeric Novak | COMPLIANT
2026-08-24 | RCV_DISPOSITION | HACCP disposition | Receiving | Emeric Novak | 2026-08-27 08:00 | 2026-08-27 09:00 | 1 | RCV_VERIFY | Disposition entry | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-24 | RCV_TRACE | Lot traceability closeout | Receiving | Emeric Novak | 2026-08-27 09:00 | 2026-08-27 10:00 | 1 | RCV_DISPOSITION | Lot traceability closeout | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-24 | PROD_PLAN | Production cut plan | Production training | Amara Draganov | 2026-08-25 07:00 | 2026-08-25 10:00 | 3 |  | Cut plan | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-24 | PROD_DEMO | Closing-crew demonstration | Production training | Amara Draganov | 2026-08-25 10:00 | 2026-08-25 11:00 | 1 | PROD_PLAN | Crew demonstration acknowledgment | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-24 | PROD_RECORD | Competency record | Production training | Amara Draganov | 2026-08-25 11:00 | 2026-08-25 12:00 | 1 | PROD_DEMO | Competency record | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-24 | INV_COUNT | Cycle count | Inventory | Yusuf Gasparyan | 2026-08-26 07:00 | 2026-08-26 10:00 | 3 |  | Count sheet | Marisol Reyes | COMPLIANT
2026-08-24 | INV_VARIANCE | Variance review | Inventory | Yusuf Gasparyan | 2026-08-26 10:00 | 2026-08-26 12:00 | 2 | INV_COUNT | Variance log | Marisol Reyes | COMPLIANT
2026-08-24 | INV_SHRINK | Shrink brief | Inventory | Yusuf Gasparyan | 2026-08-26 12:00 | 2026-08-26 13:00 | 1 | INV_VARIANCE | Shrink brief acknowledgment | Marisol Reyes | COMPLIANT
2026-08-24 | SAN_VERIFY | Sanitation verification | Sanitation | Emeric Novak | 2026-08-28 15:00 | 2026-08-28 17:00 | 2 |  | Sanitation verification log | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-31 | ORD_FORECAST | Demand forecast | Ordering | Marisol Reyes | 2026-08-31 08:00 | 2026-08-31 10:00 | 2 |  | Forecast workbook | Amara Draganov | COMPLIANT
2026-08-31 | ORD_DRAFT | Purchase-order draft | Ordering | Marisol Reyes | 2026-08-31 10:00 | 2026-08-31 13:00 | 3 | ORD_FORECAST | Draft PO | Amara Draganov | COMPLIANT
2026-08-31 | ORD_HACCP | HACCP order review | Ordering | Emeric Novak | 2026-08-31 13:00 | 2026-08-31 14:00 | 1 | ORD_DRAFT | HACCP initials | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-31 | ORD_RELEASE | Vendor order release | Ordering | Marisol Reyes | 2026-08-31 14:00 | 2026-08-31 15:00 | 1 | ORD_HACCP | Vendor release confirmation | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-31 | RCV_VERIFY | Delivery verification | Receiving | Yusuf Gasparyan | 2026-09-03 06:00 | 2026-09-03 08:00 | 2 |  | Receiving log | Emeric Novak | COMPLIANT
2026-08-31 | RCV_DISPOSITION | HACCP disposition | Receiving | Emeric Novak | 2026-09-03 08:00 | 2026-09-03 09:00 | 1 | RCV_VERIFY | Disposition entry | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-31 | RCV_TRACE | Lot traceability closeout | Receiving | Emeric Novak | 2026-09-03 09:00 | 2026-09-03 10:00 | 1 | RCV_DISPOSITION | Lot traceability closeout | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-31 | PROD_PLAN | Production cut plan | Production training | Amara Draganov | 2026-09-01 07:00 | 2026-09-01 10:00 | 3 |  | Cut plan | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-31 | PROD_DEMO | Closing-crew demonstration | Production training | Amara Draganov | 2026-09-01 10:00 | 2026-09-01 11:00 | 1 | PROD_PLAN | Crew demonstration acknowledgment | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-31 | PROD_RECORD | Competency record | Production training | Amara Draganov | 2026-09-01 11:00 | 2026-09-01 12:00 | 1 | PROD_DEMO | Competency record | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-08-31 | INV_COUNT | Cycle count | Inventory | Yusuf Gasparyan | 2026-09-02 07:00 | 2026-09-02 10:00 | 3 |  | Count sheet | Marisol Reyes | COMPLIANT
2026-08-31 | INV_VARIANCE | Variance review | Inventory | Yusuf Gasparyan | 2026-09-02 10:00 | 2026-09-02 12:00 | 2 | INV_COUNT | Variance log | Marisol Reyes | COMPLIANT
2026-08-31 | INV_SHRINK | Shrink brief | Inventory | Yusuf Gasparyan | 2026-09-02 12:00 | 2026-09-02 13:00 | 1 | INV_VARIANCE | Shrink brief acknowledgment | Marisol Reyes | COMPLIANT
2026-08-31 | SAN_VERIFY | Sanitation verification | Sanitation | Emeric Novak | 2026-09-04 15:00 | 2026-09-04 17:00 | 2 |  | Sanitation verification log | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-07 | ORD_FORECAST | Demand forecast | Ordering | Marisol Reyes | 2026-09-08 12:00 | 2026-09-08 14:00 | 2 |  | Forecast workbook | Amara Draganov | COMPLIANT
2026-09-07 | ORD_DRAFT | Purchase-order draft | Ordering | Marisol Reyes | 2026-09-08 14:00 | 2026-09-08 17:00 | 3 | ORD_FORECAST | Draft PO | Amara Draganov | COMPLIANT
2026-09-07 | ORD_HACCP | HACCP order review | Ordering | Emeric Novak | 2026-09-08 17:00 | 2026-09-08 18:00 | 1 | ORD_DRAFT | HACCP initials | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-07 | ORD_RELEASE | Vendor order release | Ordering | Marisol Reyes | 2026-09-08 18:00 | 2026-09-08 19:00 | 1 | ORD_HACCP | Vendor release confirmation | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-07 | RCV_VERIFY | Delivery verification | Receiving | Yusuf Gasparyan | 2026-09-11 06:00 | 2026-09-11 08:00 | 2 |  | Receiving log | Emeric Novak | COMPLIANT
2026-09-07 | RCV_DISPOSITION | HACCP disposition | Receiving | Emeric Novak | 2026-09-11 08:00 | 2026-09-11 09:00 | 1 | RCV_VERIFY | Disposition entry | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-07 | RCV_TRACE | Lot traceability closeout | Receiving | Emeric Novak | 2026-09-11 09:00 | 2026-09-11 10:00 | 1 | RCV_DISPOSITION | Lot traceability closeout | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-07 | PROD_PLAN | Production cut plan | Production training | Amara Draganov | 2026-09-09 13:30 | 2026-09-09 16:30 | 3 |  | Cut plan | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-07 | PROD_DEMO | Closing-crew demonstration | Production training | Amara Draganov | 2026-09-09 16:30 | 2026-09-09 17:30 | 1 | PROD_PLAN | Crew demonstration acknowledgment | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-07 | PROD_RECORD | Competency record | Production training | Amara Draganov | 2026-09-09 17:30 | 2026-09-09 18:30 | 1 | PROD_DEMO | Competency record | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-07 | INV_COUNT | Cycle count | Inventory | Yusuf Gasparyan | 2026-09-10 10:30 | 2026-09-10 13:30 | 3 |  | Count sheet | Marisol Reyes | COMPLIANT
2026-09-07 | INV_VARIANCE | Variance review | Inventory | Yusuf Gasparyan | 2026-09-10 13:30 | 2026-09-10 15:30 | 2 | INV_COUNT | Variance log | Marisol Reyes | COMPLIANT
2026-09-07 | INV_SHRINK | Shrink brief | Inventory | Yusuf Gasparyan | 2026-09-10 15:30 | 2026-09-10 16:30 | 1 | INV_VARIANCE | Shrink brief acknowledgment | Marisol Reyes | COMPLIANT
2026-09-07 | SAN_VERIFY | Sanitation verification | Sanitation | Emeric Novak | 2026-09-11 17:30 | 2026-09-11 19:30 | 2 |  | Sanitation verification log | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-14 | ORD_FORECAST | Demand forecast | Ordering | Marisol Reyes | 2026-09-14 08:00 | 2026-09-14 10:00 | 2 |  | Forecast workbook | Amara Draganov | COMPLIANT
2026-09-14 | ORD_DRAFT | Purchase-order draft | Ordering | Marisol Reyes | 2026-09-14 10:00 | 2026-09-14 13:00 | 3 | ORD_FORECAST | Draft PO | Amara Draganov | COMPLIANT
2026-09-14 | ORD_HACCP | HACCP order review | Ordering | Emeric Novak | 2026-09-14 13:00 | 2026-09-14 14:00 | 1 | ORD_DRAFT | HACCP initials | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-14 | ORD_RELEASE | Vendor order release | Ordering | Marisol Reyes | 2026-09-14 14:00 | 2026-09-14 15:00 | 1 | ORD_HACCP | Vendor release confirmation | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-14 | RCV_VERIFY | Delivery verification | Receiving | Yusuf Gasparyan | 2026-09-17 06:00 | 2026-09-17 08:00 | 2 |  | Receiving log | Emeric Novak | COMPLIANT
2026-09-14 | RCV_DISPOSITION | HACCP disposition | Receiving | Emeric Novak | 2026-09-17 08:00 | 2026-09-17 09:00 | 1 | RCV_VERIFY | Disposition entry | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-14 | RCV_TRACE | Lot traceability closeout | Receiving | Emeric Novak | 2026-09-17 09:00 | 2026-09-17 10:00 | 1 | RCV_DISPOSITION | Lot traceability closeout | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-14 | PROD_PLAN | Production cut plan | Production training | Amara Draganov | 2026-09-15 07:00 | 2026-09-15 10:00 | 3 |  | Cut plan | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-14 | PROD_DEMO | Closing-crew demonstration | Production training | Amara Draganov | 2026-09-15 10:00 | 2026-09-15 11:00 | 1 | PROD_PLAN | Crew demonstration acknowledgment | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-14 | PROD_RECORD | Competency record | Production training | Amara Draganov | 2026-09-15 11:00 | 2026-09-15 12:00 | 1 | PROD_DEMO | Competency record | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-14 | INV_COUNT | Cycle count | Inventory | Yusuf Gasparyan | 2026-09-16 07:00 | 2026-09-16 10:00 | 3 |  | Count sheet | Marisol Reyes | COMPLIANT
2026-09-14 | INV_VARIANCE | Variance review | Inventory | Yusuf Gasparyan | 2026-09-16 10:00 | 2026-09-16 12:00 | 2 | INV_COUNT | Variance log | Marisol Reyes | COMPLIANT
2026-09-14 | INV_SHRINK | Shrink brief | Inventory | Yusuf Gasparyan | 2026-09-16 12:00 | 2026-09-16 13:00 | 1 | INV_VARIANCE | Shrink brief acknowledgment | Marisol Reyes | COMPLIANT
2026-09-14 | SAN_VERIFY | Sanitation verification | Sanitation | Emeric Novak | 2026-09-18 15:00 | 2026-09-18 17:00 | 2 |  | Sanitation verification log | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-21 | ORD_FORECAST | Demand forecast | Ordering | Marisol Reyes | 2026-09-21 08:00 | 2026-09-21 10:00 | 2 |  | Forecast workbook | Amara Draganov | COMPLIANT
2026-09-21 | ORD_DRAFT | Purchase-order draft | Ordering | Marisol Reyes | 2026-09-21 10:00 | 2026-09-21 13:00 | 3 | ORD_FORECAST | Draft PO | Amara Draganov | COMPLIANT
2026-09-21 | ORD_HACCP | HACCP order review | Ordering | Emeric Novak | 2026-09-21 13:00 | 2026-09-21 14:00 | 1 | ORD_DRAFT | HACCP initials | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-21 | ORD_RELEASE | Vendor order release | Ordering | Marisol Reyes | 2026-09-21 14:00 | 2026-09-21 15:00 | 1 | ORD_HACCP | Vendor release confirmation | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-21 | RCV_VERIFY | Delivery verification | Receiving | Yusuf Gasparyan | 2026-09-24 06:00 | 2026-09-24 08:00 | 2 |  | Receiving log | Emeric Novak | COMPLIANT
2026-09-21 | RCV_DISPOSITION | HACCP disposition | Receiving | Emeric Novak | 2026-09-24 08:00 | 2026-09-24 09:00 | 1 | RCV_VERIFY | Disposition entry | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-21 | RCV_TRACE | Lot traceability closeout | Receiving | Emeric Novak | 2026-09-24 09:00 | 2026-09-24 10:00 | 1 | RCV_DISPOSITION | Lot traceability closeout | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-21 | PROD_PLAN | Production cut plan | Production training | Amara Draganov | 2026-09-22 07:00 | 2026-09-22 10:00 | 3 |  | Cut plan | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-21 | PROD_DEMO | Closing-crew demonstration | Production training | Amara Draganov | 2026-09-22 10:00 | 2026-09-22 11:00 | 1 | PROD_PLAN | Crew demonstration acknowledgment | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-21 | PROD_RECORD | Competency record | Production training | Amara Draganov | 2026-09-22 11:00 | 2026-09-22 12:00 | 1 | PROD_DEMO | Competency record | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-21 | INV_COUNT | Cycle count | Inventory | Yusuf Gasparyan | 2026-09-23 07:00 | 2026-09-23 10:00 | 3 |  | Count sheet | Marisol Reyes | COMPLIANT
2026-09-21 | INV_VARIANCE | Variance review | Inventory | Yusuf Gasparyan | 2026-09-23 10:00 | 2026-09-23 12:00 | 2 | INV_COUNT | Variance log | Marisol Reyes | COMPLIANT
2026-09-21 | INV_SHRINK | Shrink brief | Inventory | Yusuf Gasparyan | 2026-09-23 12:00 | 2026-09-23 13:00 | 1 | INV_VARIANCE | Shrink brief acknowledgment | Marisol Reyes | COMPLIANT
2026-09-21 | SAN_VERIFY | Sanitation verification | Sanitation | Emeric Novak | 2026-09-25 15:00 | 2026-09-25 17:00 | 2 |  | Sanitation verification log | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-28 | ORD_FORECAST | Demand forecast | Ordering | Marisol Reyes | 2026-09-28 08:00 | 2026-09-28 10:00 | 2 |  | Forecast workbook | Amara Draganov | COMPLIANT
2026-09-28 | ORD_DRAFT | Purchase-order draft | Ordering | Marisol Reyes | 2026-09-28 10:00 | 2026-09-28 13:00 | 3 | ORD_FORECAST | Draft PO | Amara Draganov | COMPLIANT
2026-09-28 | ORD_HACCP | HACCP order review | Ordering | Emeric Novak | 2026-09-28 13:00 | 2026-09-28 14:00 | 1 | ORD_DRAFT | HACCP initials | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-28 | ORD_RELEASE | Vendor order release | Ordering | Marisol Reyes | 2026-09-28 14:00 | 2026-09-28 15:00 | 1 | ORD_HACCP | Vendor release confirmation | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-28 | RCV_VERIFY | Delivery verification | Receiving | Yusuf Gasparyan | 2026-10-01 06:00 | 2026-10-01 08:00 | 2 |  | Receiving log | Emeric Novak | COMPLIANT
2026-09-28 | RCV_DISPOSITION | HACCP disposition | Receiving | Emeric Novak | 2026-10-01 08:00 | 2026-10-01 09:00 | 1 | RCV_VERIFY | Disposition entry | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-28 | RCV_TRACE | Lot traceability closeout | Receiving | Emeric Novak | 2026-10-01 09:00 | 2026-10-01 10:00 | 1 | RCV_DISPOSITION | Lot traceability closeout | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-28 | PROD_PLAN | Production cut plan | Production training | Amara Draganov | 2026-09-29 07:00 | 2026-09-29 10:00 | 3 |  | Cut plan | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-28 | PROD_DEMO | Closing-crew demonstration | Production training | Amara Draganov | 2026-09-29 10:00 | 2026-09-29 11:00 | 1 | PROD_PLAN | Crew demonstration acknowledgment | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-28 | PROD_RECORD | Competency record | Production training | Amara Draganov | 2026-09-29 11:00 | 2026-09-29 12:00 | 1 | PROD_DEMO | Competency record | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-09-28 | INV_COUNT | Cycle count | Inventory | Yusuf Gasparyan | 2026-09-30 07:00 | 2026-09-30 10:00 | 3 |  | Count sheet | Marisol Reyes | COMPLIANT
2026-09-28 | INV_VARIANCE | Variance review | Inventory | Yusuf Gasparyan | 2026-09-30 10:00 | 2026-09-30 12:00 | 2 | INV_COUNT | Variance log | Marisol Reyes | COMPLIANT
2026-09-28 | INV_SHRINK | Shrink brief | Inventory | Yusuf Gasparyan | 2026-09-30 12:00 | 2026-09-30 13:00 | 1 | INV_VARIANCE | Shrink brief acknowledgment | Marisol Reyes | COMPLIANT
2026-09-28 | SAN_VERIFY | Sanitation verification | Sanitation | Emeric Novak | 2026-10-02 15:00 | 2026-10-02 17:00 | 2 |  | Sanitation verification log | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-10-05 | ORD_FORECAST | Demand forecast | Ordering | Marisol Reyes | 2026-10-05 08:00 | 2026-10-05 10:00 | 2 |  | Forecast workbook | Amara Draganov | COMPLIANT
2026-10-05 | ORD_DRAFT | Purchase-order draft | Ordering | Marisol Reyes | 2026-10-05 10:00 | 2026-10-05 13:00 | 3 | ORD_FORECAST | Draft PO | Amara Draganov | COMPLIANT
2026-10-05 | ORD_HACCP | HACCP order review | Ordering | Emeric Novak | 2026-10-05 13:00 | 2026-10-05 14:00 | 1 | ORD_DRAFT | HACCP initials | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-10-05 | ORD_RELEASE | Vendor order release | Ordering | Marisol Reyes | 2026-10-05 14:00 | 2026-10-05 15:00 | 1 | ORD_HACCP | Vendor release confirmation | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-10-05 | RCV_VERIFY | Delivery verification | Receiving | Yusuf Gasparyan | 2026-10-08 06:00 | 2026-10-08 08:00 | 2 |  | Receiving log | Emeric Novak | COMPLIANT
2026-10-05 | RCV_DISPOSITION | HACCP disposition | Receiving | Emeric Novak | 2026-10-08 08:00 | 2026-10-08 09:00 | 1 | RCV_VERIFY | Disposition entry | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-10-05 | RCV_TRACE | Lot traceability closeout | Receiving | Emeric Novak | 2026-10-08 09:00 | 2026-10-08 10:00 | 1 | RCV_DISPOSITION | Lot traceability closeout | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-10-05 | PROD_PLAN | Production cut plan | Production training | Amara Draganov | 2026-10-06 07:00 | 2026-10-06 10:00 | 3 |  | Cut plan | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-10-05 | PROD_DEMO | Closing-crew demonstration | Production training | Amara Draganov | 2026-10-06 10:00 | 2026-10-06 11:00 | 1 | PROD_PLAN | Crew demonstration acknowledgment | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-10-05 | PROD_RECORD | Competency record | Production training | Amara Draganov | 2026-10-06 11:00 | 2026-10-06 12:00 | 1 | PROD_DEMO | Competency record | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT
2026-10-05 | INV_COUNT | Cycle count | Inventory | Yusuf Gasparyan | 2026-10-07 07:00 | 2026-10-07 10:00 | 3 |  | Count sheet | Marisol Reyes | COMPLIANT
2026-10-05 | INV_VARIANCE | Variance review | Inventory | Yusuf Gasparyan | 2026-10-07 10:00 | 2026-10-07 12:00 | 2 | INV_COUNT | Variance log | Marisol Reyes | COMPLIANT
2026-10-05 | INV_SHRINK | Shrink brief | Inventory | Yusuf Gasparyan | 2026-10-07 12:00 | 2026-10-07 13:00 | 1 | INV_VARIANCE | Shrink brief acknowledgment | Marisol Reyes | COMPLIANT
2026-10-05 | SAN_VERIFY | Sanitation verification | Sanitation | Emeric Novak | 2026-10-09 15:00 | 2026-10-09 17:00 | 2 |  | Sanitation verification log | NO QUALIFIED BACKUP — GM ESCALATION | COMPLIANT

## Weekly Controls
Weekly Hours by Owner and compliance controls
Formula controls recalculate from Duty Schedule; capacities from current people extract.
Operational Week | Owner | Weekly Hours by Owner | Interim cap | Hours Status | Timing Status | Weekly Control
2026-07-06 | Emeric Novak | 5 | 5 | COMPLIANT | COMPLIANT | COMPLIANT
2026-07-06 | Marisol Reyes | 6 | 7 | COMPLIANT | COMPLIANT | COMPLIANT
2026-07-06 | Amara Draganov | 5 | 6 | COMPLIANT | COMPLIANT | COMPLIANT
2026-07-06 | Yusuf Gasparyan | 8 | 8 | COMPLIANT | COMPLIANT | COMPLIANT
2026-07-13 | Emeric Novak | 5 | 5 | COMPLIANT | COMPLIANT | COMPLIANT
2026-07-13 | Marisol Reyes | 6 | 7 | COMPLIANT | COMPLIANT | COMPLIANT
2026-07-13 | Amara Draganov | 5 | 6 | COMPLIANT | COMPLIANT | COMPLIANT
2026-07-13 | Yusuf Gasparyan | 8 | 8 | COMPLIANT | COMPLIANT | COMPLIANT
2026-07-20 | Emeric Novak | 5 | 5 | COMPLIANT | COMPLIANT | COMPLIANT
2026-07-20 | Marisol Reyes | 6 | 7 | COMPLIANT | COMPLIANT | COMPLIANT
2026-07-20 | Amara Draganov | 5 | 6 | COMPLIANT | COMPLIANT | COMPLIANT
2026-07-20 | Yusuf Gasparyan | 8 | 8 | COMPLIANT | COMPLIANT | COMPLIANT
2026-07-27 | Emeric Novak | 5 | 5 | COMPLIANT | COMPLIANT | COMPLIANT
2026-07-27 | Marisol Reyes | 6 | 7 | COMPLIANT | COMPLIANT | COMPLIANT
2026-07-27 | Amara Draganov | 5 | 6 | COMPLIANT | COMPLIANT | COMPLIANT
2026-07-27 | Yusuf Gasparyan | 8 | 8 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-03 | Emeric Novak | 5 | 5 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-03 | Marisol Reyes | 6 | 7 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-03 | Amara Draganov | 5 | 6 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-03 | Yusuf Gasparyan | 8 | 8 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-10 | Emeric Novak | 5 | 5 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-10 | Marisol Reyes | 6 | 7 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-10 | Amara Draganov | 5 | 6 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-10 | Yusuf Gasparyan | 8 | 8 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-17 | Emeric Novak | 5 | 5 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-17 | Marisol Reyes | 6 | 7 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-17 | Amara Draganov | 5 | 6 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-17 | Yusuf Gasparyan | 8 | 8 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-24 | Emeric Novak | 5 | 5 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-24 | Marisol Reyes | 6 | 7 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-24 | Amara Draganov | 5 | 6 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-24 | Yusuf Gasparyan | 8 | 8 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-31 | Emeric Novak | 5 | 5 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-31 | Marisol Reyes | 6 | 7 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-31 | Amara Draganov | 5 | 6 | COMPLIANT | COMPLIANT | COMPLIANT
2026-08-31 | Yusuf Gasparyan | 8 | 8 | COMPLIANT | COMPLIANT | COMPLIANT
2026-09-07 | Emeric Novak | 5 | 5 | COMPLIANT | COMPLIANT | COMPLIANT
2026-09-07 | Marisol Reyes | 6 | 7 | COMPLIANT | COMPLIANT | COMPLIANT
2026-09-07 | Amara Draganov | 5 | 6 | COMPLIANT | COMPLIANT | COMPLIANT
2026-09-07 | Yusuf Gasparyan | 8 | 8 | COMPLIANT | COMPLIANT | COMPLIANT
2026-09-14 | Emeric Novak | 5 | 5 | COMPLIANT | COMPLIANT | COMPLIANT
2026-09-14 | Marisol Reyes | 6 | 7 | COMPLIANT | COMPLIANT | COMPLIANT
2026-09-14 | Amara Draganov | 5 | 6 | COMPLIANT | COMPLIANT | COMPLIANT
2026-09-14 | Yusuf Gasparyan | 8 | 8 | COMPLIANT | COMPLIANT | COMPLIANT
2026-09-21 | Emeric Novak | 5 | 5 | COMPLIANT | COMPLIANT | COMPLIANT
2026-09-21 | Marisol Reyes | 6 | 7 | COMPLIANT | COMPLIANT | COMPLIANT
2026-09-21 | Amara Draganov | 5 | 6 | COMPLIANT | COMPLIANT | COMPLIANT
2026-09-21 | Yusuf Gasparyan | 8 | 8 | COMPLIANT | COMPLIANT | COMPLIANT
2026-09-28 | Emeric Novak | 5 | 5 | COMPLIANT | COMPLIANT | COMPLIANT
2026-09-28 | Marisol Reyes | 6 | 7 | COMPLIANT | COMPLIANT | COMPLIANT
2026-09-28 | Amara Draganov | 5 | 6 | COMPLIANT | COMPLIANT | COMPLIANT
2026-09-28 | Yusuf Gasparyan | 8 | 8 | COMPLIANT | COMPLIANT | COMPLIANT
2026-10-05 | Emeric Novak | 5 | 5 | COMPLIANT | COMPLIANT | COMPLIANT
2026-10-05 | Marisol Reyes | 6 | 7 | COMPLIANT | COMPLIANT | COMPLIANT
2026-10-05 | Amara Draganov | 5 | 6 | COMPLIANT | COMPLIANT | COMPLIANT
2026-10-05 | Yusuf Gasparyan | 8 | 8 | COMPLIANT | COMPLIANT | COMPLIANT